## Teams_Follow_Up
Team No. | Audit/Drops | Rig No. | Well Name | Field | Job Type | Job No. | Starting Date | Job Days | Expected Rig
1 | Audit
2 | Audit | ECDC-9 | SIWA-V1X (ST) | Fagora | CA | D_CA23_ECDC-9_31 | 2023-08-12 | 2 | EDC-91
3 | Audit | EDC-42 | Carnarvon N-1X | Carnarvon | FCS-3 | D_FCS323_42_24 | 2023-08-06 | 7 | EDC-40
2 | Drops | EDC-53 | OAKHIL-1X | AG | 3rd | D_DRP23_53_97 | 2023-08-10 | 3 | Home
1 | Drops
3 | Drops

## Critical_Points_Follow_Up
Rig No. | Point | Description | Final Status
ECDC-9 | No | No
EDC-42 | 5.9.22 | Only one PAD SET FOR AED (automated external defibrillator) used for CPR in the clinic found expired from 17-4-2023, new valid sets need to be provided ASAP | Open
EDC-42 | 2.3.61 | MP no.1 (high pressure hose Vibrator Hose) between H.P surface line and stand pipe damaged in outer rubber shield and the metal shield is corroded, in need to be replaced as per API STD clear mention. | Open
EDC-42 | 3.1.35 | Two BOP control system lines damaged in outer shield and there is a damage in metal shield, all BOP control line has to be fire resistance and manufacture according API 16 D in need to be replaced. | Open
EDC-42 | 4.10.63 | There is inline receptacle used to supply diesel heater not Ex-type and it is left unused and without its protection cap HIPO of short circuit or spark to be happened. | Open
EDC-42 | 5.8.92 | Highly greased oil observed accumulated below the Kitchen fryer also the oil pans below fryers observed full of oil that present a serious fire hazard, require a deep cleaning and empty the pans periodically | Open
EDC-42 | 4 | Fuel purifier AC motor isn’t EX-type, need to be replaced by EX-type motor. | Open
EDC-42 | 5 | During carrying out F/T for Diesel Fire Pump, the water flow rate observed as pulses and the gauge giving fluctuated reading not a stable reading which should be (minimum accepted flow rate pressure 75 Psi), maintenance required ASAP. | Open