## S.B.Report
KHALDA PETROLEUM CO.
|  |  | AM DRILLING REPORT | TEAM-1-DRLG | 2023-09-02 15:29 | 0
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS
ST-5 | MRZK-207 | 12 1/4" | R/U 97 % | MOVE PLAN
1500 HP / TOP DRIVE | OIL | SPUD MUD | >> RIG RELEASED F/ BOLT 116-1X T/ MRZK-207 ON 31-7-2023 @ 10:00 A.M | BOP TO BE RECHECKED
| DEVELOPMENT |  | >> EXPECTED TO SPUD IN +/- 23/8/2023 | INSPECTION ON ALL BHA (DONE)
ISLAM EL-TAHER | DEVIATED | SLB - MUD | >> WILL USE 21 1/4" DIVERTER IN SURFACE HOLE ( ON LOCATION ) | CAT IV INSPECTION FOR HANDLING TOOLS (DONE)
| Military /MINE./EGPC/Env. Approval | SLB- MONEL & MULTISHOT | >> N/U 21 1/4" DIVERTER W/ VENT LINE INSTALLED | CHANGE THE CLIMB ASSISTANT WIRE (DONE)
| YES/ OUT OF HI RESK AREA / VERBAL / IN PROGRESS | SLB. - DIR. |  | MPI INSPEC. FOR PAD EYE WHICH HANG THE HANG OFF LINK & TDS (DONE)
010-11150765 ( C.M ) | 9 5/8'' CSG, (36 #, K-55, BTC) @ 3597' | SLB - CMT. |  | GUIDE & RE-ENFORCEMENT OF TIE BACK BEAM AS PER EPHH ( DONE )
012-83909318 ( C.M ) | (± 30' INTO APOLL. FM) | SLB TO HANDLE -TONG |  | CHANGE THE MONKEY BOARD AIR HOIST WIRE (DONE)
| 7" CSG (26# , N-80, BTC) @ 7475' | UNICO - R.REAMER | >> PERFORMED GYRO SURVEY IN THE OFFSET WELL MRZK-121 | COMPLETE SERVICE FOR POWER TONG.
01280141419 ( T.P ) | (± 257' INTO KHARITA FM .) | ` |  | HYDR. P/T FOR VALVES & PIPES & HOSES, PRV & GAUGES CALIBRATION (IN PROGRESS)
|  | M.I- CENTRIFUGE. | >> FRESH WTR PIT- : 100 % FULL ( WHITE HORSE ) | REPAIR FIXED GAS SYSTEM (H2S AND LEL SYSTEM) | RIG RELEASE
RIG SUPT: ISMAIL |  | WASTE MANGMENT: M.I | >> DRILL WTR PIT : 100 % FULL ( GREEN VALLY LINE ) | RAISING LINES & BRIDLE INSPECTION ( DONE )
012-27853358 | OFFSET WELLS: | LINER HGR - SLB | ** TARGET TOLERANCE: 50 M. | CALIBRATION FOR FIRE SUPPRESSION SYSTEM AT MAIN CAMP KITCHEN
| MRZK-121 & MRZK-135 | CRT: PREMIER | ** DIESEL STOCK ENOUGH FOR 4 DAYS. | MULTI GAS DETECTORS CALIBRATION (DONE)
V-SAT : 980-0090 |  |  | ** PRIMARY / SEC.: AR-G DOL. & U-BAH / L-BAH | FIX EMERGENCY DIESEL ENGINE RADIATOR (DONE)
| TD: 7,475' |  | ** ACTUAL / PROPOSED: --/-- DAYS.
EDC - 1 | SHADOW-E09 | 17 1/2" | R/D: 100 % R/M: 90 % R/U: 50 %. | MOVE PLAN:
1500 HP / TDS / RKB: 30' | OIL | HOLE | >> RIG RELEASED T/ SHADOW-E09 ON 17-Aug-2023 @ 10:00 AM. | >> BHA INSPECTION. | SHADOW-W-02
| VERTICAL | SPUD MUD | >> MOVE DISTANCE F/ SWAG-N6 T/SHADOW-E09: 6 KM (DESERT ROAD). | >> CHECK & GRESE TDS, CHECK TDS GUIDE, CHANGE WASH PIPE. | Militry /MINE./EGPC/Env. Approval
MOHAMED ALAA | Militry /MINE./EGPC/Env. Approval |  | >> OLD LOCATION EXPECTED TO BE CLEARE ON 22-Aug-2023. | >> CHECK MUD PUMP# 1 & 2 & CHANGE LINER FROM 5.5" TO 6.5" | NO / OUT OF HIGH RISK AREA / NO / NO
AHMED GAMAL | YES / OUT OF HIGH RISK AREA / | EMEC- MUD. | >> EXPECTED TO SPUD IN ON ± 25-Aug-2023 | >> CHECK & SERVICE DC MOTORS OF DRAWWORK. | OIL
| VERBAL / NO | SLB.- DIR. | >> FIN'D HAMMERING CONDUCTOR ON 19-Aug-2023. | >> CHECK & REPAIR MUST LIGHT. | TD. 14000'.
| 20" CONDUCTOR @ 43' | HALL - CMT. | >> DIESEL STOCK @ RIG RELEASE: 23,472 GAL. | >> COMPLETE SERVICE FOR HYDRULIC POWER TONG. | NEED TO STAKE
01283909327 (C.M) | 13 3/8" SURF. CSG @ 3,360' | W.FORD -TRS | >> TOTAL RIG LOAD ± 160 LOAD . | >> CHECK & SERVICE DC MOTORS OF MUD PUMPS. | CONSTRUCTION CO.: AL SHROUK
02-27063387(C.M) | (23' INTO APOL-A) | GESCO- JAR & SH. SUB. | >> 4/5 CONVOYS MOVED TO NEW LOCATION.
0224062501 (T.P) | 9 5/8" INTER CSG @ 8,800' | WAVE- R.REAMER | >> FRSH WTR PIT: 5 % FULL. >> DRILL WTR PIT: 5 % FULL. |  | WD-9 F-1X
| (79' INTO A/R-B) | WOOD - STAB. | >> HUMMERED 20" CONDUCTOR TO 43' |  | Militry /MINE./EGPC/Env. Approval
| 7" LINER CSG @ 14,000' | BAROID - CENTRIFUGE. | >> NEED URGENT WATER TRUCKS TO FILL WATER PITS |  | NO / OUT OF HIGH RISK AREA / NO / NO
|  | W.FORD - LINER HGR | >> RECEIVED ONLY 1 STD BY WTR TRUCKS |  | OIL
RIG SUPT: AHMED SAMIR | OFFSET WELLS: | AG WTR PIT | ** TARGET TOLERANCE: 50 M. |  | TD. 14000'.
012-21112001 | SHADOW-E08X | SINAI - D. WTR. | ** DIESEL STOCK ENOUGH FOR 6 DAYS. |  | NEED TO STAKE
|  |  | ** PRIMARY/ SECONDARY OBJECTIVE: XXX/XX |  | CONSTRUCTION CO.: ??? |  | Attia AbdElaziz
V-SAT : 980-0991 | TD: 14000' |  | ** ACTUAL/PROPOSED @ CURRENT DEPTH: XX/ XX DAYS. |  |  |  | Hany Allam
EDC - 11 | WKAN-N-7 | 8 1/2" HOLE | DRLG @ 12,830' PROG: 95 FT AV. ROP: 31.7 FPH C.ROP: 30 FPH | CONT. DRLG 8 1/2" VERTICAL HOLE TO +/- 14500'. |  |  | Ahmed Barkat
1500 HP / TOP DRIVE | OIL | KCL POLYMER | BIT (DD407VTX) FTG: 1165' HRS: 41.5 ON-BTM: 36.2 ROP: 32.2 FPH | >> LAST TRIP @11665'. | TANZNITE-2 (Deepening) |  | Mohsen Ashour
| VERTICAL |  | MASAJID @ 11,913' 40% LST & 60% SH @ 12,770' GAS: 0.27% | >> MUD PLAN CONTINUE W/10.4 PPG UNTIL PASS ZAHRA FORM. | Militry /MINE./EGPC/Env. Approval |  | Khaled Ghanaym
HOSSAM ESSAM | Militry /MINE./EGPC/Env. Approval |  | LOSSES: 12/7 BPH M.WT: 10.4 PPG OFF/ON- TRQ: 4/5-8 K-FT.LB | INREASE MW T/ 10.6 IN STEPS WHILE RECORDING LOSSES , | YES / NO NEED (RE-ENTRY ) / NO / NO |  | 01275111158
HASSAN ABD ALHAMEED | YES/RISK ASSESS.DONE BY OPER. / | Mud: M.I | WOB: 20-25 KLB RPM: 120 GPM: 400 P.P.: 1900 PSI | OFFSET WELLS: | OIL |  | Belal Sallouma
| VERBAL / IN PROGRESS | CMT: SLB | >> WASH & REAM EVERY STD. | WKAN-N1X: WHILE BIT & BHA CHANGE @ 13308, WHILE RIH, STRING | TD 14000'. |  | 01279539944
01282130459 ( C.M ) | SURF. CSG (68 PPG K-55, BTC) @ | TRS : SAPESCO | >> RECORD MWD SURVEY EVERY 2 STD'S BEFORE CONN.. | GOT STUCK @ 13290', WORK ON SAME TILL FREE (WELLBORE | READY TO H/O |  | Amr AbdElaziz
01094226663 (C.M.) | 2950 (58' INTO APOLL.) | JAR : W.F | >> ZAHRA PROGNOISIS DEPTH @ 12785 FT | STABILITY U& L-SAFA) | CONSTRUCTION CO: ELMANSOURA |  | Mohamed Abd Elsalam
| 9 5/8" CSG (43.5 ,47 PPF, N-80, BTC) @ 8150' | Centrifuge: MI SWACO |  | WKAN-N03: LOSSES 15 BPH @ 11,310 (BTM AEB-6) CURED W/CLM | HERNUFER E-9 |  | Walid Sallam
01221112116 ( T.P ) | (88 FT INTO AEB-1) | Reamer: UNICO | >> HAD 900 BBL OBM & WASTE MANAGEMENT EQUIPMENT AND CREW | @ 13496' HAD GASES INCREASED T/ 3% W/O CUT IN MWT., VERY | Militry /MINE./EGPC/Env. Approval |  | Esam Eid
| 7" LINER (29 PPF,HC, BTC) @ +/- 14500 | Stabilizer: Wood | SURVEY: | HIGH DIFF. STICKING TENDENCY INCREASED BRIDGING CONC. (STILL HAD HIGH TENDENCY) | YES / NO / NO / NO |  | Dan Mullinus
RIG SUPT:ABDALLAH IBRAHIM |  | WASTE MANGMENT: M.I | MD: 12661' INC: 0.8⁰ AZM: 131.69° TVD: 12660.59' V.SEC: 29.56' | CHEMC CONC: 10 PPB MARBLE,3 PPB STRATAHEAL4-5 PPB SOLTEX. | WIW |  | 01277612182
01212009267 |  | WATER: WHITE HORSE | DLS: 0.12° | MUD PARAM:VIS: 45, YP: 22, PV: 24, GEL:8/12, W.L: 4.7, PH: 10.2, CL:120 K. | TD 15000'. |  | Stan Jackson
V-SAT: 980-0931 | OFFSET WELLS: |  | ** DIESEL STOCK ENOUGH FOR 4 DAYS. | BHA: 8 ½” PDC BIT + BIT SUB + 1 X 6 ½” D/C++ 8 3/8” R.REAMER + | NEED TO BUILD |  | Charlie Kennedy
PMP: 3724 | WKAN N-3 & WKAN N-1X |  | ** PRIMARY/ SECONDARY: U. SAFA / AEB-6, MASAJID & L.SAFA | 6 3/4'' D/C + 6 ½” JAR + 2 X 6 ½” D/C + 21 X 5” HWDP | CONSTRUCTION CO: UNION |  | Abdelmageed Ahmed
V-SAT: | T.D: 14,500' | WATER PIT: HADAF -/+ 100 KM | ** ACTUAL/PROPOSED @ CURRENT DEPTH: 21.7 / 33 DAYS. | 8.5" BITS: DD407VTX, GTD74 |  |  | Omar Yahia
AHMED A.ATY | STAN JACKSON | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | DRLG Technical Support : MOH.NASR | Khaled Ghanaym |  | Abd-Alah Taha
TELE: 01000031116 | TELE: 01277612182 | A/G: VERNON 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01220044064 - 01013334556 | 01275111158 |  | Ahmed Elbanauosy
|  |  | KHALDA PETROLEUM CO. |  |  |  | Ahmed AbdElaaty
|  |  | AM DRILLING REPORT | TEAM-1-DRLG | 2023-09-02 15:29 |  | Vernon
RIG | WELL | PHASE | OPERATION |  | REMARKS |  | Abd-Allah Taha
EDC - 17 | BERENICE-28 | 12 1/4'' | R/U 98 % | FIN'D R/U & CHANGE AUXILIARY BRAKE.
1500 HP / TDS / RKB: 26' | OIL | HOLE | >> EXPECTED TO SPUD-IN ON TODAY AFTERNOON. | CHECK RIG FOR ACCEPTANCE & ACCEPT SAME
BOP:13 5/8"-10K PSI WP | DEVIATED | SPUD MUD | >> ACTUAL / TARGET MOVE DAYS: 4.5 / 5 | DRILL 12 1/4 '' HOLE SECTION TO +/- 2600 FT (+/-83 FT INTO APOLL. FM) | BERENICE-32
RATED DRLG DEPTH: 15,000' | Militry /MINE./EGPC/Env. Approval |  | >> RIG RELEASED F/ BERENICE-33 @ 7:00 PM ON AUG 17, 2023. | >> AT +/- 2600 FT (+/-83 FT INTO APOLL. FM) SWEEP HOLE W/ 50 BBL | Militry /MINE./EGPC/Env. Approval
| YES/ OUT OF HIGH RISK AREA /VERBAL / IN PROGRESS |  | >> DIESEL STOCK @ RIG RELEASE : 19,921 GAL. | (0.5 PPB SUPER SWEEP + 5 PPB TANNATHIN + 2% D.D + 10 PPB NUT PLUG/C) | NO/ OUT OF HIGH RISK AREA /NO / NO
|  |  | >> M/U 40 /40 STD X 5'' D/P + 0 / 6 STD X 5'' HWDP + 0 / 7 STD X 6 1/2'' D/C + | HV PILL & PERFORM WIPER TRIP TO BHA DEPTH OR TO SURFACE | CONSTRUCTION CO: EL EKHLAS .
SHADY MAHMOUD | 9 5/8'' CSG (36 #, K-55, BTC) @ 4100' (42 FT INTO A/R-A) |  | 0 / 1 X 8 1/4'' D/C. | RIH BACK & CONT DRILL 12 1/4” HOLE SECTION TO 4,100 FT (42 FT INTO | OIL
AHMED ABBAS |  | MI- MUD. | >> EDC CHANGED AUXILIARY BRAKE. | A/R A FM) CP. | TD. 13000'
| 7" CSG @ 13000' | BAKER - DIR. | >> CHECK & TEST AUXILIARY BRAKE IN PROGRESS. |  | 10% ON GOING
| (± 52 ft INTO BASUR FM) | HALL. - CMT. | >> MIXED 1700 BBL'S SPUD MUD , 250 BBL'S 60 PPB LCM & 50 BBL'S 140 PPB LCM | MUD PLAN:
|  | PREMIERE -TONG. | >> NEED WELL PROGRAM & BIT PLAN URGENT | START DRILLING WITH 25 PRE-HYDRATED BENTONITE SPUD MUD T/ 1000' | BERENICE-47
01205993336 (C.M) |  | WAVE - JAR & SH. SUB. | >> HAD 1 X 6 1/2'' JAR F.HYD W INT. LATCH. | SWITCH OVER TO LIGHT 3% NACL MUD @ +/- 1000 FT. | Militry /MINE./EGPC/Env. Approval
010-62977790 (C.M) |  | WAVE - REAMER & STAB. | >> 12 1/8'' STRG STAB ON LOCATION. | DUMP & DILUTE AS REQUIRED TO KEEP LOW MBT (MBT +/- 10 LB/BBL) | NO/ OUT OF HIGH RISK AREA /NO / NO
012-02032070 (T.P) |  | BAROID - CENTRIFUGE. | >> RECEIVED 850 OBM IN MI TKS FROM BAKER S.B FOR 8 1/2" HOLE. | PRECAUTIONAY SWEEP HOLE WITH 30 BBL HV PILL LOADED W/ 60 PPB LCM | CONSTRUCTION CO: EL EKHLAS .
02-24062615 (T.P) | OFFSET WELLS | TRISTATE-FISHING | >> RECEIVED ONLY 3/5 FRESH WATER LOAD FROM EDC. | (20 F, 20 M, 20 C) EVERY TWO STD TO AVOID LOSSES. | OIL
| BERENICE-24 | MENES WATER PIT | >> RECEIVED ONLY 4 / 8 ST. BY WATER TRUCKS FROM SINAI. | 12 1/4" BHA: | TD. 13000'
RIG SUPT: MOSTAFA ZAYED |  | RENPIT WATER PIT | >> TARGET TOLERANCE 25 M | 12 1/4" STEEL PDC + BIT SUB + 2 x 8 1/4" D/C + 12 1/8" S.STAB + 2 x | NEED TO STAKE
012-85777717 | D.WTR : RENPIT WELL | SALAM WATER PIT | ** DIESEL ENOUGH FOR 5 DAYS | 8 1/4" D/C + X/O + 18 x 6 1/2" D/C + 6 1/2" JAR + 3 x 6 1/2" D/C + 18 x
| R/O WTR : SUMPETCO |  | ** PRIMARY / SEC.OBJ: AEB-3D/3E/ SAFA, U-BAH | 5" H.W.D.P.
PMP: 3706 | TD: 13000' | SINAI - D. WTR. | ** ACTUAL / PROPOSED : XXXX/ XXXX DAYs @ CURR. DEPTH. | 12 1/4''BITS: SDI519MHBPX, R.R U616MBCDEGUZ, R.R DD507X
EDC - 40 | BRIDGE-1X | 12 1/4" | R/U 98% | FINISH R/U, CHECK RIG FOR ACCEPTANCE | BERENICE-36
1500 HP / TDS / RKB: 25' | OIL | SPUD MUD | CONT. RIG PROJECTS AS FOLLOWING : |  | Militry /MINE./EGPC/Env. Approval
BOP:13 5/8"-10K PSI WP |  |  | >> STABBING BOARD ON GOING. |  | NO/ OUT OF HIGH RISK AREA /NO / NO
RATED DRLG DEPTH :15,000' | Militry /MINE./EGPC/Env. Approval |  | >> FIN'D INSTALLING 20'' RISER W/ 3'' BALL VALVE. |  | CONSTRUCTION CO: ??
| YES/ OUT OF HIGH RISK AREA /VERBAL/ IN PROGRESS |  | >> CHECK MUD SYSTEM, FOUND SOME POINTS WORKING ON IT. |  | OIL
MAHMOUD RAFFAT |  | BAKER- MUD. | >> INSTALL DUMP LINE OF MUD SYSTEM ON GOING |  | TD. 13000'
AHMED ESSA |  | HALL- DIR. | >> CHECKED FIRE PUMP, FUNCTION TEST, OK. |  | NEED TO BUILD
01004996490 ( C.M ) | 9 5/8" SURF. CSG, (36#, K-55 , BTC) | SLB - CMT. | >> FIRE DETECTION SYETEM IN POWER HOUSING , WILL BE CHECKED
01285520932 (C.M.) | CP @ 2850 FT (67 FT INTO APOLL.) | SAP & EDC - TRS & CRT. | >> M/U 25* 5'' D/P, 7* 5'' HWDP & 6* 6 1/2'' D/C, RACK SAME BK ON DERK |  | BERENICE-37
| 7" CSG (26 PPF, N-80, BTC) | UNICO - R.REAMER. | >> WORKING ON FIXING DESERT ROAD ON GOING. |  | Militry /MINE./EGPC/Env. Approval
022-4062540(T.P) | C.P @ 7500 FT | W.F- STABLIZERS. | >>EXPECTED TO SPUD IN ON 22-AUGUST | B.H.A, ( 12 1/4” MTB + B.SUB (W/F.V.) + SHOCK .SUB + 3 X 8 1/4” | YES/ OUT OF HIGH RISK AREA /VERBAL / NO
|  | WAVE- JAR & SH. SUB. | >> RECEIVED ONLY 3 FRESH WATER TRUCKS FROM GAWEESH. | D/C’S + X/O + 15 X 6 1/2” D/C’S + 6 1/2” JAR + 3 X 6 1/2” | CONSTRUCTION CO: ??
|  | SWACO- CENTR & W.MANAGEMENT | >> BUILD UP 1300 BBL PREHYDRATED BETONITE. | D/C’S + X/O + 21 X 5” HWDP. | OIL
|  | BAKER- MONEL&MULTISHOT | >> NO STD BY TRUCKS ON LOCATION. |  | TD. 13000'
RIG SUPT: MOSTAFA ZAYED |  | GYRO-EGOSCO | >> FIXING DESERT ROAD ON GOING . |  | NEED TO STAKE
012-85777717 |  | VETCO-SETCORE-INSPECTION | ** DIESEL ENOUGH FOR XXX DAYS
|  | PBL ??? | ** PRIMARY / SEC.OBJ:
V-SAT: 980-0931 | TD: 7500' | GAWEESH - D. WTR. | ** ACTUAL / PROPOSED : XX / XX DAYs @ CURR. DEPTH. | 12 1/4'' MTB BIT (S/N 534219).
EDC - 42 | CARNARVON -N-1X | 8 1/2" | RIH W/ NEW 8 1/2" PDC BIT ON PEND. ASSY. & SLB MWD T/ 4,100' | CON'T RIH W/ NEW 8 1/2" PDC BIT ON PEND. ASSY. & SLB MWD T/ BTM
2000 HP / TDS / RKB: 35' | GAS | KCL POLYMER | >> BREAK CIRC. EVERY 2,000' | RESUME DRLG 8.5" V. HOLE T/ +/- 15,500 FT (TD)
BOP:13 5/8"-10K PSI WP | VERTICAL |  | >> TRIP IN LOSSES = 4 BPH | OBM VOLUME: 1405 BBL OBM 10.5 PPG + 475 BBL DIESEL
RATED DRLG DEPTH :20,000' | Militry /MINE./EGPC/Env. Approval | EMEC - MUD. |  | MUD PROP.: | BRAVO S-2
| YES/ YES / VERBAL / IN PROGRESS | SLB- DIR. |  | MWT: 10.4 PPG , VIS: 52, PV/YP: 26/31, GELS: 9/12, CL-: 117 K, HPHT: 11.8 | Militry /MINE./EGPC/Env. Approval
ATEF A.AHGFAR |  | SLB - CMT. |  | CHEM. CONC.: 4-5 PPB SOLTEX, 3 PPB STRATAHEAL, 10 PPB SIZED MARBLE. | YES/ NO / NO / NO
MOHMED IBRAHIM HASSEN | 13 3/8" SURF. CSG (68 PPG K-55, | PREIMER -TONG. | >> BIT: 8 1/2" NEW PDC (SMITH, MSXI713, S.N:. 5551, 7 X 12/32" NOZZLES) | 3 PPB GRAPHITE , 1% BU-LATEX, 3 PPB EMEC RESIN . | GAS
| BTC) @ +/-3060 | WAVE- JAR & SH. SUB. | >> BTM @ 12,281'. >> MWT: 10.4 PPG. AEB -5 @ 11762 | MUD PLAN:- | TD.15000'
012-82161786 (C.M) | (+/- 100' INTO APOLL.) | UNICO - REAMER |  | DRLG W/ 10.4 PPG KCL-POLY, MAINTAIN BRIDGING CHEMICALS | 20% ON GOING
010-50025781(C.M) |  | EMEC - CENTRIFUGE. | >> HAD +/- 1500 SAX NEAT CMT, CMT UNIT & BATCH MIXER. | MAINTAIN M.WT TILL BTM MASAJID. | CONSTRUCTION CO: UNION
VHF Radio channel 8 |  | BAKER - LINER HGR | >> SILICA BLEND & CHEMICALS SHOULD BE ONSITE TODAY AS PER | AT ZAHRAA SWITCH OVER T/ 10.4 PPG OBM (70/30) & MAINTAIN MWT TILL TD.
| 9 5/8" CSG (43.5 ,47 PPF, N-80, | CRT: PREMIER | SLB CMT. | BRIDGING: (15 PPB SIZED MARBLE,3 PPB STRATAHEAL, 3 PPB | TELLURIDE-1X
02- 27063393 (C.M) | BTC) @ +/-9395' | HADAF WTR PIT(+/-65 KM) |  | GRAPHITE) CONTINGENT TO CONT. W/ WBM (HIGH LOSS OR | Militry /MINE./EGPC/Env. Approval
02-24062542 (T.P) | (116 FT INTO AEB-1) |  |  | UNAVILABILITY OF OBM) | YES/ NO / NO / NO
RIG SUPT: HAITHAM KHEDR |  |  |  |  | GAS
012-83339501 | 7" LINER (29 PPF,HC, BTC) @ +/- | GAWEESH - D. WTR. | LAST SURVEY: | BHA: 8 ½” PDC BIT + BIT SUB+ 6 1/2" D/C + 8 3/8" R.REAMER + 6 3/4'' FLOAT | TD.16000'
| 15000' |  | MD: 12242' INC:1.61⁰ AZM: 279.99° TVD: 12241.56' V.SEC: 47.59' DLS: 0.52° | SUB + 6 3/4" MWD + X/O + 8 3/8” R.REAMER + 6 ¾” PBLSUB+ XO + 14 X 6 ½” | 85% ON GOING
VHF RADIO (CHANNEL 8) |  |  | ** DIESEL STOCK ENOUGH FOR 7 DAYs. | D/C XH + XO + 1 X 6 ½” D/C + 6 ½” JAR + 2 X 6 ½” D/C + 27 X 5” HWDP | CONSTRUCTION CO: UNION
V.SAT:980-0081 |  | KALABSHA WTR PIT | ** PRIMARY/SEC.OBJ: SAFA SAND & MASAJID / AEB 6 | 8 1/2" PDC BITS:
PMP: 3708 | TD.: 15,000' | GAWEESH - D. WTR. | ** ACTUAL/PROPOSED @ CURRENT DEPTH: 25 / 30 DAYS | DD407VTX, TKC66, GTD74
AHMED A.ATY | STAN JACKSON | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | DRLG Technical Support : MOH.NASR | Khaled Ghanaym
TELE: 01000031116 | TELE: 01277612182 | A/G: VERNON 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01220044064 - 01013334556 | 01275111158
KHALDA PETROLEUM CO.
|  |  | AM DRILLING REPORT | TEAM-1-DRLG | 2023-09-02 15:29
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS
EDC - 50 | NU - 34 | 8 1/2'' | BAKER E/L RIH W/1ST RUN TRIBLE COMBO W/ JAR & HOLE FINDERR | BAKER RECORD OHL'S
1500 HP / TDS / RKB: 30' | OIL | HOLE | (MRCH-JAR-TTRM-GR-CN-ZDL-RTEX-MLL-HOLEFINDER) T/ 5100' (E/L DEPTH) | M/U & RIH W/ 7" CSG STRG & CMT SAME | NU-40
BOP: 13 5/8"-10K PSI WP |  | KCL POLYER MUD | >> CABLE MAX. TENSION 12250 LBS. |  | OIL
RATED DRLG DEPTH: 15,000' | Military /MINE./EGPC/Env. Approval |  | >> TOOL LENGTH : 120.39' |  | Military /MINE./EGPC/Env. Approval
| YES/ OUT OF HIGH RISK AREA / VERBAL / IN PROG. | BAKER-MUD. | >> TOOL WT IN AIR/MUD : 2578/2191 LB'S. |  | NO/ OUT OF HIGH RISK AREA / VERBAL / IN PROGRESS.
|  | BAKER-DIR. | >> MAX. TOOL OD 4.88" | MUD PROP: | WIW
MOHMED NASSEM | 9 5/8" SURF. CSG, (36#, K-55 , BTC) | SLB - CMT. | >> SET JAR TO FIRE @ 6000 LB O.PULL. | VIS: 51, PV/YP: 28/31, GELS: 10/13, PH: 9.5,CL: 125K, FL: 3.8 | READY
| CP @ 2890 FT (75 FT INTO APOLL.) | SDF -T.R.S | >> LAST CIRC. SINCE: 30 HR'S | DIRECTION PLAN | TD : 11200'
| 7" CSG (29 & 26 PPF, N-80, BTC) | WAVE - JAR & RR. |  | KOP @ 7616 FT, BUILD TO 15.07 DEG INC. @ 166.82 AZI W/ 2 DLS, EOB @ 9270' | CONSTRUCTION CO. : UNION
01212582613 (C.M) | C.P @ 12,100 FT | BAKER- M.LOGGING | >> NEED 7" CRT F/ EDC | , DROP TO ZERO (EOD @ 10024')& HOLD TILL TD.
01004992493 (C.M) |  | SCOMI - CENTRIFUGE. |  | MUD PLAN
VHF Radio channel 8 |  | SOLID CTRL- EMEC |  | MAINTAIN M.WT 10.8 PPG TILL TD
0224062550 (T.P) |  | CRT - EDC |  |  | MENES-64
RIG SUPT: HAITHAM KHEDR |  |  |  |  | OIL
012-83339501 | OFFSET WELLS: |  |  |  | Military /MINE./EGPC/Env. Approval
| NU-22 & NU-27 |  | >> LAST OIL SHOWS: (11781-11783) |  | YES/ OUT OF HIGH RISK AREA / VERBAL / IN PROGRESS.
|  |  | PLZ @ 11860' M.WT: 10.8 PPG TD@ 12100' |  | OIL
50% ON GOING
|  |  | LAST SURVEY: |  | TD : 12100'
|  |  | MD:12039' INC: 1.96⁰ AZM: 268.05° TVD: 12055.42' V.SEC: 431.29' DLS: 1.16° |  | CONSTRUCTION CO. : UNION
CT-CT: 12.97' BELOW : 0.07' RIGHT: 12.97
** DIESEL STOCK ENOUGH FOR 7 DAYS.
PMP: 3754 |  |  | ** PRIMARY / SEC: AEB-3A, 3D & AEB-1 /AEB-3C & AEB-6
| TD: 12100' | W.HORSE - D. WTR. | ** ACTUAL / PROPOSED @ CURRENT DEPTH: 16/19 DAYs . | 8.5" BITS: TKC66 , DD506VTX
EDC - 57 | TAYIM-W8 | 8 1/2" | DRLG @ 11610' PROG: 22 FT AV. ROP: 7.33 FPH C.ROP: 7 FPH | CIRC. FOR HOLE CLEANING
2000 HP/ TDS / RKB: 30' | OIL | HOLE | BIT (TKC-66) FTG: 2682' HRS: 55.5 ON-BTM: 43 ROP: 62.4 FPH | POOH FOR BIT CHANGE | HEQET-6X
BOP:13 5/8"-10K PSI WP | DEVELOPMENT | OBM | AEB-3C @ 10267' 50%SLT.ST, 50%S.ST @ 11590' GAS: 0.5% | >> OBM LOSSES ( DAILY/TOTAL)-(160/335) | Militry /MINE./EGPC/Env. Approval
RATED DRLG DEPTH 20,000' | DEVIATED |  | LOSSES: 4/2 BPH M.WT: 10.7 PPG OFF/ON- TRQ: 4 / 16 K-FT.LB | >> TOT. OBM RECEIVED ON RIG SITE (DAILY/TOT.)-(0/2320). | YES/ OUT OF HIGH RISK AREA / NO / NO
| Militry /MINE./EGPC/Env. Approval |  | WOB: 30-35 KLB RPM: 130 GPM: 510 P.P.: 3100-3150 PSI | >> TOT. DIESEL RECEIVED ON RIG SITE (DAILY/TOT.)-(38/710). | OIL
BELAL TAHA | YES/Out of High Risk Area / YES / YES |  | >> RECORD SURVEY EVERY 2 STD | >> DIESEL STORED IN MI TANKS 233 BBLS. | TD 17700'
HAZEM ELKHALDY | 17 1/2" HOLE DRILLED TO 2445' | EMEC - MUD. | >> WASH & REAM EACH STD DRILLED | >> TOT. VOLUME OF DIESEL USED IN MUD SYSTEM ( DAILY/ TOT.)-(175/475) BBLS. | READY
| (50' INTO APOLLONIA ) | SCHL - DIR. |  | >> OBM IN (HOLE / ACTIVE / RES./ MI TANKS / TOT.) : (746 /1195/688/ 0/2629 ) | CONSTRUCTION CO: ALEKHLAS
| 13 3/8 SURF. CSG.STUCK @1850' | HALL. - CMT. |  | >> CUTTING BOXES (EMPTY, FULL, SENT, BEING FILLED, TOT.): 22,8,7,3,40
| 9 5/8" INTER CSG. @ 8928 FT | Premiere - TONG |  | MUD PLAN | SIWA-R-NW-03
012-02542198 (C.M) | 7" PRODUCTION CSG @ 15871 FT | UNICO - REAMER. |  | >> PLAN TO ENETR AEB-1 WITH 10.5 PPG , ENTER AEB-3A W/ 10.7 PPG. | Militry /MINE./EGPC/Env. Approval
010-25616837 (C.M) | WTR WELL: +/- 25 KM AWAY F/ RIG | W.FORD - JAR, SH. SUB & STAB. |  | >> PLAN TO ENTER ZAHRA W/ 11 PPG | YES/ OUT OF HIGH RISK AREA / NO / NO
VHF Radio channel 8 | OFFSET WELLS: | MI - CENTRIFUGE. |  | MUD PROP.: VIS: 70, PV/YP: 31/12, GELS: 9/17, FL: 5.2, E.S. 240 | OIL
01002191542 (T.P) | TAYIM-W3, 5 & 6 | WF-LINER HGR |  | DIREC. PLAN: | TD15500'
02-24062657 (T.P) |  | SINAI - D. WTR. |  | KOP @ 11,980’ BUILD T/ 50 INC. @ 181.39 AZI W/ 3.0 DLS EOB @ | READY
RIG SUPT: ELSAYED HAMZA |  |  |  | 13982' | CONSTRUCTION CO: ALEKHLAS
01228916988
LAST SURVEY:
| WTR WELL: SIWA WELL |  | MD: 11275' INC:0.33⁰ AZM: 278.34⁰ TVD: 11274.05' V.SEC: 68.57 DLS:0.05
8 1/2" BHA:
|  |  | >> HAD 4 ST.BY TRUCKS FROM SINAI. | 8 ½” PDC BIT + 6 ¾” POWER DRIVE W/ 8 1/2” STABLIZED CC + 6 ¾” FLOAT
VHF RADIO (CHANNEL 8) |  |  | ** DIESEL STOCK ENOUGH FOR 4 DAYS | SUB + 6 ¾” MWD + 8” STABILIZER + 6 ¾” PBL + 6 X 6 ½” D/C'S + 6 ½” JAR +
V-SAT:N/A |  |  | >> PRIMARY/SEC. OBJ.: U-SAFA SD0 & L-SAFA / NA ** TARGET TOLERANCE: 50 M | 2 X 6 ½” DRILL COLLAR + 27 X 5” HWDP.
PMP: 3717 | TD.: 15,871' | SINAI - D. WTR. | >> ACTUAL/PROPOSED @ CURRENT DEPTH: 21.2/29 DAYS. | 8 1/2" BITS: TKC66-J9G, DD407VTX, GTD65DRKHO, K5M426
AHMED A.ATY | STAN JACKSON | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | DRLG Technical Support : MOH.NASR | Khaled Ghanaym
TELE: 01000031116 | TELE: 01277612182 | A/G: VERNON 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01220044064 - 01013334556 | 01275111158
KHALDA PETROLEUM CO.
|  |  | AM DRILLING REPORT | TEAM-1-DRLG | 2023-09-02 15:29
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS
EDC-58 | WD-33C-1X(JASPER-1X | 12 1/4" | POH TO 6300' FOR CEMENT | AT 6300' CIRC. 1-1/2 STRING CAP.
2000 HP / TOP DRIVE | OIL | HOLE | >> PUMPED 10.2 HI-VIS PILL AT 6800' 73BBLS. & DISPLACED . | MIX & PUMP CEMENT FOR LOSSES: | WD 09-C-1X
ANDREW | VERTICAL | FW GEL MUD | WITH 88 BBLS. MUD. | 55.5 BBLS SPACER W/CEMNET | M./MINE CLEAR./EGPC /ENV. App.
SHERIF SOBHY | Militry /MINE./EGPC/Env. Approval | 3 APACHE TANK. | HAD 40-50 BBLS. LOSSES WHILE CIRC. PRIOR TO HI-VIS | 120BBLS 14# CEMENT W/CEMNET | NO/ OUT OF HIGH RISK AREA / NO / NO
012-76403055 (C.M) | YES / OUT OF HIGH RISK AREA / | SLB. - CMT. |  | 5.5 BBLS SPACER W/CEMNET | OIL
0100-0190891(C.M) | VERBAL / IN PROGRESS | SLB. - DIR. |  | DISPLACE TO BALANCE WITH 73 BBLS. MUD. | TD 14000'.
02- 27063372 (C.M) | CONSTRUCTION CO: ELMANSOURA | EMEC - MUD. | >> BTM @ 7228'. >> MWT: 9 PPG. KHOMAN" A " @ 6500' | POH TO 5000' & CIRC. STRING CLEAN. | 30% ON GOING
VHF Radio channel 8 | 20" CONDUCTOR HUMMERED TO 43' | TRS: PREIMER |  |  | CONSTRUCTION CO. : EL SHROUK
012-05552247 (T.P) | 13 3/8" SURF. CSG. @ +-2480 FT | UNICO - R.REAMER.
0224062689(T.P) | (15' IN APPOL.) | W.FORD - STABLIZERS. |  | MUD PLAN: | WD 09-B-1X
| 9 5/8" INTERMEDIATE @ +/-10350 FT | WAVE - JAR & SH. SUB. |  | >> SWITCH OVER TO 9.2 PPG KCL POLYMER MUD W/ 3 PPB SOLTEX | M./MINE CLEAR./EGPC /ENV. App.
RIG SUPT: ELSAYED HAMZA | 8-1/2'' HOLE @ 13,500 FT | EMEC - CENTRIFUGE. |  | @ ± 9500' (207' BEFORE KHOMAN B). INCREASE T/ 9.8 PPG BEFORE A/R-A | NO/ OUT OF HIGH RISK AREA / NO / NO
01228916988 | 7" LINER @ 13,495 FT | LINER HGR - W.FORD | NEED WATER TRUCKS FW WATER PIT EMPTY , 275 BBLS. FW IN | & MAINTAIN SAME T/ C.P. | OIL
|  | WASTE MANGMENT: EMEC | RIG TANK |  | TD 14000'.
| OFFSET WELLS: | CRT - PREMIER | MOGHRA PIT-20% |  | NEED TO BUILD
| WD-33-15-7X, YOSEMITE-1X |  |  | >> EXPECTED FAULT @ 11330 ' | CONSTRUCTION CO. : EL SHROUK
WD-33-15-9
Thuraya : +882-1633331604 | >> EXPECTED FAULT @ 11330 ' |  | >> FRESH WTR PIT : 5 % FULL >> DRILL WTR PIT :10 % FULL
V-SAT: 980-0821 |  |  | NEED FW TRUCKS NO DELIVERYS SINCE YESTERDAY AM.
ITN:75372 |  |  | ** DIESEL STOCK ENOUGH FOR 3 DAYS.
VHF RADIO (CHANNEL 8) |  |  | ** PRIMARY / SEC: A/R C&E
PMP: | TD: 13500' | SINAI - D. WTR. | ** ACTUAL/PROPOSED @ CURRENT DEPTH: 11/10 DAYS. | 12 1/4" BITS : GTI65DMHO (NEW), GTE75H (NEW) & DD507X (NEW).
EDC - 62 | PTAH-48 | 8 1/2" | CONT. RIH W/ 7" PROD. CSG (26#, N-80, BTC) T/ 4,500 FT | CON'T RIH W/ 7" PROD. CSG (26#, N-80, BTC) T/ 6,900 FT ( BTM )
1200 HP / TOP DRIVE | OIL | HOLE | >> TOT.: 116 / 178 JTS. | >> TOT. 178 JT'S
| VERTICAL | KCL POLYMER MUD | >> AVG. TRIP IN LOSSES: +/- 3 BPH. | CIRC. ( MIN. 1.5 CSG CAPACITY ) W/ 300 GPM WHILE MIXING MIX FLUID .
KAREEM MOSELHY | M. /MINE./EGPC/Env. Approval |  | >> FILL CSG WHILE RIH EVERY 5 JT'S | R/D VOLANT CRT, R/U HALL. CMT HEAD (EQUIPPED W/BTM & TOP PLUGS ) | MENES -57
| YES / OUT OF HIGH RISK AREA/VERBAL / NO |  | >> BREAK CIRC. EVERY 1,500' WHILE RIH . | R/U HALL CMT S. LINE, FLUSH & P/T SAME | Militry /MINE./EGPC/Env. Approval
01271466694 ( C.M ) | 20" COND (94#, K55, BTC) | 2 KPC TANKS | >> OPEN HOLE SECTION IN GOOD SHAPE TILL CURRENT DEPTH. | PERFORMED 7" PROD CSG CMT. JOB AS FOLLOWING : | YES / OUT OF HIGH RISK AREA/ NO / NO
01060422238 (C.M.) |  | 1 FRAC + APACHE TANK | >> SET TQ LIMIT FOR 7'' CSG (#26) @ 6,000 LBS.FT ACCORDING TO | >>PUMPED 200 BBL'S LOW RHEOLOGY MUD | OIL.
| 9 5/8" SUR. CSG | BAKER- MUD. | TRIANGLE BASE . | >> PUMPED 60 BBL 11.0 PPG MP-II SPACER | TD. 12100'
01221112177 ( T.P ) | 36 PPF, K-55, BTC @ 2750' | BAKER - DIR. | >> CHECK CRT AIR PRESS. & CLEAN GRIP DIES EVERY 20 JT. | >> PUMPED 267.5 BBL'S FILLER LEAD CMT SLURRY( 11.5 PPG-15% | READY
024062657 (T.P) | (76' INTO APOLL. ) | HALL. - CMT. | >> LAST CIRC. @ 4,100 FT W/ 250 GPM , P.P=450 PSI . | EXCESS, 626 SKS NEAT CMT) & RELEASED BTM PLUG. | CONSTRUCTION CO: UNION
|  | SAPESCO -TONG. | >> P.U.WT/S.OWT : 135 / 130 KLB'S | >> PUMPED 36 BBL TAIL CMT-SLURRY ( 15.8 PPG 15% EXCESS , 171 SKS )
RIG SUPT: ABDALLAH IBRAHIM | OFFSET WELLS: | WAVE - STAB. | L.BAH FM @6,573 ' MWT.: 10.3 PPG BTM@ 6,900 ' | >> RELEASED TOP-PLUG, DISPLACED ALL W/ 261.5 BBL's ( 10 BBL's | BERENIECE-39
01212009267 | PTAH-35 ST | WAVE- R.REAMER |  | FRESH WTR + 251.5 BBL's 9.3 PPG CORROSION INH. KHRT WTR ) . | Militry /MINE./EGPC/Env. Approval
|  | NOV - JAR & SH. SUB. |  |  | YES / OUT OF HIGH RISK AREA/ NO / NO
V-SAT: |  | EMEC - CENTRIFUGE. |  | MUD PROP:VIS:50 ,PV/YP:19/20,GEL: 7/9 , MWT.: 10.3 PPG,PH:9.5 MBT: 7.5 | OIL.
PMP: 3748 |  | CRT: EDC |  |  | TD. 6700'
|  |  | LAST SURVEY: |  | NEED TO BUILD
|  |  | MD: 6,824' INC: 0.68⁰ AZM: 202.140 ° TVD: 6,823.7' V.SEC: 26.52 ' DLS: 0.16 ° |  | CONSTRUCTION CO: UNION
| TD: 6900' |  | ** DIESEL STOCK ENOUGH FOR 4 DAYS.
** PRIMARY/SECONDARY OBJECTIVE: L-BAH/N-A
|  |  | >> ACTUAL/PROPOSED @ CURRENT DEPTH: 8.25 / 9.5 DAYS. | 8 1/2'' BITS: MI616LUBPX-P (NEW , 6035) , U6195BCEGUZ(NEW , 39012)
AHMED A.ATY | STAN JACKSON | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | DRLG Technical Support : MOH.NASR | Khaled Ghanaym
TELE: 01000031116 | TELE: 01277612182 | A/G: VERNON 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01220044064 - 01013334556 | 01275111158
KHALDA PETROLEUM CO.
|  |  | AM DRILLING REPORT | TEAM-2-DRLG | 2023-09-02 15:29
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS
ST - 7 | MRZK-210 | 12 1/4" | R/D 100 % R/M 100 % R/U 50 % | MOVE PLAN ON MRZK-210:- | MRZK-212
1000 HP / TDS / RKB: 25' | OIL | HOLE | >> RIG RELEASED. T/ MRZK-210 ON 6-AUG-2023 @ 01:00 PM | >> CHECK ALL LIFE SAVING EQUIPMENT AND STORED THEM | Militry /MINE./EGPC/Env. Approval
MAX. PULL 495 KLB | DEVIATED | SPUD MUD | >> MOVE DISTANCE F/ NRQ-13-3 T/ MRZK-210: 43 KM (21 KM DESERT | >> INSPECT ALL THE RIG MOVE HEAVY LIFT EQUIPMENTS & TRUCKS | YES/NO NEED/VERBAL/NO, (SHALLOW GAS)
(HALL BUNDLE SERVICE) | Militry /MINE./EGPC/Env. Approval | BAROID- MUD. | ROAD + 22 KM BLACK ROAD) | >> CLEANING F/ ALL MUD SYSTEM TANKS.>MAINTAIN MUD SYSTEM TANKS | OIL.
AMR ATEF | YES /NO NEED/VERBAL/NO,IN PROGR | HLS - DIR. | >> DIESEL @ RIG RELEASE = 20,020 GAL. | >> CHECK TD & TD GUIDE & HYD. FILTTER TOP DRIVE | TD: 9,000'.
| (SHALLOW GAS) | HLS - CMT. | >> MRZK-210 LOCATION IS READY. | >> CHECK FOR MAIN ENGINES AND RADIATORS > PM FOR CROWN BLOCK | 25 % ON GOING.
| 20" CONDUCTOR @ 15 FT PENT | SAP & PREM - TRS & CRT. | >> EXPECTED TO SPUD IN +/- 26/8/2023 | >> CHANGE DRAW-WORK AND BREAK PADS >CHECK&MAINTAIN DC MOTORS. | NEED TO HUMMER 20" CONDUCTOR
| 9 5/8" CSG (36#,K-55, BTC) @ 3595' | UNICO - R.REAMER. | >> PLAN TO USE DIVERTER IN SURF. HOLE | >> CHECK & MAINTAIN ALL DC MOTORS. | CONSTRUCTION CO: ELMANSORA
01283909324 (C.M) | (+/- 14 FT INTO APOLL. FM) | WAVE- STABLIZERS. | >> HAD +/- 1300' X 13-3/8" CSG IN CASE OF ENLARGE HOLE | >> MAINTENANCE FOR DRY TRANSFORMER & SCR UNIT
01157602947 (C.M) | 7" PROD CSG(26# ,N-80,BTC) @ 6,600' | WAVE- JAR & SH. SUB. | >> FRESH WTR PIT : 100 % FULL >> DRILL WTR PIT : 25 % FULL | >> PM FOR MAIN GENERATORS >MAINTENANCE FOR DW MOTORS A, B | RIG RELEASE
01003728086 (T.P) | LOCATION READY | HLS- CENTR & H.DRYER | >> PLAN TO USE DIVERTER IN SURF. HOLE | >> MAINTENANCE FOR ROTARY TABLE MOTOR
RIG SUPT:HESHAM MASOWD | 2X 500 BBL EPIS STORAGE TANK. | W.FORD- PBL | >> HAD NO STD. BY TRUCK ON LOCATION. >> HAD NO CO- MAN P/U CAR | DIRECTION PLAN:KOP @ 4000' BUILD ANGLE T/26.5 DEG INCL W/ 176 AZM
012-85455600 | PLAN TO USE DIVERTER ON SURFACE | EPIS &MI- WASTE MANG. | ** TARGET TOLERANCE: 50 M RADIUS. | & 2 DEG DLS T/ 5326' & HOLD TILL TD
| OFFSET WELL'S: | MULTI SHOT-EGOSCO | *** DIESEL STOCK ENOUGH FOR XX DAYS. | BHA:12 1/4"STEEL PDC BIT+B.S.(F.V.)+1X8 1/4"D/C+12 1/8"STB(Spiral Blade)+
V.SAT: 980-0051 | NRQ- 13-2 & NRQ 5X | NRQ WTR PIT | ** PRIMARY / SEC.: AR-G DOL. & U-BAH / L-BAH & KHARITA | 2 X8 1/4” D/C+ X/O + 12 X 6 1/2” D/C+ JAR+3 X6 1/2” D/C+X/O+12 X 5" HWDP
| TD: 6,600' | GAWEESH - D. WTR. | ** ACTUAL / PROPOSED @ CURRENT DEPTH: XX /XXX DAYs . | 12 1/4 '' BITS:
EDC - 9 | BRAVO E-2 | 12-1/4" | CONT. RIH W/ 9 5/8'' INT.CSG (#43.5 & 47 HC) T/ 2,928' (INSIDE CSG SHOE) | CON'T RIH W/ 9 5/8'' INTERM. CSG (# 43.5 & 47, N-80, P-110 BTC) | BRAVO E-3
2000 HP / TDS / RKB: 31' | G/C | HOLE | >> TOT. 78 / 240 JTS X 9 5/8" CSG. | T/ 9,138' (BTM). | Militry /MINE./EGPC/Env. Approval
RATED DRLG DEPTH 20,000' | DEVIATED | KCL POLY MUD(10.7 PPG) | >> AVG TRIP-IN LOSSES +/- 4 BPH | PERFORM 9 5/8" INTERM. CSG CMT JOB | YES/NO /NO/ NO
| Militry /MINE./EGPC/Env. Approval | EMEC- MUD. | >> FILL STRG WHILE RIH EVERY 5 JT'S |  | OIL
MAHMOUD BAKRY | YES/ NO / VERBAL / NO | HLS - DIR. | R/U SAP SPIDER ELEVATOR, SLIPS & FILL-UP TOOL… IN PROGRESS. | MUD PLAN: ENTER AEB-3G W/ 10.7 PPG & KEEP SAME TILL ENTER | TD: 16,000'
MARCORUOS |  | SLB - CMT. | >> P/U / S.O.WT: 156 / 154 KLB's. | MASAJID FM THEN INCREASE TO 10.8 PPG AT BASE MASAJID & SWITCH | 40 % ON GOING.
01226348568 (C.M) | 13 3/8"SURF. CSG. @ 3,010 FT | W.F & EDC - TRS & CRT. |  | OVER TO 10.8 PPG OBM AT BASE MASAJID FM | CONSTRUCTION CO: UNION
01060977764 (C.M) | (68' INTO APPOLONIA .) | WAVE - R.REAMER. |  | >> HAVE 390 BBL OBM ON LOCATION
VHF RADIO(CHANNEL8) | 9 5/8" INTER. CSG @ +/-9138 FT | WOOD- STABLIZERS. | AEB-1 @ 9,108' M.WT: 10.7 PPG BTM @ 9,138' | >HAVE 4 WTR TRUCKS F/ GAWEESH (VERY POOR SUPPLY) & 1 VACCUM | WKAN Z-01X
01221112109 (T.P) | (± 30 FT INTO AEB-1 FM.) | W.FORD- JAR & SH. SUB. | >> HAVE 4 WTR TRUCKS F/ GAWEESH | DIRECTION PLAN : - | Militry /MINE./EGPC/Env. Approval |  | Attia AbdElaziz
02-24062509 (T.P) | 7" LINER CSG @ 15,200' | EMEC- CENTR & H.DRYER | MD: 9,136' INC: 0.45 AZM: 176.25⁰ TVD: 9,135' V.SEC: -3.55' DLS: 0.10⁰ | KOP @11,942', BUILD 20.4° W/ 2 DOG LEG &242 AZM @ 12963' & HOLD TD | YES/NO /NO/ NO |  | Hany Allam
RIG SUPT:HAYTHAM KHEDR | 2 X 500 BBL EPIS STORAGE TANK. | WFRD- LINER HGR | ** TARGET TOLERANCE:21 M. | 12 1/4" PDC BIT + BIT SUB W/ F.V. + 1 X 9 1/2” D/C’s + 9 1/2” MWD + 3 X 9 1/2” | OIL |  | Ahmed Barkat
012-83339501 | OFFSET WELL: | W.FORD- PBL | ** DIESEL STOCK ENOUGH FOR 6 DAYS. | D/C’s + X/O SUB + 8” PBL SUB + 9 X 8 1/4” D/C’s + 12 1/8” R. R. + 8 1/4” D/C | TD: 14,500' |  | Mohsen Ashour
| KARANIS-1X | HADF WTR PIT (60 KM) | ** PRIMARY / SEC. OBJECTIVE: U. SAFA / MASAJID | 8 1/4” DRILLING JAR + 2 X 8 1/4” D/C’s + X/O SUB + 12 X 5” HWDP | NEED TO BUILD |  | Khaled Ghanaym
PMP: 3742 | NEW TD: 15,200' | GAWEESH - D. WTR. | ** ACTUAL/PROPOSED @ CURRENT DEPTH: 13.8 / 17 DAYS | 12 1/4'' BITS: MSXI616LBP, GTD65DHMHO & 8 1/2'' BIT'S : TKC66 | CONSTRUCTION CO: UNION |  | 01275111158
EDC - 48 | UMB-250 | 8.5" | DRLG @ 4600' PROG: 295 FT AV. ROP: 98.3 FPH C.ROP: 95 FPH | CONT.DRLH 8.5'' DEV. HOLE T/12300' | UMB-262 |  | Belal Sallouma
2000 HP / TDS / RKB: 35' | OIL | HOLE | BIT (DD506VTX) FTG: 1785' HRS: 19.5 ON-BTM: 11.9 ROP: 150 FPH | MUD PLAN : | Militry /MINE./EGPC/Env. Approval |  | 01279539944
FATHY MEKKAWY | DEVIATED | SPUD MUD ( 8.7 PPG) | A/R (B) @ 4390' LAST SAMPLE: 100 % LIMESTONE @ 4590' GAS: 0.1% | • SWITCH OVER WITH 9.8 PPG M. WT.+/- 100 FT ABOVE A/R "A"@4100' | YES/NO NEED /NO/ NO |  | Amr AbdElaziz
ISLAM NAZER | Militry /MINE./EGPC/Env. Approval | BAKER- MUD. | LOSSES: 13/4 BPH M.WT: 9.8 PPG OFF/ON- TRQ: 4 / 12 K-FT.LB | • ENTER A/R “G” W/ 9.8 PPG | OIL |  | Mohamed Abd Elsalam
| YES/NO NEED /NO/ IN PROGRESS | SPERRY- DIR. | WOB: 35 KLB RPM: 130 GPM: 500 P.P.: 1800 PSI | • ENTER KHARITA W/ 10.0 PPG M.WT & KEEP SAME TILL PASS ALAMEIN DOL. | TD 12,000'. |  | Walid Sallam
012-78888624 (C.M) |  | HALL. - CMT. | >> RECORD SURVEY EVERY 3 STD | **STARTING F/ AEB-1 INCREASE M.WT GRADUALLY & ENTER AEB-3C | READY |  | Esam Eid
01-024486001 (C.M) | 9-5/8" CSG (36#, K-55,BTC) @ 2815 FT | SAP & EDC - TRS & CRT. | >> WASH & REAM EACH STD DRILLED | W/ 10.4 PPG &INCREASE GRADUALLY TO 10.6PPG WHILE DRILLING TILL TD | CONSTRUCTION CO: UNION |  | Dan Mullinus
VHF RADIO(CHANNEL8) | (131 FT APOL. FM | WAVE - R.REAMER. |  | ***OPTIONAL O.B.M AT WELL TD BASED ON HOLE CONDITION |  |  | 01277612182
01221112126 ( T.P ) | 7" PROD. CSG @ 12400' | W.FORD- STABLIZERS. |  |  |  |  | Stan Jackson
0224062695 (T.P) |  | W.FORD- JAR & SH. SUB. |  | DIRECTION PLAN :- K.O.P @10100' BUILD TO 34.8 DEG@ 11840' | MAAT N-1X (NEED MILITRY APPROVAL) |  | Charlie Kennedy
RIG SUPT:HAYTHAM KHEDR |  | EMEC- CENTR & W.M |  | W/ DLS 2 DEG/100' & 105.7 AZM. , HOLD TO TD. | Militry /MINE./EGPC/Env. Approval |  | Abdelmageed Ahmed
012-83339501 |  | WFRD- LINER HGR |  |  | NO/NO NEED /NO/ NO |  | Omar Yahia
| OFFSET WELLS: | W.FORD- PBL | ** TARGET TOLERANCE: 50 M RADIUS.. | 8-1/2" BHA:- 8 1/2'' PDC BIT + BIT SUB W/ F.V + 6 1/2" D/C + 8 3/8'' R.REAMER + | G/C |  | Abd-Alah Taha
| UMB 234 & UMB 244 X |  | ** DIESEL STOCK ENOUGH FOR 5 DAYS. | 6 ¾” MWD + 8 3/8'' R. REAMER + FLOAT SUB + CIRC SUB + 9 * 6 1/2'' DC + | TD 15,000'. |  | Ahmed Elbanauosy
V.SAT:980-0761 |  | MENES & RENPIT PIT | *PRIMARY / SEC.OBJ: PALEOZOIC / AEB | 6 1/2'' JAR + 2 * 6 1/2'' DC + 24 * 4 1/2" HWDP | NEED TO BUILD. |  | Ahmed AbdElaaty
PMP: 3710 | TD: 12,400' | GAWEESH - D. WTR. | ** ACTUAL/PROPOSED @ CURRENT DEPTH: 7.25 / 9 DAYS. | 8 1/2" BITS : TKC66,U713MCDEGUZ | CONSTRUCTION CO: UNION |  | Vernon
ISLAM DAHSHAN | STAN JACKSON | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | DRLG Technical Support : MOH.NASR | Khaled Ghanaym |  | Abd-Allah Taha
TELE: 01000031114-01271488855 | TELE: 01277612182 | A/G: VERNON 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01220044064 - 01013334556 | 01275111158
KHALDA PETROLEUM CO.
|  |  | AM DRILLING REPORT | TEAM-2-DRLG | 2023-09-02 15:29
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS
EDC - 49 | TUT-135 | 8-1/2" | CON'T RIH W/ 7'' LINER CSG ON DRIFTED 5'' HWDP & D/P T/ 11,458'. | CONT RIH WITH 7" LINER ON DRIFTED 5" D/P (S-135) STD'S...T/ 12900 FT . | QASR-59
1500 HP / TDS / RKB: 25' | OIL | HOLE | >> TOTAL : ( 6 STD's X 5" HWDP + 62 /80 STD's X 5" D/P "S-135" ). | CIRC. BTM'S-UP TILL SHAKERS CLEAN. | Militry/MINE CLEAR./EGPC /ENV. App.
RATED DRLG DEPTH: 15,000' | DEVIATED | OBM(10.8PPG) | >> B. CIRC EVERY 2000' FT. | DROP 1.5” SETTING BALL & CIRC. THE BALL WITH 2-3 BPM WITH MAX. | YES / NO NEED / VERBAL / NO
| Military /MINE./EGPC/Env. Approval |  | >> AVG TRIP IN LOSSES : 1 BPH. | 900 PSI, TILL BALL SET. SET LNR HGR, RELEASE RUNNING TOOL | GAS
HANY ELSAADANY | YES / NO NEED / VERBAL/ IN PROG. |  |  | , SHEAR BALL SEAT, MAINTAIN 30-40 KLBS ON HGR WHILE CIRC. | TD. 14,000'.
MOH. SALEH |  |  |  | CONT. CIRC.WHILE HALL. MIXING CMT. & PERFORM CMT JOB | READY
|  | CRT- EDC |  |  | CONSTRUCTION CO. : UNION
| 13 3/8"CSG (68#,K-55, BTC) @ 2718' | BAKER- MUD. | >> TRANSFERRED 400 BBL OBM TO MI SALAM MUD PLANT |  | TUT-131A
| (77' INTO APPO.) | BAKER- DIR. | >> LAST PAYZONE @ 12850' | MUD PROP.:VIS:87, PV/YP: 39/16,GEL:14/25 , MWT.: 10.8 PPG. ,HPHT: 3.2 | Militry/MINE CLEAR./EGPC /ENV. App.
| 9 5/8" INTER. CSG(43.5#, K-55)@8,164' | HALL - CMT. |  | ES: 400 VOLT, OWR 70/30, LIME : 4.5 IB/BBL | YES / NO NEED / NO / NO
0121 258 2659 (C.M) | ( 36 FT INTO AEB-1 FM.) | SDF -TRS | L.SAFA @ 12597', M.WT: 10.8 PPG BTM : 12900' | >> OBM ON LOC. : HOLE/ACTIVE/RESERVE/ SILO: 860/0/0/315 BBLS. | OIL.
0100 499 2495 (C.M) |  | POSS- JAR & SH. SUB. | MD: 12900' INC: 22.77⁰ AZM: 330.6⁰ TVD: 12596.2' V.SEC: 1558.5' DLS: 0.01° |  | TD. 13,000.
0224062549 (T.P) | 7"LINER CSG @ 12,900' | THARWA- MUD LOGGING | >> DIST. FROM PLAN: RIGHT: 8.54 FT, ABOVE: 9.66 FT, C.C: 12.89 FT |  | NEED TO STAKE
|  | MI - CENTRIFUGE & G DRYER | >> HAD 100 X 7'' CENTEK CENTRALIZERS. | DIRECTION PLAN : K.O.P @ 8400' BUILD INCLINATION 23.23 DEG | CONSTRUCTION CO. : UNION
RIG SUPT:HAYTHAM KHEDR | OFFSET WELL: | MONEL- BAKER |  | W/ 331.362 AZMUITH & 2 DLS DEG @ 9561'& HOLD SAME TO TD.
012-83339501 | TUT 119 & TUT 52 | EMS- EGESO | >> W.FORD LINER & ENGINEER ON LOCATION
|  | W.FORD-P.REAMER | >> HALL. LOGGING ON LOCATION W/ JAR, HOLE FINDER & FISHING BOX.
| WTR. SOURCE: SALAM WTR WELL | M.SHOOT -WELL SERVICE | >> HAVE 2 WTR TRUCKS | BHA:
|  | BAKER - LINER HGR | ** TARGET TOLERANCE: 50 M RADIUS..
** DIESEL STOCK ENOUGH FOR 7 DAYS.
|  | KAH & RENPIT PIT | ** PRIMARY/SEC.OBJ: KHAT-2B / N/A
PMP: 3758 | TD: 12,900' | GAWEESH - D. WTR. | ** ACTUAL / PROPOSED @ CURRENT DEPTH : 33.2 / 34.07 DAYS. | 8-1/2" BITS: GTD74KHO(NEW).
EDC - 53 | OAKHILL-1X | 12 1/4" | CONT. RIH W/ 9 5/8" INTERM. CSG. (47,43.5#, N-80, BTC) T/ 7,900'. | CON'T RIH W/ 9-5/8” INTERM. CSG (47, 43.5#, N-80, BTC) T/ 9,255' (BTM) | WD 33 B-1X
2000 HP / TDS / RKB: 30' | OIL. | KCL POLY MUD | >> TOT. 205/241 JT’S X 9 5/8" CSG. | PERFORM 9 5/8" INTERM. CSG CMT JOB AS FOLLOWING: | Militry /MINE./EGPC/Env. Approval
TAREK MAHMOUD | DEVIATED |  | >> TRIP IN LOSSES: 3 BPH. | >> PUMP (60 BBL, 11.5 PPG) INHIBITED WTR AS SPACER AHEAD | YES / NO NEED / NO/ NO (SHALLOW GAS)
ISLAM THABET | Militry /MINE./EGPC/Env. Approval | EMEC- MUD. | >> BREAK CIRC. EVERY 1500 FT WHILE RIH. | >> PUMP (570 BBL’S, 12.5 PPG) W/15% EXCESS LEAD SLURRY | OIL
| YES/ NO NEED / VERBAL / IN PROG, (SHALLOW GAS) | SLB - DIR. | >> USED EDC SPIDER ELEV. & SAP FLUSH HYD. SLIPS & FILL-UP TOOL | >> PUMP (84 BBL, 15.8 PPG) W/15% EXCESS TAIL SLURRY | TD 13,500'.
02 27063295 (C.M) | 20" CONDUCTOR @ 37' PEN | SLB. - CMT. | >> LAST B.CIRC. @ 7000' W/ 210 GPM ,P.P=280 PSI & LOSSES: BPH. | >> DISPLACE CMT W/TOT 662.3 BBL | 40 % ON GOING.
012-02542678 (C.M) | 13 3/8" SURF. CSG @ 3,930' | SAPESCO-TRS. | >> ON LOCATION : 1045 BBLS OBM , 375 BBL'S DIESEL IN EPIS TANKS. | (20.3 BBL’S FRESH WTR + 642 BBL’S 9.8 PPG KCL POLYMER MUD) | CONSTRUCTION CO. : AL SHROUK
010-11151924 (C.M) | (13 FT INTO APOLLONIA "A") | W.FORD- JAR & SH. SUB. | >> HAD 42 CUTTING SKIPS FROM EPIS. | MUD PLAN: SWITCH OVER TO 11 PPG OBM WHILE DRLG SHOE TRACK | MAHROUSSA-D-1X
02-24062553 (T.P) | 9 5/8"CSG @ +/- 9,450' | WAVE - REAMER | >> BAROID AUGER AND HIGH G DRYER EXPECTED ON LOC. TODAY . | MUD PROP.: VIS: 47, PV/YP: 17/27, GELS: 10/12, FL: 4.4 , MBT: 7.5 , PH: 10 | Militry /MINE./EGPC/Env. Approval
.+882-1633331603 | (+/- 77' INTO A/R-B) | WOOD- STAB. | A/R "A"@ 9,171' MW : 9.8 PPG BTM @ 9255'. | DIRECTION PLAN :- KOP @ 7261.5' & BUILD TO +/- 41.4 AT 225 AZM | YES / NO NEED /NO/ NO (SHALLOW GAS)
RIG SUPT: MOSTAFA ZAYED | 7"LINER @ +,-14,200' | BARIOD- CENTRIFUGE. | MD: 9208' INC:37.09⁰ AZM: 225.8⁰ TVD: 9063.9' V.SEC: 607.55' DLS:1.34 | W/ 2 DLS DEG @ 9331.49' THEN HOLD SAME TILL TD | GAS
012-00614568 | 3X 500 BBL EPIS STORAGE TANK. | W.FORD.- LINER HGR | CT-CT : 25.2 FT, BELOW: 15.99 FT, LEFT: 19.48 BHCT: 177⁰ F |  | TD 17,000'.
| OFFSET WELLS: | CRT: EDC | >> FRESH WTR PIT: 70 % FULL >> DRILL WTR PIT : 100 % FULL | 8 1/2" BHA : 8 1/2" PDC BIT + 6 3/4" RSS W/ 8 3/8" STAB +6 3/4" FLOAT SUB+ | READY
V.SAT: 980-0125 | OAKHILL-W1X, MAPLE-1X |  | ** DIESEL STOCK ENOUGH FOR 6 DAYS. | 6 3/4" MWD + 8" S. STABILIZER + 6 3/4" PBL SUB +6 X 6 1/2"D/C’s + | 20" CONDUCTOR @ 49' PEN
|  | AG WTR PIT | ** PRIMARY / SEC.OBJ: A/R -C, E / A/R - G, BAH | 6 1/2" JAR + 2 X 6 1/2"D/C’s + 21X 5"HWDP | CONSTRUCTION CO. : AL SHROUK
PMP: | TD: 14,200' | SINAI - D. WTR. | ** ACTUAL/PROPOSED @ CURRENT DEPTH: 18.3/22 DAYs . | 8 1/2" BITS: DD506VTX & TK66
EDC - 54 | FAGHUR S-8 | 8-1/2" | CONT. POOH W/ 8-1/2" PEND. ASSY. W/ BAKER MWD FOR BIT | POOH W/ 8-1/2" PEND ASSY. W/ BAKER MWD F/BIT CHANGE T/ SURFACE.
2000 HP / TDS / RKB: 35' | GAS | HOLE | CHANGE T/ 11,000 FT | M/U & RIH W/ NEW BIT, CONT. DRILLING 8 1/2" VERTICAL HOLE T/ 16,300' | WKAL Y-3
| VERTICAL | OBM (10.5 PPG) | >> AVG. TRIP-OUT LOSSE's : +/- 3.0 BPH. |  | Militry/MINE CLEAR./EGPC /ENV. App.
AMR MOHSEN | Militry/MINE CLEAR./EGPC /ENV. App. | MI- MUD. | >> HOLE IN GOOD COND. |  | YES / NO NEED / VERBAL / NO
KHALAF OMAR | YES/ NO NEED / VERBAL / IN PROG | BAKER - DIR. |  | MUD PROP.: VIS:75, PV/YP: 35/21, GEL: 14/26 , MWT.: 10.5 PPG. , HPHT: 4.8 | OIL.
012-27640856 (C.M) | 20" CONDUCTOR @ 40 FT | SLB - CMT. |  | ES: 410 , OWR 71/29 ,LIME : 3.24 | TD. 14300'.
010-33345483(C.M) | 13 3/8" CSG (68#, K-55 , BTC) @ 2193' | SAP & PREM - TRS & CRT | BIT (DD407VTX) FTG: 1660' HRS: 66.5 ON-BTM: 58 ROP: 28.5 FPH | MUD PLAN :- | 80 % ON GOING.
VHF RADIO (CHANNEL8) | (14 FT INTO APOLLONIA "A") | UNICO - R.REAMER. | MASAJID @ 15,338', M.WT: 10.5 PPG BTM @ 15,390' | >>START W/FULL BRIDGING (15 PPB MARBLE, 3 PPB CHEK LOSS & 3 PPB LC LUBE F) | CONSTRUCTION CO: ALEKHLAS
0224062554(T.P) | 9 5/8" CSG (43.5#,N-80,BTC) @ 12,000' | WOOD- STABLIZERS. | >> HAD NO R.REMERS & PBL SUB BACK UP ON LOCATION | >> BEFORE ENTER AEB-6 RESERVOIR, LOAD SYSTEM W/ 2% MAX SHIELD | WKAL D-3X( NEED MILITRY APPROVAL)
0224062654(MAT) | (1034 FT INTO AEB-C) | NOV- JAR & SH. SUB. | MD: 15,305' INC: 0.6⁰ AZM: 137.71° TVD: 15,302.88' V.SEC: 94.24' DLS: 0.27° |  | Militry/MINE CLEAR./EGPC /ENV. App.
| 7"LINER CSG (29#,N-80,BTC) @16,300' | EMEC- CENTR & H.DRYER | >> HAD 2,000 BBL OBM & WASTE MANAGEMENT EQUIPMENT AND CREW |  | NO / NO NEED / NO / NO
RIG SUPT: MOSTAFA ZAYED |  | HALL- LINER HGR | >> HAD ONLY 1 STD BY WATER TRUCKS |  | OIL.
012-00614568 | OFFSET WELLS: | W.FORD- PBL | ** TARGET TOLERANCE: 50 M RADIUS. | 8 1/2'' BHA : 8 1/2'' PDC BIT + BIT SUB W/ F.V + 6 1/2" D/C + 8 3/8'' ROLLER + | TD. 17500'.
|  | EPIS &MI- WASTE MANG. | ** DIESEL STOCK ENOUGH FOR 7 DAYS. | 6 ¾” MWD + 8 3/8" R. REAMER + PBL SUB + 9 * 6 1/2'' DC + 6 1/2'' JAR + | NEED TO BUILD.
| WTR. SOURCE: SIWA MWW-1X | KALABSHA & SIWA PIT | ** PRIMARY / SEC.OBJ: SAFA | 2 * 6 1/2'' DC + 24 * 5" HWDP | CONSTRUCTION CO: ALEKHLAS
PMP: 3736 | TD: 16,300' | SINAI - D. WTR. | ** ACTUAL/PROPOSED @ CURRENT DEPTH: 29.8/ 43 DAYS. | 8-1/2" BITS: DD407VTX, K5M426, TKC66, MSXI616LUBPXG-P, MDSXI713MWEB
ISLAM DAHSHAN | STAN JACKSON | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | DRLG Technical Support : MOH.NASR | Khaled Ghanaym
TELE: 01000031114-01271488855 | TELE: 01277612182 | A/G: VERNON 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01220044064 - 01013334556 | 01275111158
KHALDA PETROLEUM CO.
|  |  | AM DRILLING REPORT | TEAM-2-DRLG | 2023-09-02 15:29
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS
EDC - 61 | NU-33 (SPUDDER WELL) | 8 1/2" | FIN'D RIH W/ 7" PROD. CSG (29# & 26#, BTC) TILL TAGGED BTM @ 12318' | CIRC. HOLE CLEAN (1.5XBTM UP ) & CONDITION MUD
1200 HP/ TDS / RKB: 22' | WIW | HOLE | >> HAD HARD WASH DOWN LAST JT AND WORKING ON SAME | R/D PREMIER POWER TONG & R/U CMT HEAD LOADED WITH TOP & BTM PLUG | NU-38
BOP:13 5/8"-5K PSI WP | DEVIATED | KCL POLY MUD(10.8 PPG) | >> WASH DOWN WITH 150 GPM & P.P : 850 PSI. & 3 BPH DYN. LOSSES | CIRC WHILE FINISH MIXING CMT. | Militry /MINE./EGPC/Env. Approval
MAX. PULL 440 KLB, 12000' | Militry /MINE./EGPC/Env. Approval |  | >> HAD PRESSURE INCREASED MANY TIMES TO 1200 PSI ON 150 GPM | PREFORM CMT JOB AS FOLLOWING | YES / NO NEED / VERBAL /IN PROGRESS
| YES/ NO NEED /VERBAL /IN PROGRESS | BAKER- MUD. | WHILE WORKING ON HOLE FILL IN LAST JT | >> PUMP 60 BBL (11 PPG) SPACER MUDPUSH II | OIL
MAHMOUD ABDEL RAHMAN |  | BAKER - DIR. | CIRC. HOLE CLEAN (1.5XBTM UP ) & CONDITION MUD WHILE FINISH | >> 146 BBLS( 11 PPG) FILER LEAD, 130 BBLS( 11 PPG) L.WT LEAD, DROP | TD 11,200'.
|  | SLB - CMT. | MIXING CMT MIX FLUID & SPACER … IN PROGRESS. | BTM PLUG, 135 BBLS( 11.5 PPG) LW TAIL | READY
| 9 5/8" CSG (36#, K-55,BTC) @ 2935' | PREM & EDC - TRS & CRT. | >> CIRC. W/ 220 GPM HAD SPP = 900-1050 PSI & DYN. LOSSES = 4 | >> DISPLACE W/ 20 BBL F.WTR, 445 BBL 9.3 KHARITA WTR
012-26759111 (C.M) | (76' INTO APOLLONIA) | WAVE - R.REAMER.
010-63522269 (C.M) | 7" CSG(29&26 PPF, N-80,BTC)@12,318 | WOOD- STABLIZERS.
VHF RADIO(CHANNEL8) | (CALL TD EARLY 182') | GESCO- JAR & SH. SUB. |  |  | MENES-75 (NEED MILITRY APPROVAL)
01221112188 (T.P) |  | EMEC- CENTR & H.DRYER |  | MUD PROP.: VIS: 56, PV/YP: 26/28, GELS: 8/12, FL: 4.6, MBT: 5, PH: 9.5 | Militry /MINE./EGPC/Env. Approval
02-24062661 (T.P) |  | WAVE- PBL | ** LAST PAY-ZONE : AEB-6 @ 11810' |  | NO/ NO NEED / NO /NO
|  | EPIS &MI- WASTE MANG. | PALEOZIOC @ 11,877' MW :10.8 PPG BTM @ 12,318' | DIR. PLAN: 1ST KOP @ 7997', BUILD 15.48° TILL 8771' THEN HOLD T/9217' | OIL
|  | M.SHOOT -WELL SERVICE | MD:12,252' INC: 2.56⁰ AZM: 203.63° TVD: 12,286' V.SEC: 340.94' DLS: 0.52° | 2ND KOP @ 9217', TILL EOC@ 9991' (0 INCLINATION) THEN HOLD TO BTM. | TD 11,200'.
|  |  | CT-CT: 15.5 FT ABOVE: 4.97 FT RIGHT :14.63 FT | 8-1/2" BHA: | NEED TO BUILD
RIG SUPT: ABDALLAH IBRAHIM | OFFSET WELL'S: |  | ** TARGET TOLERANCE: 50 M RADIUS..
01212009267 | NU-23X & NU-27 | SALAM WTR PIT | ** DIESEL STOCK ENOUGH FOR 4 DAYS.
|  | MENES WTR PIT | ** PRIMARY / SE OBJ: AEB-3A&3D / ALAM., AEB-1 , AEB-3C & AEB-6
PMP : 3711 | TD: 12,318' | GAWEESH - D. WTR. | ** ACTUAL/PROPOSED @ CURRENT DEPTH: 22.85 / 19 DAYS | >> 8 1/2" BITS: U713MCDEGZU
EDC - 65 | WD 33-15-12 | 12-1/4" | POOH W/ OPEN END 4 1/2" D/P T/ 1317’ (± 330’ ABOVE CMT PLUG) (13 STD) | M/U & RIH W/ 12.25'' DRLG SLICK ASSY. ON 4.5" D/P TILL TAGGED TOP OF | WD 33-A-1X
950 HP / TDS / RKB: 17' | OIL | HOLE | FLUSH STRING W/ 50 BBL WATER TO CONFIRM THE STRG IS CLEAN. | CMT PLUG , DRILL-OUT CMT | Militry /MINE./EGPC/Env. Approval
5K PSI BOP / CAMP/ 360 KLB | DEVIATED | MUDDY WTR | >> HAD A RETURN AFTER 30 BBLs >> LOSSES DURING FLUSH : 35 BPH | CONT. DRLG 12 1/4" VERTICAL HOLE T/ ± 4250' ( ± 56 FT IN A/R A) | YES / NO NEED /NO/ NO (SHALLOW GAS)
MAGED ELSHABRWY | Militry /MINE./EGPC/Env. Approval | EMEC- MUD. | POOH W/ OPEN END 4 1/2" D/P'S AS CMT STINGER T/ SURF. |  | OIL.
MOH. SAAD BEHARY | YES/NO NEED/VERBAL/NO (SHALLOW GAS) | BAKER- DIR. | M/U 12" TEST PLUG ASSY. & RETRIEVED 12’’ WEAR BUSHING, |  | TD 7,000'
| 20" CONDUCTOR @ 52 FT | HALL - CMT. | CHECK THE SAME, OK , INSTALLED IT AGAIN, L/D 12" TEST PLUG. |  | READY
012-82051592 (C.M) | 13 3/8" CSG (68#, K-55 , BTC) @1472' | PREMIER -TONG & CRT. | >> 2nd CMT PLUG IN PLACE @ 3:30 AM |  | CONSTRUCTION CO. : ALMANSORA
0227063241 (C.M) | (11' INTO APOLL.) | WOOD - STAB. | BIT ((U616)) FTG: 1556' HRS: 33 ON-BTM: 20.7 ROP:75 FPH
012-02034203 (T.P) | 9 5/8" CSG (43.5#,N-80,BTC) @ 4,250' | WAVE - REAMER. | KHOMAN (A) @ 1908', M.WT: 8.6 PPG BTM @ 3028' | MUD PROP.: MUDDY WTR & GEL SWEEPS , MWT:8.5 PPG , VIS: 30, | RIG RELEASE
02-24062565 (T.P) | (56 FT INTO A/R-A) | W.F - JAR & SH. SUB. | >> THIEF ZONE @ 2157' & 3006' (KHOMAN A) | MUD PLAN:- 9 PPG 3-5 % KCL POLYMER LOADED W/ 3 PPB SOLTEX, 3 PPB
| 7"LINER CSG (29#,N-80,BTC) @ 7,500' | EMEC - CENTRIFUGE. | >> ONE ST. BY WTR TRUCKS F/ SINAI ON LOCATION | STRATAHEAL, 10 PPB SIZED MARBLE 2 PPB GRAPHITE.
| PLAN TO USE DIVERTER ON SURFACE | EMEC -HI G DRYER | >> DRILL WTR PIT : 30 % FULL , FRESH WTR PIT : ZERO% FULL | DIR. PLAN: KOP @ 4900', BUILD 30.65° INC W/32.43 AZMTH TILL 6125'
RIG SUPT: MAHMOUD SHAFI | OFFSET WELL'S: | WAVE- PBL | ** TARGET TOLERANCE: 50 M RADIUS.. | THEN HOLD T/7500' (TD).
012-21110001 | WD33-15-4 | BAKER- LINER HGR | ** DIESEL STOCK ENOUGH FOR 6 DAYS. | >> BHA: 12 1/4" PDC BIT + BIT SUB + 4 X 8 1/4” D/C + X/O + 8” PBL SUB
|  | M.SHOT-WELL SERVICE | ** PRIMARY / SEC: AR-C / APPOLONIA. | 10X8 1/4” D/C +8” DRILLING JAR+2X8 1/4” D/C +X/O SUB+12X4 1/2” HWDP
VSAT : 980-0811 | TD: 7,500' | WH - D. WTR. | ** ACTUAL/PROPOSED @ CURRENT DEPTH: 6 / 6 DAYs. | >> 12 1/2" BIT: U616 (RR) & GTI65DMHO (RR)
ISLAM DAHSHAN | STAN JACKSON | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | DRLG Technical Support : MOH.NASR | Khaled Ghanaym
TELE: 01000031114-01271488855 | TELE: 01277612182 | A/G: VERNON 01283182726 |  | TEL: 01220044064 - 01013334556 | 01275111158
KHALDA PETROLEUM CO.
|  |  | AM DRILLING REPORT | TEAM-2-DRLG | 2023-09-02 15:29
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS
EDC - 75 | MRZK-208 | 12-1/4'' | DRLG @ 115' (1.5 HR) PROG: 83 FT AV. ROP: 42 FPH C.ROP: 43 FPH | CONT. DRLG. 12 1/4" SURFACE HOLE T/ +/- 2,100'. | MRZK-214
1500 HP/ TDS / RKB: 30' | OIL | HOLE | BIT (GTX-CG1) FTG: 83' HRS: 2 ON-BTM: 1.1 ROP: 75.5 FPH | >> SWEEP HOLE W/ 30 BBL HVP LOADED W/ 80 PPB LCM EVERY 2 STD'S FOR 1ST 1600 FT | Militry /MINE./EGPC/Env. Approval
(HALL BUNDLE SERVICE) | DEVIATED | SPUD MUD | MOGHRA @ SURF. 100% SD @ 90' GAS: NILL | >> SWEEP HOLE W/ 30 BBL'S ANTI BALLING F/ ±1600' TILL CP EVERY 2 STD'S. | YES/ NO NEED / NO /NO
NAGM EL-DEEN | Militry /MINE./EGPC/Env. Approval | BAROID- MUD. | LOSSES: 30/10 BPH M.WT: 8.8 PPG OFF/ON- TRQ: 0.5/1.5 K-FT.LB | @ +/- 2100' SWEEP HOLE W/ ANTIBALLING PILL & POOH FOR BIT & BHA SURFACE. | OIL.
MOHAMED MAMDOUH | YES/ NO NEED / VERBAL/IN PROGRESS | HALL- DIR. | WOB: 3-7 KLB RPM: 70-80 GPM: 250 P.P.: 50-60 PSI | RIH W/ 12 ¼” NEW PDC BIT W/ 12 1/8” S.STAB T/ 2100’ BTM. | TD 7,000'
| 20" CONDUCTOR @ 20' PEN | HALL - CMT. | >> WASH & REAM ONE TIME EVERY STD DRILLED OR AS HOLE DICTATE. | CONT. DRLG 12 1/4” SURF. HOLE T/ +/- 3,535 FT (16 ft into Apollonia-a fm). | NEED TO BUILD
| 9 5/8" CSG (36#, K-55 , BTC) @ 3535' | PREMIER -TONG & CRT. | >> PREC. SWEEP HOLE W/ 30 BBL HVP LOADED W/ 80 PPB LCM EVERY 2 STD'S. |  | SHADOW E-10
02-27063297 (C.M) | (16 FT INTO APOLL. FM) | WAVE - STAB. |  |  | Militry /MINE./EGPC/Env. Approval
01050025318 (C.M) | 7" CSG(26,N-80, BTC) @ 7000' | UNICO - REAMER. |  |  | YES/ NO NEED / VERBAL /NO/SHALLOW GAS
01283909320 (C.M) |  | WAVE - JAR & SH. SUB. |  | MUD PLAN : | OIL.
VHF RADIO(CHANNEL8) |  | EMEC - CENTRIFUGE. |  | SWITCH OVER TO 9.8 PPG 7% KCL/POLY MUD W/ 3 PPB SOLTEX @ ± 1600’ | TD 15,000'
02-24062575 (T.P.). |  | MI -HI G DRYER | >> PLAN TO USE OBM IN NEXT SECTION. | INCREASE M.WT GRADULLAY T/ 11.0 PPG @ +/- 2200' THEN INCREASE | NEED TO BUILD
012-71119760 (T.P.). |  | WAVE- PBL |  | GRADULLAY TO 11.3 PPG AT CP (11.5 PPG BASED ON WIPER TRIP COND.).
| PLAN TO USE DIVERTER ON SURFACE | BAKER- LINER HGR |  | DIRECTION PLAN:- | AG-164
RIG SUPT: EL-SAYED HAMZA | OFFSET WELL'S: | MULTI SHOT-EGOSCO | >> 21 1/4" -2K DIVERTER ON LOCATION. | KOP @ 4500' BUILD ANGLE T/32.2 DEG INCL W/31.872 DEG AZM & 2 DEG DLS | Militry /MINE./EGPC/Env. Approval
012-28916988 | MRZK-164 & MRZK-189 |  | >> DRILL WTR PIT: 70 % FULL , FRESH WTR PIT: 100 % FULL | T/6100'(J SHAPE )& HOLD TO 7000' TD | YES/ NO NEED / NO /NO/SHALLOW GAS
|  |  | *** TARGET TOLERANCE: 50 M RADIUS. | 1ST 12 1/4" SLICK BHA T/2100' | OIL.
|  |  | ** DIESEL STOCK ENOUGH FOR 4.5 DAYS. | 12 1/4" MTB +BIT SUB (F.V) + SHOCK SUB (TOTCO SEAT) + 3 x 8 1/4" D/C+X/O | TD 12,500'
PMP: |  | WD WTR PIT (5 KM) | ** PRIMARY / SEC: A/R-G DOL. & U-BAH / L-BAH & KHARITA | 18 x 6 1/2" D/C + 6 1/2" JAR + 3 x 6 1/2" D/C + 12 x 5" H.W.D.P. | NEED TO STAKE
VSAT : 980-0331 | TD: 7,000' | WH - D. WTR. | ** ACTUAL/PROPOSED @ CURRENT DEPTH: 0.3 /0.3 DAYs. | 12-1/4" BITS :GTX-CG1
EDC - 76 | WD 09-A02 | 17-1/2'' | R/M: 85 % R/U: 60 % >> EXPECTED TO SPUD ON 6/9/2023. | R/M & R/U ON WD 09-A02 | MAPLE-02 (NEED MILITRY APPROVAL)
2000 HP/TDS (BPM)/RKB: 35' | WIW | HOLE | >> R/U MAST 100%, SUBASE: 100 %, MUD SYS. :80 %, MAIN CAMP: 95% | EPIS CHECK RIG BEFORE ACCEPTEANCE. | Militry /MINE./EGPC/Env. Approval
10K PSI BOP | XXXXX | SPUD MUD | >> EXPECTED TO COMPLETE RIG MOVE ON 30 /8/2023. | >> NEED RIG CONTRACT. | NO/ NO / NO /NO/SHALLOW GAS |  | MENES-47
RATED DRLG DEPTH: 15,000' | Militry /MINE./EGPC/Env. Approval | XX - MUD. | >> RAISED UP MAST ON 9/8/2023 AFTER EPIS DROPS TEAM MADE CHECK | >> NEED RIG VENDOR LIST | OIL. |  | NO / NO NEED / NO /NO
ISLAM THABET | YES/NO NEED /NO/NO/SHALLOW GAS | XXX- DIR. | >> INSTALLED CSG BOARD, 4 FIXED PLATFORMS FOR MAST. | >> NEED WELL PROGRAM ,OUT LINE & BITS PLAN. | TD 14,000' |  | OIL.
| 20" CONDUCTOR @ 60' PEN | XXX - CMT. | >> RAISED SUB-BASE ON 12/8/2023. | >> NEED TO CREATE WELL ON WELL VIEW. | NEED TO BUILD |  | TD 12,000'
| 13 3/8" CSG (68#, K-55, BTC) @ XXX' | XXX -TONG & CRT. | >> INSTALLED TOP DRIVE GUIDE ON 20/8/2023 | >> NEED TO INSTALL V-SAT & COMMUNICATION SYSTEM. | CONSTRUCTION CO. : ALMANSORA |  | 20 % ON GOING
| ( XXX' INTO APOLL.) | XXX - STAB. | PENDING EQUIPMENT:- | >> NEED P/U CAR FOR CO. MAN. |  |  | MENES-46
0227063297 (C.M) | 9-5/8" CSG(43.5#,47,N-80, BTC) @ XXX | XXX - REAMER. | # BOP COMPLETE SET, EXPECTED T/ ARRIVE ON 30/8/2023. |  | OAKHILL SW-01X(NEED MILITRY APPROVAL) |  | YES / NO NEED / NO /NO
XXXX (C.M) | (+/-XXX FT INTO A/R-A FM.) | XXX - JAR & SH. SUB. | # ONE MAIN DIESEL ENGINE, EXPECTED ARRIVE ON 30/8/2023. |  | Militry /MINE./EGPC/Env. Approval |  | OIL.
XXXX (C.M) | 7" LINER @ XXX' | XXX - CENTRIFUGE. | # RES. TANKS OF MUD SYS, EXPECTED ARRIVE ON 30/8/2023. |  | NO/ NO NEED / NO /NO/SHALLOW GAS |  | TD 12,000'
02-24062576 (T.P.). |  | XXXX -HI G DRYER | # DIESEL TANK & ANOTHER WTR TANK, EXPECTED T/ ARRIVE ON 30/8/2023. |  | OIL. |  | NEED TO BUILD
0100-1560459 (T.P.). |  | XXXX- PBL | # D/P UNDER INSPECTION IN SALAM, EXPECTED T/ARRIVE BEFORE ACCEPT. |  | TD 14,000'
| PLAN TO USE DIVERTER ON SURFACE | XXX LINER HGR | # NEED EQUIPMENT CERTIFICATES, EPIS TO CHECK RIG BEFORE ACCEPT |  | NEED TO BUILD |  | MENES-69
RIG SUPT: EL-SAYED HAMZA | OFFSET WELL'S: | MULTI SHOT-XXX | >> PLAN TO USE DIVERTER IN SURF HOLE. |  | OLYMPIC-2 WIW |  | Militry /MINE./EGPC/Env. Approval
012-28916988 | XXXXX |  | >> DRILL WTR PIT: 40 % FULL, FRESH WTR PIT: 40 % FULL . |  | Militry /MINE./EGPC/Env. Approval |  | YES/ NO NEED / NO /NO
|  |  | *** TARGET TOLERANCE: XXX M RADIUS. |  | YES/ NO / NO /NO/SHALLOW GAS |  | OIL
|  |  | ** DIESEL STOCK ENOUGH FOR XXX DAYS. |  | WIW |  | TD 12,000'.
PMP: |  | WD WTR PIT (XXX KM) | ** PRIMARY / SEC: XXX/ XXX |  | TD 14,000' |  | NEED TO BUILD
VSAT :980-0136 | TD: 14,000' | WH - D. WTR. | ** ACTUAL/PROPOSED @ CURRENT DEPTH: XX /XXX DAYs. | 17-1/2" BITS :XXXX | NEED TO STAKE |  | CONSTRUCTION CO: UNION
ISLAM DAHSHAN | STAN JACKSON | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | DRLG Technical Support : MOH.NASR | Khaled Ghanaym
TELE: 01000031114-01271488855 | TELE: 01277612182 | A/G: VERNON 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01220044064 - 01013334556 | 01275111158
|  |  | KHALDA PETROLEUM CO. | TEAM-3-WO
|  |  | AM WORKOVER REPORT |  | 2023-09-02 15:29
RIG | WELL | PHASE | PHASE | PLAN | REMARKS
EDC - 12 | MAGGIE-1X | OIL | CONT MILLING JUNK ( ABOVE 7" B.P). F/14778' T/14779' (DRLG .DEPTH ) | CONT. MILLING JUNK W/ 6" M.M.JUNK MILL &CONT. MILL OUT 7" B.P’S
750 HP, 11"-10K BOP, 280 KLB. | R/C (Part-03) Retrieve Kill STG, continue Re-entry the well down and complete the well | 9 5/8" CSG | (1 FT PROGRESS ) W/THE FOLLOWING PARAMATERS : | & PUSH SAME DOWN TILL TOP OF PROP. @ +/-15,065 FT.
KELLY / MAIN CAMP. | on LSAFA reservoir TOP & BTM intervals. | 7" LINER | *** W.O. MILL 3-8K.LB *** RPM: 40-50 *** TORQUE : 600-1100 LB.FT | SWEEP HOLE & CHC, POOH W/ DP'S & STD BK SAME ON DRK. | TUT-135
|  |  | *** P.RATE : 4 BPM *** P.P : 1100 PSI | M/U & RIH W/7” SCR. ASSY. & T.O.L POLISH/DRESS ASSY. ON SAME 3 ½” D/P’S | I/C
AYMAN ASHRAF |  | LSAFA Top RES. PRESS. & TEM. | *** SWEEP THE WELL W/ 20 BBL H.V.P EVERY 1 FT PROGRESS. | TILL +/-15,000 FT, POLISH T.O.L.,SWEEP & DISPLACE HOLE W/ 9.3 PPG | TUT-130X
| SQUEEZED CSG LEAK INTERVAL (4448' - 5331') | ± 3,000 psi / ± 290 Deg. F. | *** HAD 2 BBL DYNAMIC LOSSES . | CORR. INHIB. FILTRATED SYS. WTR, POOH & L/D ALL. | I/C
02- 27063393 (C.M) | SQUEEZED AEB-3C&3D (9600'- 9610') 10' & (9664'-9688') 14' | LSAFA BTM RES. PRESS. & TEM. |  |  | TUT-125
01099938913 (C.M) |  | ± 6600 psi / ± 290 Deg. F. |  |  | Retrieve S&S completion string, isolate KHAT & AEB reservoirs,
01227640638 (C.M) |  | SYS. WTR (9.1 PPG FIL. KHRITA) |  |  | perforate/test LBAH reservoir and completion with suitable pump.
01221112147 (T.P) | TIE-BK T.O.L @ 12381' |  |  |  | TUT-85
V-SAT : 980-0981 |  | TRS :?? |  |  | Retrieve ESP completion on 13 % Cr TBG, retrieve/fish straddle PKR,
|  | S/L : ??? |  |  | perforate KHAT reservoir and complete well with selective WI STG.
RIG SUPT: AHMED ASHOUR | 7" B.PLUG @ 15100' | INSPECTION: ??
1204432182 | 7" CSG (29 #, N-80, BTC) @15436' | COMP: HALL | *** LAST TAGGED T.O.F " AFTER 5 FT PROGRESS AT 14,778 FT (D. DEPTH)
|  | CMT : HALL. | ** DIESEL STOCK ENOUGH FOR 10 DAYS | *** BHA : 6" M.M.R. CONCAVE JUNK MILL (3.25FT)+ 5" OD BOOT BASKET (5
|  | FISHING : BAKER | PLAN PERF LSAFA BTM ( 14790'-14810') 20' | FT)+5" OD BOOT BASKET (3 FT)+ 4 3/4" OD BIT SUB+4 3/4" BUMPER JAR+4
PMP: 3704 | PBTD @ 15305 FT | F.WTR - SINA | OPEN PERF:- LSAFA TOP ( 14682'-14710') 28' | 3/4" SUPER JAR+6 X 4 3/4" D/C'S STD'S.
HT - 101 | WKAL-N04 | WIW | R/D 100 % R/M 100 % R/U 90 % | CONT R/U
5K BOP, 1000 HP, 300 KLB. | R/C | 9 5/8" CSG | *** RELEASED RIG F/ WKAL-N02 @ 7:00 PM ON 09-08-2023. | CHECK THE RIG FOR ACCEPTANCE.
KELLY / MAIN CAMP. |  | 7" LINER | WORK DONE: | OBSERVE WELL F/ STATIC COND. & KILL SAME W/ KHAR. WTR IF NEEDED | SELKIT-05
RIG ELEVATION : 19.7 FT |  | 9.2 KHA. WTR | *** INSTALL ACS (ANTI-COLLISION SYSTEM) (WAS INSTALLED BY HI-TECH TEAM, | N/D 3 ⅛" X 5K PSI CIW X-MASS TREE & N/U BOP & P/T SAME. | R/C, Re-entry, perforate/acidize/test ALM-DOL reservoir
|  | KHAR RES. PRES & TEMP. | F/T SAME FOUND IT FAILED, NEED HT TEAM TO INVESTIGATE AND FIX PROBLEM) | POOH WITH KILL STRING ON EUE TBG AND L/D ALL. | PHIOPS-11
AHMED HENDY |  | ± 3400 PSI & 220° F. | ***HAD FALL ARRESTOR IS SUCK AT THE SECOND SECTION OF THE MAST. | R/U E/L P.C.E AND P/T SAME. | Pump Replacement
MOHAMED MANSI | 7" T.O.L @ 9483 FT | S/L: ??? | *** CLEAN MUD SYSYTEM TANKS WITH WATER BLASTING & PAINT THEM | E/L RIH WITH 5.6” GR-JB-GR-CCL, MARK THE CABLE & POOH. | PHIOPS-08 (ST)
| 7" LINER @ 14,997 FT ( 29 # , N- 80 , BTC ). | E/L: SAP. | (70%, FINISHED CLEANING 3 OUT OF 4 TANKS & PAINT 3 OUT OF 4 TANKS) | E/L RIH WITH 7” B.P ON CCL, CORRELATE AND SET SAME AT +/-10,000 FT. POOH. | TBG & PR
010-11423838 (C.M) |  | DHT : HALL | ***HAD CABLES ARE FOUND SPLICED , NEED TO BE REPLACED | PRESSURE TEST CSG TO 1,000 PSI ON STAGES. OPEN B.H TO CHECK RETURN | WKAL-I04
012-05776661 (C.M) |  | TCP : HALL | *** INSTALL EMERGENCY LIGHT ON MUD TANKS, RIG FLOOR, MAST, | E/L RIH WITH CMT BAILER AND CAP B.P WITH 10 FT CMT. POOH & R/D E/L. | P/R (13 % CR TBG)
012-82924217 (T.P) |  | M.G'S: EXPRO | SWACO CONTROL PANEL, CHOKE MANIFOLD……….(DONE BY 80%) | M/U & RIH W/ PERF.-TEST STG (S&P) ON 3 ½” EUE OR SUP. TBG (COND. B) | WKAL-P03
SUP. INT: WALID ZAYTONA |  | C.T: ??? |  | TO PERF./TEST KHAR. INT. (7,295-7,360) 65 FT & (7,485-7,620) 135 FT | TBG & PR
012-74833838 |  |  | *** NO P/U CAR FOR CO. MAN. & NO STAND BY TRUCK | R/U E/L & RIH W/ GR-CCL CORR. TOOL AND CORRELATE GUN DEPTH, POOH. | BUCHIES-S02
VHF Radio channel 8 |  |  | *** DIESEL STOCK ENOUGH FOR 12 DAYS. | SPACE STRING LENGTH, N/U KPC FLOW TREE AND P/T SAME WITH STRING | Retrieve kill string, continue Fishing ESP completion, then complete
(NOT WORKING) | PBTD (BP) @ 14489' |  | OPEN PERF.: U.SAFA (14,452-14,484) 32 FT | TO 3000 PSI AGAINST 2.75” FB-2 C.V, THEN RETRIEVE SAME. | well with new pump string.
PMP: 3745 |  | F.WTR - GAWESH | ISOLATED PERF.: U.SAFA (14,494'-14,508') 14', L.SAFA (14,548'-14,578') 30' | SET RTTS PKR AND SOW AS PER HALL. &P/T ANNUL T/ 1000 PSI ON STAGES.
NDC-04 | RIDGEWOOD-03 | OIL | R/D: 100% R/M: 100% R/U: 100% | CHECK RIG FOR ACCEPTANCE & ACCEPT SAME |  |  | Attia AbdElaziz
750 HP / KELLY | I/C Scrapper, polish/dress TOL, | 9 5/8'' CSG | *** SECURED THE WELL & RELEASED THE RIG T/ RIDGEWOOD-03 | N/D 11"-10K PSI BLIND FLANGE & 13 5/8"-5K PSI x 11"-10K PSI C.H.S |  |  | Hany Allam
11"- 5K PSI BOP, 290 KLB'S | Dipole Sonic, perforate/test LBAH reservoir (S&S) completion. | 7" LINER | @ 02:00 PM ON 15-AUG-2023. | MIDCO COLD CUTTER RE-STUB 9 5/8’’ CSG TO BE 4.5’’ TO SUIT | MEGHAR-14 |  | Ahmed Barkat
|  |  | *** DIESEL STOCK @ RIG RELEASE: 4910 GAL'S ( 117 BBL'S) | 13 5/8" - 5K PSI * 11" - 5K PSI "CIW" T.H.S | R/C (PART-02) Retrieve kill string, isolate ARG reservoir, reperforate/test ARE reservoir |  | Mohsen Ashour
AHMED GAMAL | LBAH RES PRESS: +/- 4650 PSI | 9.5 PPG (NaCL) | *** MOVE DISTANCE F/ AG-83 T/ RIDGEWOOD-03 IS 19 KM'S DESERT ROAD. | N/U 13 5/8'' - 5K PSI X 11'' - 5K PSI CIW OIL T.H.S. (COND. A) & P/T SAME | for possible completion. Otherwise, R/C up hole. |  | Khaled Ghanaym
MOHAMED MAGDY |  | COMP/TCP: HALL | ***CERTIFICATES RECEIVED REGARDING 6 MONTH MPI & LIFITNG GEARS | T/ 4000 PSI , N/U RIG BOP & P/T SAME | AG-16 A |  | 01275111158
01212582491(C.M) |  | DIPOLE SONIC LOG: HALL | NSPECTION IS NOT COMPLETE. | M/U & RIH W/ 6" CLEANING ASSY. ON 3 ½” D/P'S T/ 12,300 FT. | Retrieve existing gas lift completion, isolate BAH reservoir, perforate/test |  | Belal Sallouma
01279232426 (T.P) |  | E/L:SAP | ***RCEIVED TWO MUD AGITATORS &PLAN TO REPLACE MALFUNCTIONED ONE. | POOH STD BACK ON DRK. & L/D EXCESS JT'S. | ARG reservoir and completion with suitable string. |  | 01279539944
01228432312 (T.P) |  | POLISH-DRESS MILL: HALL | ***REPLACE ANNULAR BOP PACKING ELEMNT W/NEW ONE….IN PROGRESS. | M/U & RIH W/ 7” X 9 5/8” W.F. TANDEM SCRAPPER ON 3 ½” D/P TILL +/- 12300. | QRN-20 |  | Amr AbdElaziz
| T.O.7" LINER @ 7636 ' | SCRAPER: W.F | *** CHECKING RIG FOR ACCEPTANCE | DISPLACE THE HOLE W/ CORROSION INBITIED NACL BRINE (9.5 PPG) & POOH | R/C-WDW |  | Mohamed Abd Elsalam
Rig Superintendent Eng | MAX. INC. 59.54 DEG @ 10456' | TRS: ??? |  | STD BACK ON DRK. & L/D EXCESS JT'S. |  |  | Walid Sallam
AMR ZIDAN |  | S/L: IOD |  |  |  |  | Esam Eid
012-77442999 | P.B.T.D. @ 12330' | [5 empty] | Dan Mullinus
01277612182
V-SAT : 980-0232 |  |  | *** DIESEL STOCK ENOUGH FOR 5 DAYS. |  |  |  | Stan Jackson
| PBTD @ 12330' | F.WTR: W.HORSE | PLANNED INTERVALS: LBAH (11,934-11,956) 22 ft |  |  |  | Charlie Kennedy
MOHAMED ABDALLA | CHARLIE KENEEDY | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | WO Technical Support : WALID SALLAM | Khaled Ghanaym |  | Abdelmageed Ahmed
TELE: 01000031117 / 01226762111 | TELE: 01201112590 | A/G: VERNON 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01285026752 - 01024478008 | 01275111158 |  | Omar Yahia
|  |  | KHALDA PETROLEUM CO. | TEAM-3-WO |  |  | Abd-Alah Taha
|  |  | AM WORKOVER REPORT | ** MISSED ITEMS: ** NEED S.ROD EQUIP & HYD. SLIPS | 2023-09-02 15:29 |  | Ahmed Elbanauosy
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS |  | Ahmed AbdElaaty
EDC - 31 | NU-10 | OIL | POOH W/ESP ASSY ON 2 7/8'' EUE TBG "FLAT" T/ 5,600 FT. & L/D ALL. | POOH W/ THE EXISTING ESP STRING ON 2 7/8” EUE TBG & L/D ALL. |  |  | Vernon
350 HP, 5K PSI BOP, 100 KLB | R/W (Re-Perforation), TBG & PR | 7" CSG | *** TOT. 125/290 JT 2 7/8" EUE "FLAT" ABOVE 2 7/8" EUE SSD-XD (2.31"). | M/U & RIH WITH TOP PART OF ON-OFF TOOL ON 3 ½” EUE TBG (COND. B). | KAH-UC84 |  | Abd-Allah Taha
|  | AEB-3A/3C RES. PRESS. 2000 PSI | *** FILLED THE WELL W/METAL DISPLACEMENT WHILE POOH . | LATCH INTO BTM PART OF ON-OFF TOOL, CONFIRM LATCH W/ JUST O/P. | SRPR
| ORKB: 22' (EDC-61) | TEMP: 260 °F. | *** USED EDC POWER TONG W/BACK UP & 2 SNUP LINES. | N/U KPC FLOW TREE & P/T SAME W/ STRG T/2000 PSI & P/T SAME W/ STRG | SETH-28
BESHOE SAFWAT |  |  | *** CHECK THE RIG ALIGNMENT EVERY 20 JT. | AGAINST 2.81” FB-2 C.V, THEN RETRIEVE SAME. | SRPR
|  |  | *** 1 CLAMP LOST IN HOLE. | S/L RIH T/RETRVE EXIST. 2.75” FB-2 C.V IN 3 ½” F-NIPPLE @ 9,627 FT. POOH. | SETH-38
| 9 5/8" CSG @ 4723' | 4% KCL WTR | *** MEASURED NORM READING WHILE POOH = (0.1 - 0.3 μSv/ HR). | R/U S/L & RIH WITH 2.3” G.C DUMMY RUN TILL +/-10,700 FT, POOH. | SRPR
| 7" CSG @ 11900' | 8.55 PPG |  | R/U E/L PCE, RIH SETCORE 2” THRU TBG GUN (6 SPF & HMX EXPLOSIVE) | SETH-02
01094478008(C.M) |  | S/L: IOD |  | ON GR-CCL, THEN RE-PERFORATE AEB-3A/3C RESV INT.. POOH & R/D E/L. | ESPR
01285026749(C.M) |  | E/L: SETCORE |  | OBSERVE WELL FOR STATIC COND., UNLATCH STRING F/ ON-OFF TOOL, | TAYIM-W03
02-24062531(T.P) | 7" PHL PKR @ 9493' | COMPLETION: HALL |  | POOH WITH TOP PART AND L/D ALL. | ISRPI
| 3 1/2"ON-OFF TOOL BTM PART@ 9483' | ESP: ***** |  | M/U & RIH W/ NEW ESP ASSY. ON 2 7/8” EUE TBG (COND.-A). | UMB-206
RIG SUPT: AHMED FOUAD | T.O.F (RELEASED GUNS) @ 11529' | TRS: | *** DIESEL STOCK ENOUGH FOR 3 DAYS. | SET CV, P/T STRING FIRST & FINAL WAYS T/ 2500 PSI AGAINST C.V. | SRPR
012-00614093 |  | INSPECTION: | OPEN PERF: AEB-3A INTERVAL (10,114-10,129) 15 FT, (10,210-10,235) 25 FT, | START-UP PUMP & FLOW WELL T/ FLARE TILL GET ACCEPTED RATE. | UMB-222
|  |  | (10,252-10,270) 18 FT, (10,280-10,292) 12 FT, (10,374-10,392) 18 FT & | CHECK PHASE'S ROTATION, SECURE WELL AND RELEASE RIG. | SRPR
PMP: 3760 | P.B.T.D @11823' (CORRELATED) |  | AEB-3C INTERVAL (10,500-10,519) 19 FT.
EDC - 82 | MENES-63 | OIL | DIVERT FLOW T/ AL-MANSOURI TMU F/ TEST (10.5/ +/- 12 HRS STABILIZED
500 HP, 5K PSI BOP , 170 KLB. | I/C | 7'' CSG | TEST) | CONT. TESTING WELL | NU-33
P. SWIVEL / FLY CAMP | 4 1/2" CSG GUN / HYD FRAC |  |  | POOH W/C.T, R/D & OPEN PKR BY PASS, KILL WELL WITH 4 % KCL WATER | I/C
RIG ELEVATION.: 13'. |  | AEB-3D RES. PRESSURE: 3277 PSI | CHOKE WHP SEP,P BFPD BOPD GAS RATE B.S&W CL | OBSERVE WELL STATIC, N/D FLOW TREE, UNSET PKR, POOH WITH FRAC | MENES-01X
|  | TEMP: 270 °F. | " PSI PSI BBL/D BBL/D MMSCF/D % PPM | STRING ON PH-06 TBG, L/D ALL | R/C
FAHD GAMAL |  |  | OP 120 90 573 123 NIL 74 48000 | SUPPLEMENT PROGRAM NEEDED | TUT-72
AHMED EL GHARIEB | 9 5/8" CSG @2,855 FT,(36#,K-55 , BTC) |  |  |  | ESPR
| 7" CSG @ 11,600 FT (29 & 26 PPF, N-80, BTC) | E/L : |  |  | HAY-72
01203311271 (C.M) |  | S/L: |  |  | TBG & PR
| KOP @ 7755 | DHT: HALL | *** HAVE 47 JT'S X 4 1/2" PH6 TBG (W.FORD) USED IN STRG. |  | HAY-17
| MAX. ANG. 22.6 DEG @ 8858 FT | TRS : | *** ON LOCATION: |  | TBG & PR [Cable W/INJ TUBE]
|  | M.G's: EXPRO | *** 6 FRAC TANKS, 3000 BBLS FRESH WTR |  | HAY-67
RIG SUPT: AHMED FOUAD |  | C.T. : | *** 75 * 3 1/2" KPC PH-6 TBG. *** 275 * 4 1/2" KPC PH-6 TBG. |  | TBG & PR
012-00614093 |  | FRESH WTR : SINA | *** 189 * 4 1/2" W.F PH-6 TBG. |  | SAL-18
|  |  | *** DIESEL STOCK ENOUGH FOR 4 DAYS. |  | TBG & PR
PMP: 5923 | PBTD (F.COLLAR) @ 11,516 FT |  | OPEN PERF: AEB - 3D (11,057-11,077) 20 FT
EDC - 84 | WKAN-T03X | OIL & GAS | FIN'D P/U, M/U & RIH W/ O.E STRG W/ 7" HALL.PHL PKR ASSY. T/249' | CON'T RIH WITH OPEN-END COMPLETION STRING ON SAME 3 ½” EUE (B). | WKAN-X02
500 HP, 5K PSI BOP, 240 KLB. | I/C, Wellbore Scrapper, Perforate/Test Safa reservoir, isolate same, then | 9 5/8'' CSG | *** BHA : 5-3/4" CUT LIP GUIDE ( 5" ID ) + 5-3/4" WASHPIPE EXTENSION ( 5" ID) + | R/U & RIH WITH 1 11/16” GR-CCL, CORRELATE DEPTH, POOH & R/D E/L. | I/C
POWER SWIVEL/FLY CAMP | perforate/test/acidize ALM-DOL and completion with suitable pump. | 7" LINER | 5-3/4" DRIVE SUB ( 2-11/16" ID )+ X-O (3 1/2'' IF X 3 1/2'' EUE) ( 2-1/4" ID )+ | SPACE IN/OUT AS NEEDED TO SWALLOW BOTTOM PART OF ON-OFF TOOL, | Perforate/test USAFA reservoir via S&S completion string.
RIG ELEVATION: 12.5' |  | 9.5 KHARITA | 2 X 3 1/2" EUE TBG JT (A)+ 3 1/2" EUE X-NIPPLE (SIZE 2.75") + 4 X 3 1/2" EUE TBG | POSITION PKR ON DEPTH WHILE SET HGR. | MIHOS-1X
|  | TCP : HALL | JT (A) + 7" * 3 1/2" EUE HALL. PHL HYD. PKR. + 3-1/2" EUE TBG PUP JT (A) + 3-1/2" | M/U 4 ½” VAM TOP CIW TBG HANGER ASSY. THEN, PRESSURE-TEST SAME | ESPR
MOH.SALAH EL DEEN |  | CSG GUN : EL-MANSORI | EUE ON-OFF TOOL + 3-1/2" EUE TBG JT + 3-1/2" EUE SSD TYPE "XD" (SIZE 2.81"). | WITH STRING TO 4,500 PSI AGAINST 2.81” MODIFIED PX-PLUG & PRONG | HERUNFER-W07
AHMED FATOH |  | F.WTR: GAWESH | P/T 7" HALL. PHL HYD. PKR USING ITS TEST PINS AGAINST 2.75" MOD. PX-PLUG | INSIDE XD-SSD TOP NIPPLE PROFILE & RETRIEVE SAME. | ESPR
01050025782 (C.M.) | 7" T.O.L @ 8623' | E/L: EL-MANSORI | & PRONG INSIDE X-NIPPLE PROFILE T/3000 PSI, HOLD, OK. | S/L RIH WITH MODIFIED 2.75” PXX PLUG INSIDE X-NIPPLE, P/U STRING TO | HERUNFER-W03
01282161785 (C.M.) | 9 5/8" CSG @ 8886' | COMP : HALL | HALL. S/L RIH & RETRIEVED 2.75” MODI.PX-PLUG & PRONG FROM X-NIPPLE | SET PHL PKR. THEN RETRIEVE THE PLUG & PRONG. POOH. | IPI
01221112123 (T.P) |  | N2 UNIT : PICO | PROFILE, POOH T/ SURF., & L/D. | P/T ANNULUS TO 500 PSI TO CONFIRM PKR SEALING. | HERUNFER-W10
02-24062584 (T.P) | *** ON OFF TOOL @ 11,993' | TEST PKG : PICO | HALL. S/L RIH TO SET 2.81” MOD.PX-PLUG & PRONG INSIDE SSD TOP NIPPLE | INSTALL THE BACK PRESSURE VALVE & N/D THE RIG BOP’S AND N/U | IPI
RIG SUPT:AHMED ASHOUR | *** 7" PHL PKR.12,000.5' | ESD : PICO | PROFILE… IN PROGRESS. | 4 1/16” SOLID BLOCK X-MASS TREE & P/T SAME TO 5000 PSI AGAINST B.P.V. | HERUNFER-W15
012-04432182 |  | M.G'S: EXPRO | *** DIESEL STOCK ENOUGH FOR 6 DAYS. | L-SAFA NATURAL TEST DATA : | Retrieve injection string, Hyd Frac USAFA reservoir and completion
V-SAT :980-0841 |  | S/L : IOD | OPENED PERF ALM-DOL (8,018'-8,028') 10 FT | CK. WHP SEP. BFPD BS&W BOPD GAS H2S | again with WI string.
PMP:3726 | PBTD @ 14,412' | FLUID PUMP : SAP & PICO | OPENED PERF L-SAFA INT's : ( 14,006'-14,030') 24' | 24/64 3350 510 1232 8% 1133 11.6 10
MOHAMED ABDALLA | CHARLIE KENEEDY | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | WO Technical Support : WALID SALLAM | Khaled Ghanaym
TELE: 01000031117 / 01226762111 | TELE: 01201112590 | A/G: VERNON 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01285026752 - 01024478008 | 01275111158
|  |  | KHALDA PETROLEUM CO. | TEAM-3-WO
|  |  | AM WORKOVER REPORT |  | 2023-09-02 15:29
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS
EDC - 86 | SWAG N-06 | OIL | R/D 100 % R/M 0% R/U 0% | CONT R/D ,R/M
5K PSI BOP, 500 HP ,240 KLB | I/ C | 9 5/8" CSG | *** SECURED THE WELL & RELEASED THE RIG T/ SWAG N-06 | CHECK RIG FOR ACCEPTANCE | SWAG-03
POWER SWIVEL/CAMP/12.5' | Test ARG reservoir through S&S completion STG, then Hyd Frac & test same, and completion with suitable pump. | 7" LINER | @ 10:00 PM ON19/8/2023. | RECORD/REPORT SIWHP & CSGSIP AND BLEED OFF SAME | R/W, Retrieve G.L Completion top part, Hyd Frac ARC reservoir and complete
|  | AVG ARC RES. PRESS = | *** DIESEL STOCK @ RIG RELEASE: 4859 GAL'S ( 115.7 BBL'S) | S/L RIH 2.34" G.C TAGGED ON 2 7/8” R-NIPPLE, POOH. | well back with suitable completion STG.
SAMIER ASHMAWY |  | +/-2500 PSI | *** MOVE DISTANCE F/ AG-125 T/ SWAG N-06 IS 17 KM'S DESERT ROAD. | S/L RIH WITH 2 X 10 K PSI M.G AND SET SAME IN 2 7/8” R-NIPPLE. POOH & R/D S/L. | AG-78 DD
AHMED ELNAWAGY |  | TEMP: 230 F | *** RIG WILL MOVE ON 2 CONVEYS (RIG+FLY CAMP) | R/U C.T & N2 UNIT. FLUSH SAME W/WATER TO FLARE, P/T T/3000 PSI | R/C Retrieve N.C, isolate BAH reservoir intervals, perforate/Frac ARG
|  | HALL.:FRAC | *** MOVE CONVOY WILL BE ACCOMPANIED BY AG SECURITY & SAFETY REP. | HOOK UP 5 K PSI TMU TO THE CT FLOW TEE, P/T UPSTREAM LINE TO 3000 PSI. | reservoir and completion with suitable completion.
012-75111153 (C.M) |  | HALL.:C.T | *** ROUTE SURVEY & MOVE PAPERS APPROVED & SIGNED. | RIH W/ C.T START PUMPING N2 AND LIFT THE WELL. | SHADOW-E01
| MAX DLS 3.92 @9108 FT-ORKB | EXPRO :M.G | *** PETROLIFT ENGINEER WILL CHECK ALL LOADS BEFORE RIG MOVE. | DIVERT THE WELL THROUGH THE TESTING EQUIPMENT | TBG & SRPR (Continue Job)
012-21110006 (T.P) | MAX INC 7.89 @9204 FT-ORKB | HALL : COMP. |  | & CONDUCT AN ACCURATE PRODUCTION TEST FOR 12 HR’S. | OLYMPIC-N1X (ST)
0224062586 (T.P) | T. O 7" LINER @ 8676' | SAP : E/L |  | POOH W/C.T TO SURFACE & R/D ALL EQUIPMENT. | I/C Perforate/test AR/E reservoir and completion with suitable A/L system.
|  | HALL.: DHT |  | SHUT IN THE WELL FOR 24 HRS PBU PERIOD. | SWAG-05
RIG SUPT: AHMED ASHOUR |  | S/L:??? |  | R/U S/L & RIH TO RETRIEVE THE M.G’S. | R/C
1200614568 |  |  |  | OBSERVE WELL FOR STATIC CONDITION, N/D X-MASS TREE, N/U BOP AND P/T SAME. | Retrieve natural completion, re-open 5" Liner, add UBAH with ARG reservoir
VHF RADIO (CH-10) |  | F.WTR. WH. HORSE | ** DIESEL STOCK ENOUGH FOR 5 DAYS. | UNSET TBG HGR, UNSET PLS PKR, DISPLACE HOLE WITH 4 % KCL BRINE
V.SAT: 980-0781 | PBTD (L.C) @ 11823 FT-ORKB |  | OPEN PERF. : A/R "G" : (10634' - 10694) 60' | POOH WITH PERFORATION STRING ON 2 7/8” EUE TBG, L/D ALL.
EDC - 87 | WKAL-O02 | OIL | SWEPT HOLE W/ 50 BBL'S H.V.P & DISPLACED SAME W/ 940 BBLS | CON'T POOH W/ 7” SCRAPPER & TOL POLISH/DRESS MILL ASSY. T/SURF& L/D ALL.
500 HP, 11-5K PSI BOP,240 KLB. | R/C,Retrieve ESP completion and complete the well with single WI String. | 9-5/8" CSG | FILTRATED 9.2 PPG KHRT WTR T/ MUD PIT | M/U &RIH W/ ALMANS TCP ASSY W/7” RTTS PKR ON 3 1/2” SUPERIOR (A) | WKAL-O-01X
POWER SWIVEL/FLY CAMP |  | 7" LINER | ** P.RATE = 3 - 4 BPM &P.P. = 500 - 950 PSI ** M.WT IN = M.WT OUT 9.2 PPG | TO REPERF/PERF SAFA INTERVALS. | R/C-WSW
RIG ELEVATION.: 11.5'. |  | 9.1 PPG KHARITA WTR | H.P.J.S.M. & R/D EDC 120 TON POWER SWIVEL. | R/U & RIH W/GR-CCL CORRELATION TOOL & CORRELATE GUN DEPTH. SPACE IN/OUT TO HAVE THE GUN ON DEPTH. | KHEPRI-W02
|  | RIG FILTER | POOH W/ 7" W.FORD NON-ROTATING SCRAPER EQUIPPED W/ 7" BAKER | N/U KPC F.TREE & P/T SAME W/ STRING TO 4000 PSI AND RETRIEVE C.V. | R/C
JOHN KARAM |  | E/L: SAP | POLISH/DRESS MILL ASSY. ON 3 1/2" D/P'S T/14,100' & L/D ALL. | SET 7” RTTS PKR AND SOW AS PER HALL. RECOM, P/T ANNULUS T/ 1,000 | KHP-W03
| 7'' T.O.L @ 8,687 FT | FISH: TRISTATE | *** TOTAL : (11/ 275 JT'S) X 3 1/2" D/P ABOVE POLISH & DRESS MILL ASSY. | PSI TO ENSURE THE PKR SEALING | R/C
| 7” L.SHOE @ 15,447 FT (29#, N-80, BTC) | COMP: HALL | *** PUMPED METAL DISP. WHILE POOH. | OPEN MCV, R/U N2 UNIT, P/T SURFACE LINES TO 4000 PSI, DISPLACE TBG | Retrieve ESP completion on 13 % Cr TBG, isolate ALM-DOL, conduct remedial CMT job against BAH reservoir, then perforate/test
01227640906 (C.M.) |  | POLISH/DRESS MILL: BAKER | *** USE EDC POWER TONG SECURED W/ 2 SNUB LINES. | W/ N2 TILL FLUID LEVEL AT 500 FT ABOVE MCV. | BAH reservoir and completion with suitable pump.
01016372666 (C.M.) | MAX INC = 30.19° @ 10,590' | TCP: ELMANS |  | CLOSE MCV, P/T ANNULUS TO 1000 PSI TO CONFIRM ITS SEALING. | WKAL-P-S1X
01201508884 (T.P) | MAX D.L.S = 2.85° @ 9,931' | DHT: HALL |  | BLEED OFF PART OF WHN2P TO ACHIEVE ± 1500 PSI UNDER BALANCE. | I/C, Scrapper, Polish/dress TOL, perforate/test AEB-3C reservoir and
|  | S/L : IOD |  | R/U W/L LUBRICATOR; LOAD THE FIRING BAR; THEN DROP SAME TO | completion with suitable pump.
| ON OF TOOL DEPTH @ 12992' | TRS: EDC | *** ON OF TOOL DEPTH @ 12992' | PERFORATE THE A/M INTERVALS. | NARMER-1X
RIG SUPT: AHMED FOUAD |  | M.G'S: EXPRO | ** DIESEL STOCK ENOUGH FOR 7 DAYS. |  | SRPR
012-00614093 |  | C.T: ?? | OPEN PERF: SAFA (15,055'-15,077') 22 FT & (15,090-15,120) 30 FT. | ***BHA: (6" MTB+ BIT SUB + 1 X 4 3/4" D/C'S + 7" SCRAPER +5 X 4 3/4" D/C'S
PMP: 3722 | PBTD @ 15,318' |  | PLAN PERF. & RE-PERF. : SAFA (15,055-15,077) 22 ft & (15,083-15,135) 52 ft | X/O + 141 JT 3 1/2 EUE + X/O + 41 JT D/P+POLISH /DRESS MILL+X/O+D/P
EDC - 91 | TAYIM-N04 | OIL | ALMANS. S/L POOH W/ 2.34" M.S.V. FROM 2 7/8" P.S.N, POOH T/ SURF. & R/D ALL. | N/D 11" X 5 K PSI BOP'S STACK W/ 2 7/8'' PIPE RAM.
500 HP, 5K PSI BOP, 240 KLB | R/C | 9 5/8" CSG | M/U 11'' X 3 1/2" - 5K PSI CIW TBG. HGR., SET SAME IN T.H.S. W/ 1-WAY | L/D TBG HGR, N/U THE KTH FLANGE ON TYPE HANGER FLANGE.
POWER SWIVEL/CAMP/13.2'. | EXPECTED PROD. RATE =300 BOPD | 7" LINER | B.P.V. & TIGHTENED L.D.S. | SET 7" TBG ANCHOR CATCHER WITH 22 KLB O.P. | TAYIM-N01(ST)
|  |  |  | PICK UP & INSTALL S. ROD BOP & PUMPING TEE T/ SECURE THE WELL | R/C ON AEB-3C
MOH. ABDEL HAMEED |  | AEB-3C RES. PRSS. = 5740 PSI |  | FLUSH SROD COMPLETION W/ ONE TBG CAPACITY OF SYSTEM WATER | TAYIM-W01
MOH. SAID ABDEL KADER | 7" T.O.L (CORRELATED) @ 8,948' | AEB-3C RES. TEMP. = 280 DEG |  | M/U & RIH W/ 25-150-RHBM-20-6-2-2 DHSRP EQUIPPED W/ SAND SCREEN | TBG & PR (Cr TBG)
010-04666721 (C.M) | 7" CSG @ 14,997' (29# ,N-80, BTC) | KHARITA |  | & DIP TUBE | TAYIM-N02
012-71474140 (C.M) |  |  |  | ** FLUSH SEATING NIPPLE W/ 10 BBL SYSTEM WATER BEFORE SETTING DHSRP | R/C to AEB-3D
012-21118788 (T.P) |  | S/L : IOD |  | P/T THE TBG TO 500 PSI (AGAINST DHSRP), IF OK, BLEED OFF PRESSURE | TAYIM-W06
| 7" B.P. @ 13400' | TRS: EDC |  | T/ 200 PSI, THEN START RECIPROCATIONG PUMP WHILE CLOSING THE 3" | R/W & IPI
RIG SUPT: MAHMOUD ESMAT |  | COMP: HALL |  | BALL VALVE T/ 500 PSI. | FGHR-S04
012-01544463 |  | TCP: ALMAN. | *** DIESEL STOCK ENOUGH FOR 7 DAYS | LAST TEST DATA: | R/C
V-SAT:980-0155 |  | E/L: SAPESCO | ** ISOL. PERF.: AEB-3D (13,480-13,493) 13' | CHOKE WHP SEP.P BFPD BOPD F.GAS RATE B.S. & W. | Retrieve the existing WI string, isolate SAFA reservoir, perforate AEB-U06 and complete the well with WI string.
PMP: 3713 | PBTD (CORRELATED) @ 14,830' | F.WTR - GAWEESH | ** OPEN PERF.: AEB-3C (13,109-13,120) 11' | OP 60 27 184 60 NILL 67%
EDC - 95 | PTAH-30 | OIL | R/D = 50% R/M = 0 % R/U = 0 % | CONT R/D & R/M
5K BOP, 500 HP, 240 KLB. | TBG & PR | 7" CSG | ** SECURED THE WELL & RELEASED THE RIG F/PTAH-47 @1:00 AM
POWER SWIVEL / (F.UNIT) |  | LBAH PRESS.: 2,900 PSI | ON 22-08-2023. |  | PTAH-30
AHMED SABRY | EST. PROD. RATE = 200 BOPD |  | ** MOVE DISTANCE F/ PTAH-47 T/ PTAH-30 = 8 KM DESERT ROAD | NEED WELL PROGRAM | ESPR
|  | 9.2 PPG KHRT WTR | ** R/M PERMIT & ROUTE SURVEY APPROVED & SIGNED. |  | PTAH-06
012-26749111 (C.M) | 9 5/8'' CSG @ 2,730 FT | TRS : | ** PETROLIFT T/ CHECK & APPROVE ALL LASHINGS & MOVE TRUCK |  | TBG & PR (High Norm)
010-16416661(C.M) | 7'' CSG @ 12,800 FT | E/L : | LOADS BEFORE START MOVE.
VHF Radio channel 8 |  | S/L: | ** EXPECTED T/CLEAR PTAH-47 WH AREA ON 22/AUG/2023 @ 1:00 PM.
01271469246 (T.P) | MAX INC. 13.1 @ 12676' | H2S: | ** DIESEL STOCK @ RIG RELEASE = 34.1 BBL (5426 LTR)
V.SAT: 980-0161 | MAX D.L.S 1.85 / 100' @ 12,486' | INSPECTION:
RIG SUPT: AHMED MAGDY |  | FILTER : RIG
1207777038 |  | TCP: AL- | *** DIESEL STOCK ENOUGH FOR 6 DAYS.
|  | DHT: | OPEN PERF. : AEB-3E (11,378'-11,400') 22', AEB-3G (11,488'-11,500') 12'
PMP: 3757 | PBTD @ 11,694' ( CORR.) | F.WTR - GAWEESH | ISOL. : AEB-5B (11,840'-11,866') 26', (11,876'-11,900') 24', (11,918'-11,930') 12'
MOHAMED ABDALLA | CHARLIE KENEEDY | A/G: HANY ALLAM TELE : 01272370011 - 01275111157 |  | WO Technical Support : WALID SALLAM | Khaled Ghanaym
TELE: 01000031117 / 01226762111 | TELE: 01201112590 | A/G: VERNON 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01285026752 - 01024478008 | 01275111158
KHALDA PETROLEUM CO.
|  |  | AM WORKOVER REPORT | TEAM-4-WO | 2023-09-02 15:29
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS
EDC - 90 | KARANIS-05 | OIL | SWEPT HOLE W/40 BBL's H.V.P & DISPLACED SAME W/ 700 BBL's | CON'T POOH W/ 7" CLEANING ASSY. ON 3 1/2" D/P'S T/ SURF., & STD BK ON DRK.
10K BOP, 750 HP, 280 KLB. | I/C (500-1000 BOPD) | 7" LINER | (9.5 PPG KHARITA WATER) TILL ALL SPACER , H.V.P OUT & HAD CLEAR WTR. | M/U & RIH WITH 7” SCRAPPER ASSY. ON SAME 3 ½” D/P’S TILL +/-9,500 FT,
KELLY / CAMP.(F.UNIT.) | PERFORATE/TEST AEB-01 INTERVALS (8,980-8,995) 15 FT |  | *** P.P: 900 PSI@ 4 BPM | SWEEP HOLE AND CHC WITH SYSTEM BRINE.
RIG ELEVATION : 20.2 FT | & (8,808-8,820) 12 FT AND COMPLETE THE WELL WITH SUITABLE PUMP STRING | 9.5 PPG KHARITA-NACL BRINE | R/D 4 1/4" RIG KELLY. | M/U & RIH W/ PERFORATION & TEST STRING (SHOT & PULL) ON 3 ½” VA SUPERIOR TBG (COND. A) TO PERFORATE AEB-01 RESERVOIR
|  |  | H.P.J.S.M & POOH W/ 7" CLEANING ASSY. ON 3 1/2" D/P'S T/ 7,900, & STD BK ON DRK. | INTERVALS (8,980-8,995) 15 FT & (8,808-8,820) 12 FT.
AHMED MAGDY |  | COLD CUTTER: MIDCO | *** TOT.: (25/143 X 3 1/2" IF D/P'S STD'S) ABOVE BHA. | *** P/T STG WHILE RIH TO 3500 PSI AGAINST 2.75” FB-2 C.V
AHMED ABDELGHAFAR |  | WFD: POLISH/DRESS MILL | *** PUMPED METAL DISPLACMENT WHILE POOH | INSIDE 3 1/2” F-NIPPLE
012-71484448 (C.M) | 9 5/8” CSG (43.5#, N-80, BTC @ 8,803 ft) | TCP: HALL | *** RECORDED STATIC LOSSES = ZERO. | R/U E/L P.C.E. & RIH WITH 1 11/16” GR-CCL CORRELATION TOOL &
010-06664098 (C.M) | 7" LINER CSG SHOE (29 PPF, N-80, BTC) @ 15,147' | DHT: HALL | *** USED EDC POWER TONG WITH TWO SNUB LINES. | CORRELATE THE GUN DEPTH. SPACE OUT/IN TO HAVE THE GUN ON DEPTH.
02- 27063376 (C.M) | 8 1/2" HOLE TD @ 15,150'. | TRS:… |  | N/U KPC FLOW TREE AND P/T SAME WITH STRING TO 3,500 PSI | KARANIS-1X
0224062590(T.P) |  | S/L:… |  | AGAINST 2.75” FB-2 C.V, THEN RETRIEVE SAME. | P/R [13 % CR TBG]
012-21112148 (T.P) | T.O. 7"LINER @ 8,560 ft CORRELATED | E/L: SAP |  | SET THE 9 5/8" RTTS PKR & SOW TO PERFORATE THE A/M RESERVOIR INTERVALS. | TAREK-NE02
SUP. INT: AHMED MAGDY | PBTD L.C @ 15,066 ft |  |  | PRESSURE TEST ANNULUS SIDE TO 1,000 PSI TO CHECK PKR SEALING. | R/C Retrieve top part of completion, perforate/test (OPTION ACIDIZING) ALM-DOL
01207777038 |  |  |  | OPEN THE M.C.V., R/U N2 UNIT SURFACE LINES, P/T SAME AGAINST | and completion with suitable completion.
VHF RADIO (CHANNEL 8) |  |  |  | FLOW TREE, DISPLACE THE HOLE WITH N2 TILL +/-500 FT ABOVE M.C.V.
|  |  | ** DIESEL STOCK ENOUGH FOR 6 DAYS. | CLOSE M.C.V AND PRESSURE TEST ANNULUS TO 1000 PSI TO
VSAT : 980 - 0161 |  |  | SQUEEZED PUNCHES :INTERVALS (8820-8825) 5 FT & (9300-9305) 5 FT | CONFIRM ITS SEALING AND HOLD +/- 500 PSI IN THE ANNULUS
PMP: 3759 |  | F.WTR - GAWESH | PLAN . : AEB-1 RESERVOIR INTERVALS (8,980-8,995) 15 FT & (8,808-8,820) 12 FT | DURING PERFORATION.
ECDC-9 | SIWA-V1X (ST) | OIL | FIN'D TIGHTENED L.D.S | N/U 3 1/8" - 5K PSI CIW X-MAS TREE & P/T SAME T/ 500 - 3500 PSI (BODY TEST)
| TBG & PR (115 BOPD) | 9 5/8" CSG. | INSTALLED 1-WAY B.P.V , N/D FLOW LINE, BELL NIPPLE & 11" - 5K PSI BOP STACK. | CONNECT SURF. PIG TAIL CABLE, START UP PUMP T/LINED PIT & CHECK PERFORMANCE & RIGHT DIRECTION.
750 HP / KELLEY / RKB: 23' | 13 3/8" CSG @ 1895' ( 68 #, K-55, BTC) | 7" LINER & 5" LINER | N/U 11" X 3 1/8" - 5K CIW E.S.A SPOOL & P/T SAME T/ 500 - 3000 PSI (CAVITY TEST)…………. IN PROGRESS. | CONNECTED PRODUCTION LINE.
5K PSI BOP / CAMP/ 400 KLB | 9 5/8" CSG @ 12300' ( 43.5,47 #, N-80, BTC) | AVG. L-SAFA RES.PRESS. 6,300 PSI |  | RIG MOVE TO SIWA-R-NW02. | SIWA R-NW02
ISLAM ABDEL RAHAN |  | AVG. L-SAFA RES. TEMP. 270° F |  |  | R/C
MOHAMED GEHAD | 7" T.O.LINER @ 11761' |  |  |  | Retrieve ESP completion, add perforation and complete the well with single WI STG.
010-98983763 (C.M) | 5" T.O.L @ 13374'. | 9.1 PPG FILT. KHRT. WTR. |  |  | SIWA 3-R02
012-26348631 (C.M) | 5" L.C @ 14618' | FILTER UNIT: MI |  |  | R/C AS WSW
010-99590109 (T.P) |  | E/L XXXXX |  |  | SIWA 2-L07
012-72520145 (T.P) | MAX. INCLINATION 7.81 DEG @ 14531' | H2S: DREXEL |  |  | TBG & PR
S/L: XXX
TCP: XXX
RIG SUPT: ALI AMEEN | MAX. DOG LEG 2.79 DEG @ 14150'
010-99164227 | MAX. INCLINATION 7.81 DEG @ 14531' | [5 empty] | Attia AbdElaziz
Hany Allam
|  | F.WTR - SINAI CO. | DIESEL STICK ENOGH FOR 10 DAYS |  |  |  | Ahmed Barkat
PMP: 3738 |  | D.WTR - ELHAMY CO. | ** OPEN PERF.: LSAFA (14,272' - 14,292') 20' &(14,250'-14,287') 37' |  |  |  | Mohsen Ashour
EDC - 32 | KAR-SW27 | OIL | N/D DSA & 11"-5K ANNULAR BOP. | CONNECTED SURFACE PIGTAIL T/ESP ELECTRIC PENETRATOR. |  |  | Khaled Ghanaym
| (ESPR) ( 90 BOPD) |  | N/U (11" X 3 1/8")-3K PSI FMC E.S.A & P/T SAME T/(300-2000) PSI HOLD,OK. | START-UP THE PUMP AND FOLLOW UP THE WELL TILL GET ACCEPTED RATE. |  |  | 01275111158
5K BOP, 350 HP, 100 KLB. | 30" COND @ 115 FT-ORKB | 13 3/8" CSG | N/U 3 1/8"-3K FMC X-MASS TREE&P/T SAME T/2000 PSI HOLD,OK (BODY TEST) | RETRIEVE C.V/V |  |  | Belal Sallouma
HAGAG AWAD | 13 3/8" CSG @ 1980 FT-ORKB (68 PPF, K55, BTC) | 9 5/8" CSG |  | SECURE THE WELL AND RELEASE THE RIG. | YOM-02 |  | 01279539944
0227063623 - 5032 (C.M.) | 9 5/8" CSG @ 5467 FT-ORKB (43.5 PPF, L-80, BTC) | 7'' LINER |  |  | ESPR (100 BOPD) PRODUCTION REACTIVATION |  | Amr AbdElaziz
01203311317 (C.M.) | 7" Liner SHOE@ 8070 FT-ORKB (29 PPF, L-80, BTC) | NACL BRAINE WTR 8.5 PPG |  |  | ASA-55 |  | Mohamed Abd Elsalam
0224062532 (T.P) |  | AVG. RES. PRESS. XXX PSI |  |  | SRPR (40 BOPD) |  | Walid Sallam
RIG SUPT: AHMED FOUAD | T.O.F. @ 7530FT-ORKB | S/L: IOD |  |  | HAM-04 |  | Esam Eid
01200614093 | 7'' T.O.L@ 5177 FT-ORKB | ESP: BORETS |  |  | SRPR (50 BOPD) |  | Dan Mullinus
| 7" B. PLUG @ 7540 FT -ORKB | H2S : DREXEL |  |  |  |  | 01277612182
| MAX. INC. 21.1⁰ @6478' M.D. | LAST H2S READING 140 PPM | ** DIESEL STOCK ENOUGH FOR 05 DAYS |  |  |  | Stan Jackson
| MAX. D.L. 3.96⁰/100 FT@ 5,821 | FRESH WTR: AL-EMAN | OPEN PERF: L.A/R "G" (7142'-7150') 8 FT, (7160'-7168') 8 FT & (7196'-7206') 10 FT |  |  |  | Charlie Kennedy
|  |  | U-BAH (7348'-7349') 1 FT, (7353'-7354') 1 FT, (7420'-7421') 1 FT |  |  |  | Abdelmageed Ahmed
|  |  | (7427'-7428') 1 FT, (7434'-7436') 2 FT, (7346'-7356') 10 FT&(7420'-7440') 20 FT |  |  |  | Omar Yahia
HATEM ZEDAN | CHARLIE KENEEDY | A/G: AHMED BARKAT TELE : 01272370011 - 01275111157 |  | WO Technical Support : WALID SALLAM | Khaled Ghanaym |  | Abd-Alah Taha
TELE: 01013334559 / 01272363263 | TELE: 01201112590 | A/G: ERIK 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01285026752 - 01024478008 | 01275111158 |  | Ahmed Elbanauosy
|  |  | KHALDA PETROLEUM CO. |  |  |  | Ahmed AbdElaaty
|  |  | AM WORKOVER REPORT | TEAM-4-WO | 2023-09-02 15:29 |  | Vernon
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS |  | Abd-Allah Taha
EDC - 83 | WD-33-15-11 | OIL | MANS. E/L RECORDED UP CBL-VDL-GR-CCL FOR 7" LINER & 9 5/8" CSG | P/T CSG TO 1500 PSI ON STAGES. HOWEVER, OPEN B.H TO CHECK RETURN .
500 HP, 5K PSI BOP , 240 KLB. | I/C ( BASED ON TEST) perforate/test ARC reservoir interval | 9 5/8" CSG | F/6770' T/ 700' (T.O.C.) POOH, R/D ALL | M/U & RIH W/ PERFORATION-TEST STRING (S& P) ON 3 ½” SUPERIOR TBG | SWQ-10
P. SWIVEL / FLY CAMP | (5,134-5,172) 38 ft and complete the well with suitable pump string. | 7" LINER | *** LOG SHOWED GOOD CMT AROUND PLAN PERF'S INTERVALS. | (COND. A) TO PERFORATE ARC RESERVOIR INTERVAL (5134-5172) 38 FT | TBG & PR===Continue
RIG ELEVATION.: 11'. |  | 9 PPG NACL | *** CORRELATION REFERENCE: BAKER HUGHES OPEN HOLE LOG | R/U E/L P.C.E. & RIH WITH 1 11/16” GR-CCL CORRELATION TOOL
|  | TRS: SDF | DATED: 05-AUG-2023 | CORRELATE THE GUN DEPTH. SPACE OUT/IN TO HAVE THE GUN ON DEPTH.
KARIM ABDEL AZIM |  | E/L : EL-MANSOORI | *** WHILE RIH HAD TAG @ 6770 FT | N/U KPC FLOW TREE AND P/T SAME W/ STRG TO 2000 PSI AGAINST 2.75”
| ARC RES PRESS: +/- 800PSI |  | *** T.O.C BEHIND 9 5/8" CSG @ 700' (CORRELATED). | FB-2 C.V, THEN RETRIEVE SAME. | WON-X-30
01275238785 (C.M) | ARC RES TEMP: +/- 160 ° F | TCP: SAPESCO | *** 7" TOP OF LINER @ 3631' (CORRELATED). | SET THE RTTS PKR & SOW TO PERFORATE THE A/M RESERVOIR INTERVAL. | ESPR
01275238785 (C.M) |  | DHT: HALL |  | P/T ANNULUS SIDE TO 1,000 PSI TO CHECK PKR SEALING.
0-227063269 | 13 3/8" CSG (68#, K-55 , BTC) @ 1482' | S/L: |  | HOOK UP TESTING PACKAGE EQUIPMENT LINES TO FLOW TREE P/T SAME
V-SAT:980-0362 | 9 5/8"INTER. CSG (43.5#,N-80,BTC) @ 4060' |  |  | R/U W/L LUBRICATOR; LOAD THE FIRING BAR; THEN DROP SAME TO
01205552275 (T.P) | 7'' LINER SHOE @ 7,030' |  |  | PERFORATE THE INTERESTED RESERVOIR INTERVAL.
RIG SUPT: AHMED FOUAD | T.O. 7" LINER (29#,N-80,BTC) @ 3628.2' | ARC RES PRESS: +/- 800PSI | DIESEL ENOUGH FOR 10 DAYS
01200614093 | (PBTD) 6951' | ARC RES TEMP: +/- 160 ° F | PLAN PERF.: ARC (5,134-5,172) 38 ft
EDC - 85 | ERZK-21 | OIL | POOH W/ESP COMP. ASSY (GN-1600N) ON 3 1/2" EUE TBG FLAT T/227 FT. | RIH W/ ESP ON “COND. A” 3 ½” SUPERIOR TBG. TILL PUMP INTAKE 5450 FT.
500 HP, 5K PSI BOP, 240 KLB |  | 9-5/8" CSG | L/D ESP BHA. ASSY AS FOLLOWING: | TEST THE STRING @ MIDWAY & FINAL WAY TO 2,500 PSI
POWER SWIVEL/CAMP/ 12.5' |  |  | *** ESP ASSY: 3 X 3 1/2" EUE TBG + 3 1/2" R-NIPPLE W/2.75" RB-2 C.V | START PUMP TO FLARE, CONFIRM PERFORMANCE, MOTOR PHASE ROTATION.
| ESP UPGRADE | KHARITA WATER (9.1 PPG) | + 3 1/2" EUE F.COUPLING + 1 X 3 1/2" EUE TBG JT+ 3 1/2"SSD"GL" 2.81 | SECURE THE WELL AND RELEASE THE RIG. | WRZK-59
AHMED GAMIL |  | E/L: SAPESCO | KPC ESP CREW SERVICE & L/D (GN-1600N) ESP ….. IN PROGRESS |  | R/C
S/L : IOD.
0227063297 (C.M) Land line |  | FRESH WTR : GAWISH |  |  | WD-33-15-12
01282130364 (C.M) |  | SYS. WTR. -ELHAMY |  |  | I/C
02-227062585(T.P) |  | TRS : EDC
RIG SUPT: MAHMOUD ESMAT |  |  |  |  | OAKHIL-W1X
| PBTD @ 6,195' (F.C) | ARG & BAH +/- 1,850 PSI. | ** DIESEL STOCK ENOUGH FOR 7 DAYS. |  | ESP DOWNGRADE
012-01544463 |  |  | ** OPEN PERF: ARG (5,646'-5,666')20',(5775'-5790')15',(5818'-5838')20'
** OPEN PERF: UBAH :,(5848'-5850')2',(5950'-5965')15',(5990'-6005')15',
PMP : 6602 |  |  | (6080'-6090')10',(6100'-6108')8',(6138'-6178') 40'
EDC - 88 | BERENICE-33 | OIL | R/D: 100 % R/M: ZERO % R/U: ZERO% | RIG MOME & CHECK RIG FOR ACCEPTANCE
500 HP / POWER SWIVEL | I/C | 7'' CSG | ** RIG RELEASED FROM PTAH-12 @ 4:00 PM ON 21-AUG-2023 | N/D 3 ⅛" X 5K PSI X-MASS TREE & N/U BOP & P/T SAME.
11"- 5K PSI BOP , 240 KLB'S | Perforate/test AEB-3E reservoir and complete well with ESP no 13 % Cr TBG. |  | ** MOVE DISTANCE F/ PTAH-12 T/ BERENICE-33 = 14 KM DESSERT ROAD | R/U E/L, M/U & RIH WITH 5.8” GR-JB-CCL TILL PBTD, POOH.
RIG ELEVATION.: 14.7'. | 9 5/8" CSG @ 4150 FT (94# , K-55 , BTC) |  | ** R/M PERMIT & ROUTE SURVEY APPROVED & SIGNED. | M/U & RIH W/CBL-VDL-GR-CCL LOG TILL PBTD AND RECORD SAME | PTAH-09
|  | 9.2 KHARITA WTR | ** PETROLIFT REP. CHECKED ALL LASHINGS & MOVE TRUCK LOADS | FOR THE 7” CASING TILL T.O.C., POOH TO SURFACE. | TBG & PR
AMEER ELSAYED |  | AVG RES. PRESS | BEFORE RIG MOVE. | PRESSURE TEST CSG TO 2,000 PSI ON STAGES.
| 7" CSG @ 13155 FT (29 & 26 PPF,N-80, BTC) |  | ** DIESEL STOCK @ RIG RELEASE = 67 BBL'S. | M/U & RIH W/ HALL. PERF./TEST ASSY. STRG (S & P) ON 2 7/8” EUE TBG ( A) | BERENICE-11
01221729475 (c.m) |  |  | *** PERFORMED PRE-MOVE SAFETY MEETING BEFORE R/M | TO PERFORATE AEB-3D/3E RESERVOIR INTERVAL (11,302-11,327) 25' | TBG & PR====OR RES. RECOMM
01006663917 (c.m) |  |  |  | & (11,268-11,290) 22
PMP: 3720 | P.B.T.D. (F.COLLAR) @ 13077 FT | FILTER : RIG
01205552208 (T.P). |  | S/L: IOD
VHF RADIO (CHANNEL 8) |  | TRS: SAP. | ** DIESEL STOCK ENOUGH FOR 10 DAYS.
RIG SUPT: AHMED MAGDY |  |  | ** PLAN PERF: AEB- 3D/ 3E (11,302-11,327) 25', (11,268-11,290) 22
01207777038 |  | F.WTR - GAWEESH
EDC - 89 | NRQ-9X | OIL | BLEED-OFF PART OF WHN2P T/ 1200 PSI TO ACHIEVE 1500 PSI U.B. | IOD S/L RIH W/2.23" G.C. AS DUMMY RUN TILL TAGGED 2 7/8"
500 HP, 5K PSI BOP, 240 KLB | R/C (700-1500 BOPD) | 7" CSG | R/U IOD S/L LUBRICATOR & P/T SAME T/ 1000 PSI, HOLD, OK. | R-NIPPLE @ 7887'(S/L DEPTH), POOH & L/D TOOL.
POWER SWIVEL/CAMP/ 12.5' | RETRIEVE ESP COMP., RE-PERF. & ADD PERF. | 9 PPG BRINE [4 % KCL + NACL] | HPJSM, LOAD & DROP THE FIRING BAR TO PERF. LBAH RES. INTERVALS | IOD S/L RIH W/BOMB HANGER W/ 2 X 10K EXPRO M.G.'S, SET SAME
AHMED EL DASH | THROUGH LBAH, PROD. TEST (S&P) AND | H2S : DREXEL | (8,010-8,030) 20'' & (8,047-8,054) 7'' | INTO 2 7/8” R-NIPPLE, POOH T/ SURF & R/D S/L LUBRICATOR. | NRQ-255-18
| COMPLETE WELL W/ SUITABLE PUMP STRING. | S/L : IOD | *** NO SOUND INDICATION | *** PROGRAM MG'S TO READ EVERY 5 & 10 SEC | R/C Retrieve ESP completion, drill out B.P isolating UBAH reservoir and complete
01050025319(C.M) |  | ESP : KPC | *** WHP INCREASE 400 PSI WITHIN 15 MIN | R/U 1.5'' SLB C.T."CAT-03" (SINGLE RAM BOP, FLOW TEE,QUAD BOP, STRIPPER | the well with suitable pump.
01206111732 (C.M) |  | E/L : SAP. | *** ANNULUS PRES.DIDNT CHANGE IN 15 MINS | & INJECTOR HEAD) & SURFACE LINES .
01221112152 (T.P) |  | TCP : SAP. | OPENED THE WELL T/ FLARE PIT FOR 0.5 HR, HAD NO RETURN, SI SAME | HOOK UP ALMANSOORI TEST PACKAGE TO SLB C.T. TEE-SUB & P/T SAME
RIG SUPT: MAHMOUD ESMAT |  | SCRAP. : W.FORD | IOD S/L RIH W/ 1.8" JDC PULLING TOOL T/ RETRIEVE 1.5" FRINGING | RIH W/ SLB 1.5" C.T T/ 2000 FT & START PUMP N2 W/ 500 SCF/MIN TILL 7500'
012-01544463 | 7" CSG (26PPF, N-80,BTC)@8476' | DHT: HALL. | BAR IN ,RETRIIVED SAME ,FOUND GOOD MARK OF FIRING . | (355' ABOVE PERF. JT)
ITN:75297 | PBTD @ 8,289' (CORR.) | C.T.: XXX |  | DIVERTED THE FLOW THRU AL-MAN TMU & TEST SAME LIQUID T/PROD. & GAS
V.SAT: 980-0901 / 77-0901 |  | M.G: EXPRO | ** DIESEL STOCK ENOUGH FOR 12 DAYS. | TO FLARE PIT
01207777038 |  |  | OPEN PERF. :LBAH (8020'-8030') 10'
PMP :6603 |  | FRESH WTR: GAWESH | PLAN PERF.: LBAH (8010'-8030') 20' & (8,047-8,054) 7'.
HATEM ZEDAN | CHARLIE KENEEDY | A/G: AHMED BARKAT TELE : 01272370011 - 01275111157 |  | WO Technical Support : WALID SALLAM | Khaled Ghanaym
TELE: 01013334559 / 01272363263 | TELE: 01201112590 | A/G: ERIK 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01285026752 - 01024478008 | 01275111158
KHALDA PETROLEUM CO.
|  |  | AM WORKOVER REPORT | TEAM-4-WO | 2023-09-02 15:29
RIG | WELL | PHASE | OPERATION | PLAN | REMARKS
EDC - 92 | NU-04 | WIW | R/U IOD. S/L LUBRICATOR & P/T SAME T/1000 PSI …. HOLD OK | S/L RIH W/ MOD.C.V & SET SAME IN 3 ½” VAM TOP X-NIPPLE AT 7,844 FT.
500 HP, 5K PSI BOP , 240 KLB. | TBG & PR. | 7" CSG | IOD S/L RIH W/ 2.86" G.C. TILL TAG 3 1/2" SSD ''XD'' TOP PROFILE | S/L RIH W/SHIFTING TOOL TO OPEN 3 ½” VAM TOP SSD “XD” AT 7,802 FT,
P. SWIVEL / FLY CAMP | R/C (CONVERSION WIW) isolate DAHAB reservoir, perforate |  | AT 7821 FT (S/L DEPTH) , POOH T/ SURF. & L/D TOOL. | DISPLACE HOLE TO PROD. LINE USING FILTRATED KHARITA WATER.
RIG ELEVATION.: 11.5'. | AEB-3D reservoir & test its injectivity (option Stimulation), then complete well | AEB-3D RES. PRESS.: are +/-1000 PSI | IOD S/L RIH W/ 2.75 " MODIFIED C.V & SET SAME IN 3 ½” VAM TOP | N/D X-MASS TREE, N/U BOP AND P/T SAME.
| with WI String. | AEB-3D RES.TEMP.:275 Deg. F. | X-NIPPLE …. IN PROGRESS. | UNSET TBG HGR, POOH W/ THE ESP STRG ON 3 ½” JFE-BEAR TBG&L/D ALL.
MAHMOUD ADEL ZAKY |  |  |  | CONDUCT INJECT TEST FOR DAHAB INT.L UP T/2500 PSI MAX. SURFACE PRESS.
KEROLES SOBHY |  | 9.2 FILT. KHART WTR |  | IN CASE OF HIGH INJECTIVITY, PROCEED TO CONDUCT RETAINER CMT
| 9 5/8" CSG (43.5#,N-80 )@ 4730' | FILTER : RIG FILTER |  | JOB, OTHERWISE CONSIDER SPOT CMT PLUG AND CONDUCT BLOCK SQUEEZE | MIHOS-1X
012-77706931 (C.M) | LAST TAG: SAP. E/L RIH E/ 6" GR-JB | TRS : PREMIER |  | M/U & RIH WITH 7” CMT RETAINER ON MECHANICAL SETTING TOOL ON | ESPR
010-00194097 (C.M) | ON CCL TILL TAGGED OBST @ 11550' | WL: IOD |  | 3 ½” D/P’S, SPACE IN/OUT AND SET THE RETAINER AT +/-9,000 FT.
0224062592 (T.P) | 7'' F.COLLAR @ 11816' ORKB | CMT: SCHL |  | RELEASE M.S.T, CIRCULATE HOLE, THEN STING INTO RETAINER AND
01221112166 (T.P) | 7" CSG ( 304 JTS ) @ 11900 FT |  |  | OPEN THE SQUEEZE VALVE.
RIG SUPT: AHMED ashor
012-00614093 |  |  | ** DIESEL STOCK ENOUGH FOR 5 DAYS.
VHF RADIO (CHANNEL 8) |  |  | OPENED PERF : DAHAB (9060'-9084') 24'
V.SAT: N/A |  |  | PLAN PERF:AEB-3D (10,744-10,782) 38 '
PMP: 3721 |  | F.WTR - GAWESH
EDC - 93 | WKAL-A14 | OIL | REPLACED THE CABLE REEL (WRAPPED BY 10,000' R-CABLE) BY AN EMPTY REEL, AS PER ESP TEAM REQUEST | POOH W/BORETS 400-1050 ESP BHA ASSEMBLY
500 HP, 5K PSI BOP, 240 KLB | TBG & PR (ESP PKR) | 7" CSG | CONT. POOH W/ BORETS 400-1050 ESP BHA ASSEMBLY (BELOW 7" RDH PKR) T/ 122' & L/D SAME. | SAP E/L RIH WITH 5.8” GR-JB-GR-CCL TILL THE PLANNED B.P DEPTH
KELLY/CAMP/ 17'. | (140 BOPD) |  | BHA: (3 1/2" EUE FLOW COUPLING) + (3 1/2" EUE SSD XD-TYPE 2.81") + 2*(3 1/2" EUE TBG JT BVLD) + (X-OVER) + (2 7/8" TBG JT) + (7" RDH PKR) | E/L RIH WITH 7" B. PLUG ,SET SAME @ +/-10,800 FT, TO TEMPORARY
|  |  | + (2 7/8" EUE PUP JT 5.8') + 12 *(2 7/8" EUE TBG JT BVLD) + (2 7/8" FLOW COUPLING) + (2 7/8" R-NIPPLE 2.25") + (2 7/8" EUE TBG JT FLAT) | ISOLATE AEB-3C-7 & BASE INTERVALS, POOH.
MOH MAGDY |  |  | *** NO CABLE BANDS LOST IN WELL BORE | E/L RIH WITH CMT BAILER AND CAP B.P WITH 10 FT CMT. POOH & R/D E/L
|  | FILTRATED KHARITA WATER | ***BORETS ESP TEAM WITNESS POOH W/7"RDH PKR, CHECKED THE LOWER & UPPER SPLICE TO THE PKR | M/U & RIH WITH 7” RTTS PKR ON 3 ½” D/P’S, SET PKR @ +/-8900 FT | BERENICE-18
| DEVIATED WELL | RES. PRESS: 2400 PSI | *** FOUND SHORTING SPOT IN THE RKR PENETRATOR CABLE ( AS PER BORETS TEAM INTIAL INVESTIGATION) | *** P/T ANNULUS ON STAGES TO 1000 PSI AGAINST SQUEEZED ALM-DOL | R/C
01202543018 (C.M) | MAX. INC., 47.09˚ @ 9,940' |  | POOH W/ W/ ESP ASSEMBLY T/ SURFACE & L/D ALL,,, IN PROGRESS. | ***CONDUCT INJ. TEST AGAINST AEB-3C PAY-01 ON STAGES UP TO 2000 PSI | Retrieve ESP completion, isolate AEB-3D BTM, perforate/Frac AEB-3D Top, perforate (option Frac) AEB-3C, then complete the well with WI STG.
01033345012 (C.M) | MAX. DOG LEG 3.39 ˚/100 @ 9186' | EXPECTED OIL RATE 140 BOPD | *** D.H.SENSOR + 175 HP MOTOR + 2 X SEAL + PUMP INTAKE + 4 X 400-1050, TOTAL 495 STAGES (134 +124+ 124 +113) + 2 7/8'' DIS. HEAD | POOH WITH OPEN END TEST STRING ON 3 ½” D/P’S STD'S | WKAL-QAR-S1X
01200613123 (T.P) |  | 732 BFPD, 81 % W.C. | *** MAX. OD 5.5" (MTR SHROUD) | IN CASE OF HIGH INJECTIVITY, PROCEED TO CONDUCT RETAINER CMT | I/C
02-24062593 (T.P) |  |  |  | M/U & RIH WITH 7” CMT RETAINER ON HALL MST & 3 ½” D/P’S,
|  | S/L: IOD | ** DIESEL STOCK ENOUGH FOR 5 DAYS. | ABOVE AEB-3C PAY-01 | WKAL-A16
| 7" CSG (29 & 26 PPF, N-80, BTC) @ 13,500' | INSPECTION : ??? | OPEN PERF :AEB-3C (PAY-7) 46' ,(12414'-12422') 8', (12432'-12450') | OTHERWISE | R/C Retrieve ESP completion string, isolate AEB-3C Top, re-enter AEB-3C Base,
|  | E/L: SAP | 18', (12460'-12480') 20' AEB-3C (BASE PAY) 27' : OPEN (12707'-12716') 9' , | RIH WITH CMT STINGER AND CONDUCT BLOCK CMT SQUEEZE JOB
RIG SUPT: MAHMOUD ESMAT | PBTD: 7" B.P @ 12,850' CAP W/ 10 FT CMT | COMP: HALL | (12734'-12752') 18' ,AEB-3C PAY-1: ( 10,710' - 10,770') 60' | AGAINST AEB-3C PAY-01 INTERVAL | isolate AEB-3D reservoir, reperforte/test AEB-3C base and complete the well with suitable pump.
012-01544463 |  | FISH: TRI STATE | SQUEEZED ALM-DOL (8,804' - 8,830') 26'),
PMP: 3749 |  | TRS: ?? | ISOLATED BY B.P. & CMT AEB-3D ( 13,040' - 13,090') 50'
EDC-97 | MENES-33 | OIL | HALL. S/L RIH W/ 2 X 10K EXPRO M.G.'S, SET SAME IN 2 7/8" EUE R-NIPPLE | CON'T R/U C.T & N2 UNIT. FLUSH SAME W/ WATER TO FLARE & P/T SAME
5K BOP, 500 HP, 240 KLB. |  | 7" CSG | @ 10781' (S/L DEPTH), POOH & R/D S/L. | TO 3000 PSI AGAINST FLOW TREE S/V.
POWER SWIVEL / (F.UNIT.) | R/W & PR (400 BOPD) | FILT. KHARITA WATER | *** PROGRAMMED M.G.'S TO READ EVERY 5 & 10 SEC'S. | OPEN SWAB, WING (TO FLARE) & MASTER VALVES AND START RIH W/ C.T
|  | RES. PRESS= +/-4000 PSI | *** SIWHP = ZERO. | AS IT REACHED DEPTH ± 2,000 FT, START PUMPING N2 WITH 500 SCF/MIN | MENES-35
MOHAMED EL SHAWAAF |  | RES. TEMP.= +/- 280 F | R/U SAPESCO 1.5" C.T. CAT-3 & N2 PUMPS,….IN PROGRESS | AND CONTINUE RIH W/C.T, TILL DEPTH OF +/-10,000 FT. THEN, OPTIMIZE N2 | R/C
| 9 5/8" CSG ( 36#,K-55, BTC ) @ 2,790 ft |  |  | PUMPING RATE TO GET CONTINUOUS FLOW FROM THE FORMATION | Retrieve ESP completion string, isolate AEB-U01 reservoir, perforate/test
VHF RADIO (CHANNEL 8) |  |  |  | WITH MAX. DRAWDOWN | lower AEB reservoir (Option HFRAC) and completion with suitable
01011152087 (CM) |  | H2S = NIL |  | ONCE HAVING CONTINUOUS RETURN, DIVERT THE FLOW THROUGH THE | completion string.
01202542721(C.M) | P.B.T.D (CORRELATED) @ 11,952 FT | TRS :WF |  | TESTING EQUIPMENT & CONDUCT AN ACCURATE PRODUCTION TEST FOR | NU-28
01203377774 (T.P) |  | INSPEC. : SETCORE |  | +/-8 HR’S STABILIZED PERIOD. | I/C
RIG SUPT: AHMED MAGDY | F.C @ 11,967' | S/L : MANSORI |  | POOH W/C.T TO SURFACE & R/D ALL EQUIPMENT
1207777038 | 7" CSG ( 26, 29 #, N-80, BTC ) @ 12,049 | FILTER : RIG | ** DIESEL STOCK ENOUGH FOR 5 DAYS | R/U S/L & RIH TO RETRIEVE THE M.G’S
V-SAT:980-0951 |  |  | OPEN INTERVALS : AEB-3D BTM (10,898-10,912) 14 ft | R/U S/L LUBRICATOR & P/T SAME
PMP: 3707 |  | F.WTR - GAWEESH
HATEM ZEDAN | CHARLIE KENEEDY | A/G: AHMED BARKAT TELE : 01272370011 - 01275111157 |  | WO Technical Support : WALID SALLAM | Khaled Ghanaym
TELE: 01013334559 / 01272363263 | TELE: 01201112590 | A/G: ERIK 01283182726 | KALABSHA : BASEM 01222338275 | TEL: 01285026752 - 01024478008 | 01275111158