## S.B.Report
RIG | WELL
ST-5 | MRZK-207
1500 HP / TOP DRIVE | OIL
DEVELOPMENT
ISLAM EL-TAHER | DEVIATED
Military /MINE./EGPC/Env. Approval
YES/ OUT OF HI RESK AREA / VERBAL / IN PROGRESS
010-11150765 ( C.M ) | 9 5/8'' CSG, (36 #, K-55, BTC) @ 3597'
012-83909318 ( C.M ) | (± 30' INTO APOLL. FM)
7" CSG (26# , N-80, BTC) @ 7475'
01280141419 ( T.P ) | (± 257' INTO KHARITA FM .)
RIG SUPT: ISMAIL
012-27853358 | OFFSET WELLS:
MRZK-121 & MRZK-135
V-SAT : 980-0090
TD: 7,475'
EDC - 1 | SHADOW-E09
1500 HP / TDS / RKB: 30' | OIL
VERTICAL
MOHAMED ALAA | Militry /MINE./EGPC/Env. Approval
AHMED GAMAL | YES / OUT OF HIGH RISK AREA /
VERBAL / NO
20" CONDUCTOR @ 43'
01283909327 (C.M) | 13 3/8" SURF. CSG @ 3,360'
02-27063387(C.M) | (23' INTO APOL-A)
0224062501 (T.P) | 9 5/8" INTER CSG @ 8,800'
(79' INTO A/R-B)
7" LINER CSG @ 14,000'
RIG SUPT: AHMED SAMIR | OFFSET WELLS:
012-21112001 | SHADOW-E08X
V-SAT : 980-0991 | TD: 14000'
EDC - 11 | WKAN-N-7
1500 HP / TOP DRIVE | OIL
VERTICAL
HOSSAM ESSAM | Militry /MINE./EGPC/Env. Approval
HASSAN ABD ALHAMEED | YES/RISK ASSESS.DONE BY OPER. /
VERBAL / IN PROGRESS
01282130459 ( C.M ) | SURF. CSG (68 PPG K-55, BTC) @
01094226663 (C.M.) | 2950 (58' INTO APOLL.)
9 5/8" CSG (43.5 ,47 PPF, N-80, BTC) @ 8150'
01221112116 ( T.P ) | (88 FT INTO AEB-1)
7" LINER (29 PPF,HC, BTC) @ +/- 14500
RIG SUPT:ABDALLAH IBRAHIM
01212009267
V-SAT: 980-0931 | OFFSET WELLS:
PMP: 3724 | WKAN N-3 & WKAN N-1X
V-SAT: | T.D: 14,500'
AHMED A.ATY | STAN JACKSON
TELE: 01000031116 | TELE: 01277612182
RIG | WELL
EDC - 17 | BERENICE-28
1500 HP / TDS / RKB: 26' | OIL
BOP:13 5/8"-10K PSI WP | DEVIATED
RATED DRLG DEPTH: 15,000' | Militry /MINE./EGPC/Env. Approval
YES/ OUT OF HIGH RISK AREA /VERBAL / IN PROGRESS
SHADY MAHMOUD | 9 5/8'' CSG (36 #, K-55, BTC) @ 4100' (42 FT INTO A/R-A)
AHMED ABBAS
7" CSG @ 13000'
(± 52 ft INTO BASUR FM)
01205993336 (C.M)
010-62977790 (C.M)
012-02032070 (T.P)
02-24062615 (T.P) | OFFSET WELLS
BERENICE-24
RIG SUPT: MOSTAFA ZAYED
012-85777717 | D.WTR : RENPIT WELL
R/O WTR : SUMPETCO
PMP: 3706 | TD: 13000'
EDC - 40 | BRIDGE-1X
1500 HP / TDS / RKB: 25' | OIL
BOP:13 5/8"-10K PSI WP
RATED DRLG DEPTH :15,000' | Militry /MINE./EGPC/Env. Approval
YES/ OUT OF HIGH RISK AREA /VERBAL/ IN PROGRESS
MAHMOUD RAFFAT
AHMED ESSA
01004996490 ( C.M ) | 9 5/8" SURF. CSG, (36#, K-55 , BTC)
01285520932 (C.M.) | CP @ 2850 FT (67 FT INTO APOLL.)
7" CSG (26 PPF, N-80, BTC)
022-4062540(T.P) | C.P @ 7500 FT
RIG SUPT: MOSTAFA ZAYED
012-85777717
V-SAT: 980-0931 | TD: 7500'
EDC - 42 | CARNARVON -N-1X
2000 HP / TDS / RKB: 35' | GAS
BOP:13 5/8"-10K PSI WP | VERTICAL
RATED DRLG DEPTH :20,000' | Militry /MINE./EGPC/Env. Approval
YES/ YES / VERBAL / IN PROGRESS
ATEF A.AHGFAR
MOHMED IBRAHIM HASSEN | 13 3/8" SURF. CSG (68 PPG K-55,
BTC) @ +/-3060
012-82161786 (C.M) | (+/- 100' INTO APOLL.)
010-50025781(C.M)
VHF Radio channel 8
9 5/8" CSG (43.5 ,47 PPF, N-80,
02- 27063393 (C.M) | BTC) @ +/-9395'
02-24062542 (T.P) | (116 FT INTO AEB-1)
RIG SUPT: HAITHAM KHEDR
012-83339501 | 7" LINER (29 PPF,HC, BTC) @ +/-
15000'
VHF RADIO (CHANNEL 8)
V.SAT:980-0081
PMP: 3708 | TD.: 15,000'
AHMED A.ATY | STAN JACKSON
TELE: 01000031116 | TELE: 01277612182
RIG | WELL
EDC - 50 | NU - 34
1500 HP / TDS / RKB: 30' | OIL
BOP: 13 5/8"-10K PSI WP
RATED DRLG DEPTH: 15,000' | Military /MINE./EGPC/Env. Approval
YES/ OUT OF HIGH RISK AREA / VERBAL / IN PROG.
MOHMED NASSEM | 9 5/8" SURF. CSG, (36#, K-55 , BTC)
CP @ 2890 FT (75 FT INTO APOLL.)
7" CSG (29 & 26 PPF, N-80, BTC)
01212582613 (C.M) | C.P @ 12,100 FT
01004992493 (C.M)
VHF Radio channel 8
0224062550 (T.P)
RIG SUPT: HAITHAM KHEDR
012-83339501 | OFFSET WELLS:
NU-22 & NU-27
PMP: 3754
TD: 12100'
EDC - 57 | TAYIM-W8
2000 HP/ TDS / RKB: 30' | OIL
BOP:13 5/8"-10K PSI WP | DEVELOPMENT
RATED DRLG DEPTH 20,000' | DEVIATED
Militry /MINE./EGPC/Env. Approval
BELAL TAHA | YES/Out of High Risk Area / YES / YES
HAZEM ELKHALDY | 17 1/2" HOLE DRILLED TO 2445'
(50' INTO APOLLONIA )
13 3/8 SURF. CSG.STUCK @1850'
9 5/8" INTER CSG. @ 8928 FT
012-02542198 (C.M) | 7" PRODUCTION CSG @ 15871 FT
010-25616837 (C.M) | WTR WELL: +/- 25 KM AWAY F/ RIG
VHF Radio channel 8 | OFFSET WELLS:
01002191542 (T.P) | TAYIM-W3, 5 & 6
02-24062657 (T.P)
RIG SUPT: ELSAYED HAMZA
01228916988
WTR WELL: SIWA WELL
VHF RADIO (CHANNEL 8)
V-SAT:N/A
PMP: 3717 | TD.: 15,871'
AHMED A.ATY | STAN JACKSON
TELE: 01000031116 | TELE: 01277612182
RIG | WELL
EDC-58 | WD-33C-1X(JASPER-1X
2000 HP / TOP DRIVE | OIL
ANDREW | VERTICAL
SHERIF SOBHY | Militry /MINE./EGPC/Env. Approval
012-76403055 (C.M) | YES / OUT OF HIGH RISK AREA /
0100-0190891(C.M) | VERBAL / IN PROGRESS
02- 27063372 (C.M) | CONSTRUCTION CO: ELMANSOURA
VHF Radio channel 8 | 20" CONDUCTOR HUMMERED TO 43'
012-05552247 (T.P) | 13 3/8" SURF. CSG. @ +-2480 FT
0224062689(T.P) | (15' IN APPOL.)
9 5/8" INTERMEDIATE @ +/-10350 FT
RIG SUPT: ELSAYED HAMZA | 8-1/2'' HOLE @ 13,500 FT
01228916988 | 7" LINER @ 13,495 FT
OFFSET WELLS:
WD-33-15-7X, YOSEMITE-1X
WD-33-15-9
Thuraya : +882-1633331604 | >> EXPECTED FAULT @ 11330 '
V-SAT: 980-0821
ITN:75372
VHF RADIO (CHANNEL 8)
PMP: | TD: 13500'
EDC - 62 | PTAH-48
1200 HP / TOP DRIVE | OIL
VERTICAL
KAREEM MOSELHY | M. /MINE./EGPC/Env. Approval
YES / OUT OF HIGH RISK AREA/VERBAL / NO
01271466694 ( C.M ) | 20" COND (94#, K55, BTC)
01060422238 (C.M.)
9 5/8" SUR. CSG
01221112177 ( T.P ) | 36 PPF, K-55, BTC @ 2750'
024062657 (T.P) | (76' INTO APOLL. )
RIG SUPT: ABDALLAH IBRAHIM | OFFSET WELLS:
01212009267 | PTAH-35 ST
V-SAT:
PMP: 3748
TD: 6900'
AHMED A.ATY | STAN JACKSON
TELE: 01000031116 | TELE: 01277612182
RIG | WELL
ST - 7 | MRZK-210
1000 HP / TDS / RKB: 25' | OIL
MAX. PULL 495 KLB | DEVIATED
(HALL BUNDLE SERVICE) | Militry /MINE./EGPC/Env. Approval
AMR ATEF | YES /NO NEED/VERBAL/NO,IN PROGR
(SHALLOW GAS)
20" CONDUCTOR @ 15 FT PENT
9 5/8" CSG (36#,K-55, BTC) @ 3595'
01283909324 (C.M) | (+/- 14 FT INTO APOLL. FM)
01157602947 (C.M) | 7" PROD CSG(26# ,N-80,BTC) @ 6,600'
01003728086 (T.P) | LOCATION READY
RIG SUPT:HESHAM MASOWD | 2X 500 BBL EPIS STORAGE TANK.
012-85455600 | PLAN TO USE DIVERTER ON SURFACE
OFFSET WELL'S:
V.SAT: 980-0051 | NRQ- 13-2 & NRQ 5X
TD: 6,600'
EDC - 9 | BRAVO E-2
2000 HP / TDS / RKB: 31' | G/C
RATED DRLG DEPTH 20,000' | DEVIATED
Militry /MINE./EGPC/Env. Approval
MAHMOUD BAKRY | YES/ NO / VERBAL / NO
MARCORUOS
01226348568 (C.M) | 13 3/8"SURF. CSG. @ 3,010 FT
01060977764 (C.M) | (68' INTO APPOLONIA .)
VHF RADIO(CHANNEL8) | 9 5/8" INTER. CSG @ +/-9138 FT
01221112109 (T.P) | (± 30 FT INTO AEB-1 FM.)
02-24062509 (T.P) | 7" LINER CSG @ 15,200'
RIG SUPT:HAYTHAM KHEDR | 2 X 500 BBL EPIS STORAGE TANK.
012-83339501 | OFFSET WELL:
KARANIS-1X
PMP: 3742 | NEW TD: 15,200'
EDC - 48 | UMB-250
2000 HP / TDS / RKB: 35' | OIL
FATHY MEKKAWY | DEVIATED
ISLAM NAZER | Militry /MINE./EGPC/Env. Approval
YES/NO NEED /NO/ IN PROGRESS
012-78888624 (C.M)
01-024486001 (C.M) | 9-5/8" CSG (36#, K-55,BTC) @ 2815 FT
VHF RADIO(CHANNEL8) | (131 FT APOL. FM
01221112126 ( T.P ) | 7" PROD. CSG @ 12400'
0224062695 (T.P)
RIG SUPT:HAYTHAM KHEDR
012-83339501
OFFSET WELLS:
UMB 234 & UMB 244 X
V.SAT:980-0761
PMP: 3710 | TD: 12,400'
ISLAM DAHSHAN | STAN JACKSON
TELE: 01000031114-01271488855 | TELE: 01277612182
RIG | WELL
EDC - 49 | TUT-135
1500 HP / TDS / RKB: 25' | OIL
RATED DRLG DEPTH: 15,000' | DEVIATED
Military /MINE./EGPC/Env. Approval
HANY ELSAADANY | YES / NO NEED / VERBAL/ IN PROG.
MOH. SALEH
13 3/8"CSG (68#,K-55, BTC) @ 2718'
(77' INTO APPO.)
9 5/8" INTER. CSG(43.5#, K-55)@8,164'
0121 258 2659 (C.M) | ( 36 FT INTO AEB-1 FM.)
0100 499 2495 (C.M)
0224062549 (T.P) | 7"LINER CSG @ 12,900'
RIG SUPT:HAYTHAM KHEDR | OFFSET WELL:
012-83339501 | TUT 119 & TUT 52
WTR. SOURCE: SALAM WTR WELL
PMP: 3758 | TD: 12,900'
EDC - 53 | OAKHILL-1X
2000 HP / TDS / RKB: 30' | OIL.
TAREK MAHMOUD | DEVIATED
ISLAM THABET | Militry /MINE./EGPC/Env. Approval
YES/ NO NEED / VERBAL / IN PROG, (SHALLOW GAS)
02 27063295 (C.M) | 20" CONDUCTOR @ 37' PEN
012-02542678 (C.M) | 13 3/8" SURF. CSG @ 3,930'
010-11151924 (C.M) | (13 FT INTO APOLLONIA "A")
02-24062553 (T.P) | 9 5/8"CSG @ +/- 9,450'
.+882-1633331603 | (+/- 77' INTO A/R-B)
RIG SUPT: MOSTAFA ZAYED | 7"LINER @ +,-14,200'
012-00614568 | 3X 500 BBL EPIS STORAGE TANK.
OFFSET WELLS:
V.SAT: 980-0125 | OAKHILL-W1X, MAPLE-1X
PMP: | TD: 14,200'
EDC - 54 | FAGHUR S-8
2000 HP / TDS / RKB: 35' | GAS
VERTICAL
AMR MOHSEN | Militry/MINE CLEAR./EGPC /ENV. App.
KHALAF OMAR | YES/ NO NEED / VERBAL / IN PROG
012-27640856 (C.M) | 20" CONDUCTOR @ 40 FT
010-33345483(C.M) | 13 3/8" CSG (68#, K-55 , BTC) @ 2193'
VHF RADIO (CHANNEL8) | (14 FT INTO APOLLONIA "A")
0224062554(T.P) | 9 5/8" CSG (43.5#,N-80,BTC) @ 12,000'
0224062654(MAT) | (1034 FT INTO AEB-C)
7"LINER CSG (29#,N-80,BTC) @16,300'
RIG SUPT: MOSTAFA ZAYED
012-00614568 | OFFSET WELLS:
WTR. SOURCE: SIWA MWW-1X
PMP: 3736 | TD: 16,300'
ISLAM DAHSHAN | STAN JACKSON
TELE: 01000031114-01271488855 | TELE: 01277612182
RIG | WELL
EDC - 61 | NU-33 (SPUDDER WELL)
1200 HP/ TDS / RKB: 22' | WIW
BOP:13 5/8"-5K PSI WP | DEVIATED
MAX. PULL 440 KLB, 12000' | Militry /MINE./EGPC/Env. Approval
YES/ NO NEED /VERBAL /IN PROGRESS
MAHMOUD ABDEL RAHMAN
9 5/8" CSG (36#, K-55,BTC) @ 2935'
012-26759111 (C.M) | (76' INTO APOLLONIA)
010-63522269 (C.M) | 7" CSG(29&26 PPF, N-80,BTC)@12,318
VHF RADIO(CHANNEL8) | (CALL TD EARLY 182')
01221112188 (T.P)
02-24062661 (T.P)
RIG SUPT: ABDALLAH IBRAHIM | OFFSET WELL'S:
01212009267 | NU-23X & NU-27
PMP : 3711 | TD: 12,318'
EDC - 65 | WD 33-15-12
950 HP / TDS / RKB: 17' | OIL
5K PSI BOP / CAMP/ 360 KLB | DEVIATED
MAGED ELSHABRWY | Militry /MINE./EGPC/Env. Approval
MOH. SAAD BEHARY | YES/NO NEED/VERBAL/NO (SHALLOW GAS)
20" CONDUCTOR @ 52 FT
012-82051592 (C.M) | 13 3/8" CSG (68#, K-55 , BTC) @1472'
0227063241 (C.M) | (11' INTO APOLL.)
012-02034203 (T.P) | 9 5/8" CSG (43.5#,N-80,BTC) @ 4,250'
02-24062565 (T.P) | (56 FT INTO A/R-A)
7"LINER CSG (29#,N-80,BTC) @ 7,500'
PLAN TO USE DIVERTER ON SURFACE
RIG SUPT: MAHMOUD SHAFI | OFFSET WELL'S:
012-21110001 | WD33-15-4
VSAT : 980-0811 | TD: 7,500'
ISLAM DAHSHAN | STAN JACKSON
TELE: 01000031114-01271488855 | TELE: 01277612182
RIG | WELL
EDC - 75 | MRZK-208
1500 HP/ TDS / RKB: 30' | OIL
(HALL BUNDLE SERVICE) | DEVIATED
NAGM EL-DEEN | Militry /MINE./EGPC/Env. Approval
MOHAMED MAMDOUH | YES/ NO NEED / VERBAL/IN PROGRESS
20" CONDUCTOR @ 20' PEN
9 5/8" CSG (36#, K-55 , BTC) @ 3535'
02-27063297 (C.M) | (16 FT INTO APOLL. FM)
01050025318 (C.M) | 7" CSG(26,N-80, BTC) @ 7000'
01283909320 (C.M)
VHF RADIO(CHANNEL8)
02-24062575 (T.P.).
012-71119760 (T.P.).
PLAN TO USE DIVERTER ON SURFACE
RIG SUPT: EL-SAYED HAMZA | OFFSET WELL'S:
012-28916988 | MRZK-164 & MRZK-189
PMP:
VSAT : 980-0331 | TD: 7,000'
EDC - 76 | WD 09-A02
2000 HP/TDS (BPM)/RKB: 35' | WIW
10K PSI BOP | XXXXX
RATED DRLG DEPTH: 15,000' | Militry /MINE./EGPC/Env. Approval
ISLAM THABET | YES/NO NEED /NO/NO/SHALLOW GAS
20" CONDUCTOR @ 60' PEN
13 3/8" CSG (68#, K-55, BTC) @ XXX'
( XXX' INTO APOLL.)
0227063297 (C.M) | 9-5/8" CSG(43.5#,47,N-80, BTC) @ XXX
XXXX (C.M) | (+/-XXX FT INTO A/R-A FM.)
XXXX (C.M) | 7" LINER @ XXX'
02-24062576 (T.P.).
0100-1560459 (T.P.).
PLAN TO USE DIVERTER ON SURFACE
RIG SUPT: EL-SAYED HAMZA | OFFSET WELL'S:
012-28916988 | XXXXX
PMP:
VSAT :980-0136 | TD: 14,000'
ISLAM DAHSHAN | STAN JACKSON
TELE: 01000031114-01271488855 | TELE: 01277612182
RIG | WELL
EDC - 12 | MAGGIE-1X
750 HP, 11"-10K BOP, 280 KLB. | R/C (Part-03) Retrieve Kill STG, continue Re-entry the well down and complete the well
KELLY / MAIN CAMP. | on LSAFA reservoir TOP & BTM intervals.
AYMAN ASHRAF
SQUEEZED CSG LEAK INTERVAL (4448' - 5331')
02- 27063393 (C.M) | SQUEEZED AEB-3C&3D (9600'- 9610') 10' & (9664'-9688') 14'
01099938913 (C.M)
01227640638 (C.M)
01221112147 (T.P) | TIE-BK T.O.L @ 12381'
V-SAT : 980-0981
RIG SUPT: AHMED ASHOUR | 7" B.PLUG @ 15100'
1204432182 | 7" CSG (29 #, N-80, BTC) @15436'
PMP: 3704 | PBTD @ 15305 FT
HT - 101 | WKAL-N04
5K BOP, 1000 HP, 300 KLB. | R/C
KELLY / MAIN CAMP.
RIG ELEVATION : 19.7 FT
AHMED HENDY
MOHAMED MANSI | 7" T.O.L @ 9483 FT
7" LINER @ 14,997 FT ( 29 # , N- 80 , BTC ).
010-11423838 (C.M)
012-05776661 (C.M)
012-82924217 (T.P)
SUP. INT: WALID ZAYTONA
012-74833838
VHF Radio channel 8
(NOT WORKING) | PBTD (BP) @ 14489'
PMP: 3745
NDC-04 | RIDGEWOOD-03
750 HP / KELLY | I/C Scrapper, polish/dress TOL,
11"- 5K PSI BOP, 290 KLB'S | Dipole Sonic, perforate/test LBAH reservoir (S&S) completion.
AHMED GAMAL | LBAH RES PRESS: +/- 4650 PSI
MOHAMED MAGDY
01212582491(C.M)
01279232426 (T.P)
01228432312 (T.P)
T.O.7" LINER @ 7636 '
Rig Superintendent Eng | MAX. INC. 59.54 DEG @ 10456'
AMR ZIDAN
012-77442999 | P.B.T.D. @ 12330'
V-SAT : 980-0232
PBTD @ 12330'
MOHAMED ABDALLA | CHARLIE KENEEDY
TELE: 01000031117 / 01226762111 | TELE: 01201112590
RIG | WELL
EDC - 31 | NU-10
350 HP, 5K PSI BOP, 100 KLB | R/W (Re-Perforation), TBG & PR
ORKB: 22' (EDC-61)
BESHOE SAFWAT
9 5/8" CSG @ 4723'
7" CSG @ 11900'
01094478008(C.M)
01285026749(C.M)
02-24062531(T.P) | 7" PHL PKR @ 9493'
3 1/2"ON-OFF TOOL BTM PART@ 9483'
RIG SUPT: AHMED FOUAD | T.O.F (RELEASED GUNS) @ 11529'
012-00614093
PMP: 3760 | P.B.T.D @11823' (CORRELATED)
EDC - 82 | MENES-63
500 HP, 5K PSI BOP , 170 KLB. | I/C
P. SWIVEL / FLY CAMP | 4 1/2" CSG GUN / HYD FRAC
RIG ELEVATION.: 13'.
FAHD GAMAL
AHMED EL GHARIEB | 9 5/8" CSG @2,855 FT,(36#,K-55 , BTC)
7" CSG @ 11,600 FT (29 & 26 PPF, N-80, BTC)
01203311271 (C.M)
KOP @ 7755
MAX. ANG. 22.6 DEG @ 8858 FT
RIG SUPT: AHMED FOUAD
012-00614093
PMP: 5923 | PBTD (F.COLLAR) @ 11,516 FT
EDC - 84 | WKAN-T03X
500 HP, 5K PSI BOP, 240 KLB. | I/C, Wellbore Scrapper, Perforate/Test Safa reservoir, isolate same, then
POWER SWIVEL/FLY CAMP | perforate/test/acidize ALM-DOL and completion with suitable pump.
RIG ELEVATION: 12.5'
MOH.SALAH EL DEEN
AHMED FATOH
01050025782 (C.M.) | 7" T.O.L @ 8623'
01282161785 (C.M.) | 9 5/8" CSG @ 8886'
01221112123 (T.P)
02-24062584 (T.P) | *** ON OFF TOOL @ 11,993'
RIG SUPT:AHMED ASHOUR | *** 7" PHL PKR.12,000.5'
012-04432182
V-SAT :980-0841
PMP:3726 | PBTD @ 14,412'
MOHAMED ABDALLA | CHARLIE KENEEDY
TELE: 01000031117 / 01226762111 | TELE: 01201112590
RIG | WELL
EDC - 86 | SWAG N-06
5K PSI BOP, 500 HP ,240 KLB | I/ C
POWER SWIVEL/CAMP/12.5' | Test ARG reservoir through S&S completion STG, then Hyd Frac & test same, and completion with suitable pump.
SAMIER ASHMAWY
AHMED ELNAWAGY
012-75111153 (C.M)
MAX DLS 3.92 @9108 FT-ORKB
012-21110006 (T.P) | MAX INC 7.89 @9204 FT-ORKB
0224062586 (T.P) | T. O 7" LINER @ 8676'
RIG SUPT: AHMED ASHOUR
1200614568
VHF RADIO (CH-10)
V.SAT: 980-0781 | PBTD (L.C) @ 11823 FT-ORKB
EDC - 87 | WKAL-O02
500 HP, 11-5K PSI BOP,240 KLB. | R/C,Retrieve ESP completion and complete the well with single WI String.
POWER SWIVEL/FLY CAMP
RIG ELEVATION.: 11.5'.
JOHN KARAM
7'' T.O.L @ 8,687 FT
7” L.SHOE @ 15,447 FT (29#, N-80, BTC)
01227640906 (C.M.)
01016372666 (C.M.) | MAX INC = 30.19° @ 10,590'
01201508884 (T.P) | MAX D.L.S = 2.85° @ 9,931'
ON OF TOOL DEPTH @ 12992'
RIG SUPT: AHMED FOUAD
012-00614093
PMP: 3722 | PBTD @ 15,318'
EDC - 91 | TAYIM-N04
500 HP, 5K PSI BOP, 240 KLB | R/C
POWER SWIVEL/CAMP/13.2'. | EXPECTED PROD. RATE =300 BOPD
MOH. ABDEL HAMEED
MOH. SAID ABDEL KADER | 7" T.O.L (CORRELATED) @ 8,948'
010-04666721 (C.M) | 7" CSG @ 14,997' (29# ,N-80, BTC)
012-71474140 (C.M)
012-21118788 (T.P)
7" B.P. @ 13400'
RIG SUPT: MAHMOUD ESMAT
012-01544463
V-SAT:980-0155
PMP: 3713 | PBTD (CORRELATED) @ 14,830'
EDC - 95 | PTAH-30
5K BOP, 500 HP, 240 KLB. | TBG & PR
POWER SWIVEL / (F.UNIT)
AHMED SABRY | EST. PROD. RATE = 200 BOPD
012-26749111 (C.M) | 9 5/8'' CSG @ 2,730 FT
010-16416661(C.M) | 7'' CSG @ 12,800 FT
VHF Radio channel 8
01271469246 (T.P) | MAX INC. 13.1 @ 12676'
V.SAT: 980-0161 | MAX D.L.S 1.85 / 100' @ 12,486'
RIG SUPT: AHMED MAGDY
1207777038
PMP: 3757 | PBTD @ 11,694' ( CORR.)
MOHAMED ABDALLA | CHARLIE KENEEDY
TELE: 01000031117 / 01226762111 | TELE: 01201112590
RIG | WELL
EDC - 90 | KARANIS-05
10K BOP, 750 HP, 280 KLB. | I/C (500-1000 BOPD)
KELLY / CAMP.(F.UNIT.) | PERFORATE/TEST AEB-01 INTERVALS (8,980-8,995) 15 FT
RIG ELEVATION : 20.2 FT | & (8,808-8,820) 12 FT AND COMPLETE THE WELL WITH SUITABLE PUMP STRING
AHMED MAGDY
AHMED ABDELGHAFAR
012-71484448 (C.M) | 9 5/8” CSG (43.5#, N-80, BTC @ 8,803 ft)
010-06664098 (C.M) | 7" LINER CSG SHOE (29 PPF, N-80, BTC) @ 15,147'
02- 27063376 (C.M) | 8 1/2" HOLE TD @ 15,150'.
0224062590(T.P)
012-21112148 (T.P) | T.O. 7"LINER @ 8,560 ft CORRELATED
SUP. INT: AHMED MAGDY | PBTD L.C @ 15,066 ft
01207777038
VHF RADIO (CHANNEL 8)
VSAT : 980 - 0161
PMP: 3759
ECDC-9 | SIWA-V1X (ST)
TBG & PR (115 BOPD)
750 HP / KELLEY / RKB: 23' | 13 3/8" CSG @ 1895' ( 68 #, K-55, BTC)
5K PSI BOP / CAMP/ 400 KLB | 9 5/8" CSG @ 12300' ( 43.5,47 #, N-80, BTC)
ISLAM ABDEL RAHAN
MOHAMED GEHAD | 7" T.O.LINER @ 11761'
010-98983763 (C.M) | 5" T.O.L @ 13374'.
012-26348631 (C.M) | 5" L.C @ 14618'
010-99590109 (T.P)
012-72520145 (T.P) | MAX. INCLINATION 7.81 DEG @ 14531'
RIG SUPT: ALI AMEEN | MAX. DOG LEG 2.79 DEG @ 14150'
010-99164227 | MAX. INCLINATION 7.81 DEG @ 14531'
PMP: 3738
EDC - 32 | KAR-SW27
(ESPR) ( 90 BOPD)
5K BOP, 350 HP, 100 KLB. | 30" COND @ 115 FT-ORKB
HAGAG AWAD | 13 3/8" CSG @ 1980 FT-ORKB (68 PPF, K55, BTC)
0227063623 - 5032 (C.M.) | 9 5/8" CSG @ 5467 FT-ORKB (43.5 PPF, L-80, BTC)
01203311317 (C.M.) | 7" Liner SHOE@ 8070 FT-ORKB (29 PPF, L-80, BTC)
0224062532 (T.P)
RIG SUPT: AHMED FOUAD | T.O.F. @ 7530FT-ORKB
01200614093 | 7'' T.O.L@ 5177 FT-ORKB
7" B. PLUG @ 7540 FT -ORKB
MAX. INC. 21.1⁰ @6478' M.D.
MAX. D.L. 3.96⁰/100 FT@ 5,821
HATEM ZEDAN | CHARLIE KENEEDY
TELE: 01013334559 / 01272363263 | TELE: 01201112590
RIG | WELL
EDC - 83 | WD-33-15-11
500 HP, 5K PSI BOP , 240 KLB. | I/C ( BASED ON TEST) perforate/test ARC reservoir interval
P. SWIVEL / FLY CAMP | (5,134-5,172) 38 ft and complete the well with suitable pump string.
RIG ELEVATION.: 11'.
KARIM ABDEL AZIM
ARC RES PRESS: +/- 800PSI
01275238785 (C.M) | ARC RES TEMP: +/- 160 ° F
01275238785 (C.M)
0-227063269 | 13 3/8" CSG (68#, K-55 , BTC) @ 1482'
V-SAT:980-0362 | 9 5/8"INTER. CSG (43.5#,N-80,BTC) @ 4060'
01205552275 (T.P) | 7'' LINER SHOE @ 7,030'
RIG SUPT: AHMED FOUAD | T.O. 7" LINER (29#,N-80,BTC) @ 3628.2'
01200614093 | (PBTD) 6951'
EDC - 85 | ERZK-21
500 HP, 5K PSI BOP, 240 KLB
POWER SWIVEL/CAMP/ 12.5'
ESP UPGRADE
AHMED GAMIL
0227063297 (C.M) Land line
01282130364 (C.M)
02-227062585(T.P)
RIG SUPT: MAHMOUD ESMAT
PBTD @ 6,195' (F.C)
012-01544463
PMP : 6602
EDC - 88 | BERENICE-33
500 HP / POWER SWIVEL | I/C
11"- 5K PSI BOP , 240 KLB'S | Perforate/test AEB-3E reservoir and complete well with ESP no 13 % Cr TBG.
RIG ELEVATION.: 14.7'. | 9 5/8" CSG @ 4150 FT (94# , K-55 , BTC)
AMEER ELSAYED
7" CSG @ 13155 FT (29 & 26 PPF,N-80, BTC)
01221729475 (c.m)
01006663917 (c.m)
PMP: 3720 | P.B.T.D. (F.COLLAR) @ 13077 FT
01205552208 (T.P).
VHF RADIO (CHANNEL 8)
RIG SUPT: AHMED MAGDY
01207777038
EDC - 89 | NRQ-9X
500 HP, 5K PSI BOP, 240 KLB | R/C (700-1500 BOPD)
POWER SWIVEL/CAMP/ 12.5' | RETRIEVE ESP COMP., RE-PERF. & ADD PERF.
AHMED EL DASH | THROUGH LBAH, PROD. TEST (S&P) AND
COMPLETE WELL W/ SUITABLE PUMP STRING.
01050025319(C.M)
01206111732 (C.M)
01221112152 (T.P)
RIG SUPT: MAHMOUD ESMAT
012-01544463 | 7" CSG (26PPF, N-80,BTC)@8476'
ITN:75297 | PBTD @ 8,289' (CORR.)
V.SAT: 980-0901 / 77-0901
01207777038
PMP :6603
HATEM ZEDAN | CHARLIE KENEEDY
TELE: 01013334559 / 01272363263 | TELE: 01201112590
RIG | WELL
EDC - 92 | NU-04
500 HP, 5K PSI BOP , 240 KLB. | TBG & PR.
P. SWIVEL / FLY CAMP | R/C (CONVERSION WIW) isolate DAHAB reservoir, perforate
RIG ELEVATION.: 11.5'. | AEB-3D reservoir & test its injectivity (option Stimulation), then complete well
with WI String.
MAHMOUD ADEL ZAKY
KEROLES SOBHY
9 5/8" CSG (43.5#,N-80 )@ 4730'
012-77706931 (C.M) | LAST TAG: SAP. E/L RIH E/ 6" GR-JB
010-00194097 (C.M) | ON CCL TILL TAGGED OBST @ 11550'
0224062592 (T.P) | 7'' F.COLLAR @ 11816' ORKB
01221112166 (T.P) | 7" CSG ( 304 JTS ) @ 11900 FT
RIG SUPT: AHMED ashor
012-00614093
VHF RADIO (CHANNEL 8)
V.SAT: N/A
PMP: 3721
EDC - 93 | WKAL-A14
500 HP, 5K PSI BOP, 240 KLB | TBG & PR (ESP PKR)
KELLY/CAMP/ 17'. | (140 BOPD)
MOH MAGDY
DEVIATED WELL
01202543018 (C.M) | MAX. INC., 47.09˚ @ 9,940'
01033345012 (C.M) | MAX. DOG LEG 3.39 ˚/100 @ 9186'
01200613123 (T.P)
02-24062593 (T.P)
7" CSG (29 & 26 PPF, N-80, BTC) @ 13,500'
RIG SUPT: MAHMOUD ESMAT | PBTD: 7" B.P @ 12,850' CAP W/ 10 FT CMT
012-01544463
PMP: 3749
EDC-97 | MENES-33
5K BOP, 500 HP, 240 KLB.
POWER SWIVEL / (F.UNIT.) | R/W & PR (400 BOPD)
MOHAMED EL SHAWAAF
9 5/8" CSG ( 36#,K-55, BTC ) @ 2,790 ft
VHF RADIO (CHANNEL 8)
01011152087 (CM)
01202542721(C.M) | P.B.T.D (CORRELATED) @ 11,952 FT
01203377774 (T.P)
RIG SUPT: AHMED MAGDY | F.C @ 11,967'
1207777038 | 7" CSG ( 26, 29 #, N-80, BTC ) @ 12,049
V-SAT:980-0951
PMP: 3707
HATEM ZEDAN | CHARLIE KENEEDY
TELE: 01013334559 / 01272363263 | TELE: 01201112590