## Teams_Follow_Up
Team No. | Audit/Drops | Rig No. | Well Name | Field | Job Type | Job No. | Starting Date | Job Days | Expected Rig
1 | Audit | EDC-62 | PTAH-48 | Kalabsha | RA-3 | D_RA23_62_99999 | 2023-08-12 | 5 | EDC-48
2 | Audit | ECDC-9 | SIWA-V1X (ST) | Fagora | CA | D_CA23_ECDC-9_31 | 2023-08-12 | 2 | EDC-92
3 | Audit
1 | Drops
2 | Drops
3 | Drops

## Critical_Points_Follow_Up
Rig No. | Point | Description | Final Status
ECDC-9 | 5.1 | - Multiple of Non-conformity for derrick climber system assembly as following: * Counter weight attached on mast guy line. * Moveable wire rope sling for climber assist create cross and friction condition with guy line wire. * Individually guide line for counter weight not available. All above may lead for severe injuries and property damage, in case of wind gusts exist and personal using the system for climbing there will be an wind effect and force on mast and guy lines lead the guy lines slightly shacking included the attached climber system that's effects will pass to the user. Property damage may happen for the guy line wire and movable climb assist wire rope sling due to the friction condition. Recommendations: * Remove the climber assist counter weight from guy line. * Providing the rig with proper climber assist guide line as per the OEM recommendation and fixed individually. * 3rd party to inspect the guy line affected by friction condition and moveable wire rope sling attached with counter weight. * Proper method of clamping and to use the fist grip clamp. * Providing Climber assist COC, manual and thorough examination. (Zone#5 – Item No: 5.6.57). | Open
EDC-42 | 1 | A | Open
EDC-42 | 2 | B | Closed
EDC-42 | 3 | C | Closed
EDC-42 | 4 | D | In Progress

## Sheet1
Rig No. | Point | Description | Final Status